## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhandani Piped Water Supply Scheme at Dhupguri Block | SM/06958 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna including retrofitting of existing LDS under the command area of BHANDANI piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. Phase-II | Assistant Engineer,HQ | Junior Engineer | ORD/000207/2020-2021 | 42/JD | 06/01/2021 | 06/04/2021 | DULAL CHOUDHURY | 38.46 | 12.41 | 32.26 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhandani Piped Water Supply Scheme at Dhupguri Block | SM/06958 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Bhandani piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase- III) | Assistant Engineer,HQ | Junior Engineer | ORD/000210/2020-2021 | 49/JD | 07/01/2021 | 08/03/2021 | ASIM GUPTA | 39.45 | 78.83 | 199.81 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhandani Piped Water Supply Scheme at Dhupguri Block | SM/06958 | Retrofitting | FHTC BHANDANI PWSS |  |  | VCH/000339/2021-2022 |  | 04/10/2021 | 04/10/2021 | ASIM GUPTA | 18.14 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhandani Piped Water Supply Scheme at Dhupguri Block | SM/06958 | Retrofitting | FHTC BHANDABNI PWSS |  |  | VCH/000325/2021-2022 |  | 01/10/2021 | 01/10/2021 | ASIM GUPTA | 18.14 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhandani Piped Water Supply Scheme at Dhupguri Block | SM/06958 | Retrofitting | providing fhtc for Mathachulka pwss |  |  | VCH/000376/2021-2022 | 281 | 26/09/2021 | 26/09/2021 | DEEP CONSTRUCTION | 4.67 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhandani Piped Water Supply Scheme at Dhupguri Block | SM/06958 | Retrofitting | FHTC BHANDANI |  |  | VCH/000249/2022-2023 | BP-2022-23-66 | 04/07/2022 | 04/07/2022 | DULAL CHOUDHURY | 8.03 | 0 | 0 | 0
Total | [13 empty] | 126.9 | 91.24 | 71.9