## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Sajnapara Mouza under Sajnapara Piped Water Supply Scheme | SM/06959 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Pradhanpara Mouza under SAJNAPARA piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  | Junior Engineer | ORD/000327/2020-2021 | 221/JD | 12/02/2021 | 14/03/2021 | RAGHU DAS | 23.09 | 0 | 0 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Sajnapara Mouza under Sajnapara Piped Water Supply Scheme | SM/06959 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Sajnapara Mouza under SAJNAPARA piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000190/2020-2021 | 1543/JD | 31/12/2020 | 16/03/2021 | RAGHU DAS | 39.54 | 35.7 | 90.3 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Sajnapara Mouza under Sajnapara Piped Water Supply Scheme | SM/06959 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of ARGIGORALBARI piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (Part-C) |  | Junior Engineer | ORD/000083/2020-2021 | 1268/JD | 18/11/2020 | 16/02/2021 | NARAYAN CHAKRABORTY | 36.96 | 6.88 | 18.61 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Sajnapara Mouza under Sajnapara Piped Water Supply Scheme | SM/06959 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of CHAUHADDI piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  | Junior Engineer | ORD/000311/2020-2021 | 289/JD | 23/02/2021 | 25/03/2021 | HARIPADA BANERJEE | 24.4 | 23.53 | 96.43 | 1
5 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Sajnapara Mouza under Sajnapara Piped Water Supply Scheme | SM/06959 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Goralbari (Zone-III) Piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division P.H.E. Dte.( Part-B). |  | Junior Engineer | ORD/000477/2020-2021 | 61/RWS | 09/02/2021 | 24/02/2021 | NEW KUNDU ENTERPRISE | 4.09 | 4.09 | 100 | 1
Total | [13 empty] | 128.09 | 70.2 | 54.81