## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dakshin Dangapara & Dambari Mouza Under Patkidaha Piped Water Supply Scheme | SM/06961 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Dambari Mouza under Patkidaha piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000197/2020-2021 | 1541/JD | 31/12/2020 | 14/02/2021 | KULDIP KAPOOR | 24.3 | 32.14 | 132.28 | 80
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dakshin Dangapara & Dambari Mouza Under Patkidaha Piped Water Supply Scheme | SM/06961 | Retrofitting | PROVIDING FHTC UNDER PORA PARA |  |  | VCH/001174/2020-2021 | 1044 | 11/01/2021 | 11/01/2021 | SUKES BASU MAJUMDAR | 4.45 | 0 | 0 | 0
Total | [13 empty] | 28.74 | 32.14 | 111.82