## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Engo Tea Garden Piped Water Supply Scheme at Matiali Block | SM/07301 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Engo T.G. area PWSS at Matiali Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  | Junior Engineer | ORD/000243/2020-2021 | 561/JSSD | 01/02/2021 | 16/02/2021 | JOYDEB SAHA | 4.64 | 9.28 | 199.96 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Engo Tea Garden Piped Water Supply Scheme at Matiali Block | SM/07301 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of ENGO T.G. Area Piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte (PART-C) |  | Junior Engineer | ORD/000072/2021-2022 | 63/JSSD | 13/05/2021 | 28/05/2021 | BIMAN DAS | 2.34 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Engo Tea Garden Piped Water Supply Scheme at Matiali Block | SM/07301 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of ENGO T.G. Area Piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte (PART-D) |  | Junior Engineer | ORD/000067/2021-2022 | 59/JSSD | 12/05/2021 | 27/05/2021 | PRITAM DUTTA | 1.87 | 3.47 | 184.97 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Engo Tea Garden Piped Water Supply Scheme at Matiali Block | SM/07301 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of ENGO T.G. Area Piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte (PART-B) |  | Junior Engineer | ORD/000075/2021-2022 | 68/JSSD | 19/05/2021 | 03/06/2021 | NABIN PRODHAN | 2.35 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Engo Tea Garden Piped Water Supply Scheme at Matiali Block | SM/07301 | Retrofitting | Preparation of D.P.R. (consultancy work) in connection with Augmentation of Matially PWSS (Matially block) under Jalpaiguri Division PHED |  |  | ORD/000539/2021-2022 | .93/JSSD | 10/06/2021 | 10/07/2021 | SUBHANKAR GHOSH | 1.99 | 0 | 0 | 0
Total | [13 empty] | 13.19 | 12.75 | 96.64