## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Patkidaa & Jakhaikona Mouza under Patkidaha Piped Water Supply Scheme | SM/07304 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Patkidaha and Jakhaikona Mouza under Patkidaha piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte |  | Junior Engineer | ORD/000326/2020-2021 | 209/JD | 11/02/2021 | 13/03/2021 | PRABIR SHOME | 21.88 | 0 | 0 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Patkidaa & Jakhaikona Mouza under Patkidaha Piped Water Supply Scheme | SM/07304 | Retrofitting | PROVIDING FHTC FOR PURBA MAGURMARI PWSS |  |  | VCH/000239/2021-2022 | 192/21-22 | 02/08/2021 | 02/08/2021 | A.P CONSTRUCTION | 25.1 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Patkidaa & Jakhaikona Mouza under Patkidaha Piped Water Supply Scheme | SM/07304 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Argi Goralbari piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-D) |  | Junior Engineer | ORD/000183/2020-2021 | 1498/JD | 22/12/2020 | 21/01/2021 | BISWAJIT BHADURI | 17.51 | 10.76 | 61.47 | 1
Total | [13 empty] | 64.49 | 10.76 | 16.69