## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block | SM/07891 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of PURBA MAGURMARI piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000313/2020-2021 | 291/JD | 23/02/2021 | 25/03/2021 | A.P CONSTRUCTION | 24.41 | 0 | 0 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block | SM/07891 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Purba Magurmari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-III) | Assistant Engineer,HQ | Junior Engineer | ORD/000055/2021-2022 | 1075/JD | 02/07/2021 | 01/08/2021 | ARATI CONSTRUCTION | 24.34 | 0 | 0 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block | SM/07891 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna at Purba Magurmari and Paschim Magurmari village under the command area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000188/2021-2022 | 1690/JD | 28/10/2021 | 27/11/2021 | ANUP SARKAR | 24.44 | 0 | 0 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block | SM/07891 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Purba Magurmari and Paschim Magurmari and Jhar Magurmari village under the command area of Purba Magurmari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-IV) | Assistant Engineer,HQ | Junior Engineer | ORD/000266/2021-2022 | 2044/JD | 07/12/2021 | 28/12/2021 | ARATI CONSTRUCTION | 39.59 | 0 | 0 | 1
5 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block | SM/07891 | Retrofitting | fhtc for purba magurmari pwss |  |  | VCH/000462/2021-2022 |  | 21/10/2021 | 21/10/2021 | MONOJ GHOSH | 16.71 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block | SM/07891 | Retrofitting | FHTC PURBA MAGURMARI |  |  | VCH/000793/2021-2022 | BP-2021-22-90 | 01/11/2021 | 01/11/2021 | MANOJ GHOSH | 16.71 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block | SM/07891 | Retrofitting | fhtc for purba magurmari pwsws |  |  | VCH/000461/2021-2022 |  | 21/10/2021 | 21/10/2021 | ARATI CONSTRUCTION | 17.45 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block | SM/07891 | Retrofitting | Providing Functional Household Tap Connection in connection with Jal Swapna/ JJM with minor retrofitting works at various mouza under command area of Purba Magurmari Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. (Phase-V) | Assistant Engineer,HQ | Junior Engineer | ORD/000092/2022-2023 | 1291/JD | 14/06/2022 | 05/07/2022 | ARATI CONSTRUCTION | 4.8 | 0 | 0 | 1
9 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block | SM/07891 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000074/2024-2025 | 2205/JD | 01/12/2024 | 01/12/2024 | Resource Division | 28.93 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block | SM/07891 | Retrofitting | Laying of Distribution System along with Functional Household Tap Connection (Phase-VI) in connection with Jal Jeevan Mission under Rejuvenation of Purba Magurmari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000425/2022-2023 | 628/JD | 13/03/2023 | 16/04/2025 | SANKAR DAS | 43.78 | 0 | 0 | 60
11 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block | SM/07891 | Retrofitting | Laying of Rising Main/Direct Boosting Line for The Rejuvenation of Purba Magurmari P.W.S.S and Rejuvenation of Chouhaddi P.W.S.S. along with FHTC(PhaseVII) within the command area of Rejuventaion of Purba Magurmari P.W.S.S. in connection with Jal Jeevan Mission under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000397/2023-2024 | 1587/JD | 06/11/2023 | 01/11/2025 | SAHA CONSTRUCTION | 37.11 | 0 | 0 | 30
Total | [13 empty] | 278.25 | 0 | 0