## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block | SM/07892 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of KHALAIGRAM piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000315/2020-2021 | 290/JD | 23/02/2021 | 15/03/2021 | PARESH CHANDRA ROY | 12.8 | 0 | 0 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block | SM/07892 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of KHALAIGRAM piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  | Junior Engineer | ORD/000314/2020-2021 | 296/JD | 24/02/2021 | 26/03/2021 | M/S SIBU DEY AND CO. | 24.41 | 0 | 0 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block | SM/07892 | Retrofitting | shifting of pipe line khalaigram |  |  | VCH/000341/2021-2022 | null | 05/10/2021 |  | LOKNATH CONSTRUCTION | 9.83 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block | SM/07892 | Retrofitting | FHTC KHALAIGRAM |  |  | VCH/000482/2021-2022 | null | 29/10/2021 |  | M/S SIBU DEY AND CO. | 22.47 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block | SM/07892 | Retrofitting | SHIFTING OF PIPE LINE FOR KHALAIGRAM PWSS |  |  | VCH/000673/2021-2022 | BP-2021-22-77 | 08/10/2021 |  | LOKNATH CONSTRUCTION | 9.83 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block | SM/07892 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna including retrofitting of existing LDS under the command area of Khalaigram Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase- III) | Assistant Engineer,HQ | Junior Engineer | ORD/000249/2021-2022 | 1990/JD | 03/12/2021 | 02/01/2022 | M/S R.N. TRADERS | 47.9 | 9.31 | 19.44 | 1
7 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block | SM/07892 | Retrofitting | fhtc khalaigram |  |  | VCH/000807/2021-2022 | BP-2021-22-94 | 13/11/2021 |  | M/S SIBU DEY AND CO. | 22.47 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block | SM/07892 | Retrofitting | IEP FOR RAIPUR T.G |  |  | VCH/000060/2022-2023 | BP-2021-22-24 | 26/04/2022 |  | MONDAL PRECISION PRIVATE LIMITED | 2.39 | 0 | 0 | 0
Total | [13 empty] | 152.11 | 9.31 | 6.12