## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block | SM/07893 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase- IV) | Assistant Engineer,HQ | Junior Engineer | ORD/000111/2021-2022 | 1405/JD | 03/09/2021 | 03/10/2021 | RABINDRANATH DUTTA | 23.6 | 19.54 | 82.83 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block | SM/07893 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000099/2021-2022 | 1338/JD | 23/08/2021 | 22/09/2021 | ASIT PAUL | 30.22 | 44.3 | 146.61 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block | SM/07893 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Chauhaddi piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. Phase-III | Assistant Engineer,HQ | Junior Engineer | ORD/000105/2021-2022 | 1256/JD | 10/08/2021 | 25/08/2021 | HARIPADA BANERJEE | 4.81 | 0 | 0 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block | SM/07893 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of CHAUHADDI piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  | Junior Engineer | ORD/000311/2020-2021 | 289/JD | 23/02/2021 | 25/03/2021 | HARIPADA BANERJEE | 24.4 | 0 | 0 | 1
5 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block | SM/07893 | Retrofitting | fhtc chauhaddi |  |  | VCH/000345/2021-2022 |  | 05/10/2021 | 05/10/2021 | ASIT PAUL | 22.15 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block | SM/07893 | Retrofitting | fhtc chauhaddi |  |  | VCH/000344/2021-2022 |  | 06/10/2021 | 06/10/2021 | RABINDRANATH DUTTA | 9.77 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block | SM/07893 | Retrofitting | FHTC GORALBARI |  |  | VCH/001349/2021-2022 | BP-2021-22-454 | 27/03/2022 | 27/03/2022 | SAPTASWA SARKAR | 2.69 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block | SM/07893 | Retrofitting | HDPE UTTAR ANGRAVASA PWSS |  |  | VCH/001328/2021-2022 | BP-2021-22-461 | 27/03/2022 | 27/03/2022 | ROY & SARKAR CONSTRUCTION | 4.89 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block | SM/07893 | Retrofitting | RETRO FITTING WOR FOR GORALBARI ZONE -I |  |  | VCH/001427/2021-2022 | BP-2021-22-455 | 27/03/2022 | 27/03/2022 | SAPTASWA SARKAR | 3.67 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block | SM/07893 | Retrofitting | FHTC KAMARVITA VILLAGE RAJGANJ BLOCK |  |  | VCH/001382/2021-2022 | BP-2021-22-444 | 26/03/2022 | 26/03/2022 | BARUN KUMAR DUTTA | 3.63 | 0 | 0 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block | SM/07893 | Retrofitting | FHTC GORALBARI ZONE - I |  |  | VCH/001419/2021-2022 | BP-2021-22-453 | 27/03/2022 | 27/03/2022 | SAHA CONSTRUCTION | 3.49 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block | SM/07893 | Retrofitting | Providing Functional Household Tap Connection in connection with Jal Swapna/ JJM with minor retrofitting works under Rejuvenation of Chauhaddi Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. (Phase-V) | Assistant Engineer,HQ | Junior Engineer | ORD/000093/2022-2023 | 1292/JD | 14/06/2022 | 29/06/2022 | ASIT PAUL | 1.69 | 1.72 | 101.85 | 0
Total | [13 empty] | 135.02 | 65.57 | 48.56