## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Porapara piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (Part-E) |  | Junior Engineer 2 | ORD/000028/2021-2022 | 748/JD | 13/05/2021 | 12/06/2021 | DEBASISH DEY | 30 | 0 | 0 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Providing Functional House hold tap Connection (FHTC ) in connection with Jaldhara/ Jalsapna under the command area of PORAPARA W/S/S at Sadar Block under Jalpaiguri Division , P.H.E Dte. (part ¿ G) |  | Junior Engineer 2 | ORD/000165/2021-2022 | 674/RWS | 27/09/2021 | 12/10/2021 | SUKES BASU MAJUMDAR | 4.98 | 4.98 | 99.91 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of PORAPARA Water Supply Scheme at Sadar Block under under Jalpaiguri Division, PHE Dte. (PART-F) |  | Junior Engineer 2 | ORD/000095/2021-2022 | 1334/JD | 23/08/2021 | 07/09/2021 | B.M CONSTRUCTION | 14.64 | 16 | 109.26 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | FHTC PORA PARA PWSS |  |  | VCH/000332/2021-2022 |  | 01/10/2021 | 01/10/2021 | B.M CONSTRUCTION | 8 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | PORA PARA |  |  | VCH/000919/2021-2022 | BP-2021-22-117 | 03/12/2021 | 03/12/2021 | SUKES BASU MAJUMDAR | 4.56 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Retrofitting work related to FHTC in connection to Jalswapna at Haldibari Bypass, Najir Para under Pora para Piped Water Supply under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000279/2022-2023 | 644/RWS | 21/10/2022 | 10/11/2022 | B.M CONSTRUCTION | 4.34 | 4.34 | 100 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jalswapna, retrofitting of LDS and rising main connection of 3rd tube well & 4th Tube well site under Porapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-I) | Assistant Engineer | Junior Engineer 2 | ORD/000072/2022-2023 | 1298/JD | 14/06/2022 | 13/08/2022 | B.M CONSTRUCTION | 91.26 | 82.32 | 90.2 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission for Rejuvenation of Porapara PWSS at block- Jalpaiguri Sadar under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000538/2023-2024 | 1973/JD | 03/01/2024 | 24/01/2024 | B.M CONSTRUCTION | 21.19 | 21.15 | 99.8 | 100
9 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000083/2024-2025 | 2218/JD | 01/12/2024 | 01/12/2024 | Resource Division | 36.07 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Supply of Printer Logic Board, Relay, Power Supply Board and Toner for Office use. |  |  | BILL/00221/2025-2026 |  | 12/06/2025 | 12/06/2025 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.09 | 0 | 0 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Supply of Printer Power Supply, Logic Board, Toner and SSD of Office use. |  |  | BILL/00229/2025-2026 |  | 12/06/2025 | 12/06/2025 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Supply of Printer Power Supply, Logic Board, Toner and SSD for Office use. |  |  | BILL/00226/2025-2026 |  | 12/06/2025 | 12/06/2025 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Supply of Printer Power Supply Board, Logic Board, Pickup Roller and SSD for Office use. |  |  | BILL/00228/2025-2026 |  | 12/06/2025 | 12/06/2025 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
14 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Supply of Toner, Power Supply Unit, Logic Board and Printer Relay for Office use. |  |  | BILL/00231/2025-2026 |  | 12/06/2025 | 12/06/2025 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.09 | 0 | 0 | 0
15 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Supply of Mother Board, Logic Board and Relay for Office use. |  |  | BILL/00227/2025-2026 |  | 12/06/2025 | 12/06/2025 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
16 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Supply of Printer Logic Board, Teflon, Keyboard for Office use. |  |  | BILL/00223/2025-2026 |  | 12/06/2025 | 12/06/2025 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
17 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Supply of Toner and Printer Ink Bottle for Office use. |  |  | BILL/00225/2025-2026 |  | 12/06/2025 | 12/06/2025 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
18 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Supply of Mother Board and Printer Power Supply Board for Office use. |  |  | BILL/00222/2025-2026 |  | 12/06/2025 | 12/06/2025 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
19 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Supply of Toner, Cartridge, Logic Board for Office use. |  |  | BILL/00235/2025-2026 |  | 12/06/2025 | 12/06/2025 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
20 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Supply of Printer Power Supply Board and Mother Board for Office use. |  |  | BILL/00224/2025-2026 |  | 12/06/2025 | 12/06/2025 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
21 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Supply of Power Supply, Logic Board, Teflon, Pickup Roller and Keyboard for Office use. |  |  | BILL/00234/2025-2026 |  | 12/06/2025 | 12/06/2025 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
22 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Supply of Mother Board, SSD and Toner for Office use. |  |  | BILL/00232/2025-2026 |  | 12/06/2025 | 12/06/2025 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
23 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Supply of Logic Board, Magnetic Relay and Mother Board for Office use. |  |  | BILL/00230/2025-2026 |  | 12/06/2025 | 12/06/2025 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
24 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | Retrofitting | Supply of Power Supply Unit, Magnetic Relay, Teflon, Logic Board and Keyboard for Office use. |  |  | BILL/00233/2025-2026 |  | 12/06/2025 | 12/06/2025 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.09 | 0 | 0 | 0
Total | [13 empty] | 216.5 | 128.78 | 59.48