## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block | SM/08037 | Retrofitting | FHTC SATHKAYA TG PWSS |  |  | VCH/000338/2021-2022 |  | 04/10/2021 | 04/10/2021 | LOKNATH CONSTRUCTION | 22.44 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block | SM/08037 | Retrofitting | NH Road(4 Lane) crossing through underpass at Assam More .i.c.w. FHTC of Mohit Nagar W/S Scheme under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000281/2022-2023 | 646/RWS | 21/10/2022 | 20/11/2022 | M/S DEY & ROY CHOUDHURY | 3.86 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block | SM/08037 | Retrofitting | fhtc matiali bazar |  |  | VCH/001173/2021-2022 | BP-2021-22-233 | 23/02/2022 | 23/02/2022 | M/S DEY & ROY CHOUDHURY | 15.39 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block | SM/08037 | Retrofitting | FHTC DABGRAM-II |  |  | VCH/001256/2021-2022 | BP-2021-22-410 | 23/03/2022 | 23/03/2022 | SAHA CONSTRUCTION | 52.17 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block | SM/08037 | Retrofitting | FHTC BATABARI T.G |  |  | VCH/001162/2021-2022 | BP-2021-22-264 | 22/02/2022 | 22/02/2022 | PRIYABRATA KARMAKAR | 7.52 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block | SM/08037 | Retrofitting | FHTC JABRAMALI |  |  | VCH/001210/2021-2022 | BP-2021-22-332 | 28/02/2022 | 28/02/2022 | SUKES BASU MAJUMDAR | 12.67 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block | SM/08037 | Retrofitting | FHTC CHALAUNI |  |  | VCH/001161/2021-2022 | BP-2021-22-240 | 22/02/2022 | 22/02/2022 | BILTU DAS | 10.56 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block | SM/08037 | Retrofitting | FHTC BHANGARHAT PWSS |  |  | VCH/001311/2021-2022 | BP-2021-22-341 | 03/03/2022 | 03/03/2022 | BILTU DAS | 26.16 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block | SM/08037 | Retrofitting | FHTC MOHIT NAGAR |  |  | VCH/001147/2021-2022 | BP-2021-22-252 | 16/02/2022 | 16/02/2022 | ANUP KUMAR KUNDU | 20.15 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block | SM/08037 | Retrofitting | FHTC DAKSHIN SALBARI PWSS |  |  | VCH/001259/2021-2022 | BP-2021-22-402 | 23/03/2022 | 23/03/2022 | NARAYAN SARKAR | 20.51 | 0 | 0 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block | SM/08037 | Retrofitting | FHTC DAKSHIN SALBARI PWSS |  |  | VCH/001342/2021-2022 | BP-2021-22402 | 23/03/2022 | 23/03/2022 | NARAYAN SARKAR | 20.51 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block | SM/08037 | Retrofitting | FHTC MOHITNAGAR |  |  | VCH/000087/2022-2023 | BP-2022-2023-41 | 24/05/2022 | 24/05/2022 | M/S DEY & ROY CHOUDHURY | 7.1 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block | SM/08037 | Retrofitting | FHTC MOHIT NAGAR PWSS |  |  | VCH/001392/2021-2022 | BP-2021-22-550 | 31/03/2022 | 31/03/2022 | M/S DEY & ROY CHOUDHURY | 15.24 | 0 | 0 | 0
14 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block | SM/08037 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Sebagram In connection with Jaldhara/ Jal Sapna under the command area of Mohit Nagar W/S Scheme under Jalpaiguri Division PHE Dte. (PART-I) | Assistant Engineer | Junior Engineer | ORD/000333/2023-2024 | 1081/RWS | 19/09/2023 | 19/10/2023 | M/S DEY & ROY CHOUDHURY | 6.68 | 0 | 0 | 100
15 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block | SM/08037 | Retrofitting | Thorough repairing and overhauling of the Iron Elimination Plant (double Unit) at Mohitnagar Water Supply Scheme (H/W Site), under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000335/2023-2024 | 1083/RWS | 19/09/2023 | 04/10/2023 | M/S DEY & ROY CHOUDHURY | 5.41 | 0 | 0 | 100
Total | [13 empty] | 246.35 | 0 | 0