## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Goralbari (Zone-III) Piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division P.H.E. Dte.( Part-A). |  | Junior Engineer | ORD/000354/2020-2021 | 34/RWS | 28/01/2021 | 12/02/2021 | NARAYAN SARKAR | 4.82 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Goralbari (Zone-I) piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-B) |  | Junior Engineer | ORD/000053/2021-2022 | 1072/JD | 02/07/2021 | 01/08/2021 | SAHA CONSTRUCTION | 23.05 | 0 | 0 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Goralbari (Zone-II) piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-C) |  | Junior Engineer | ORD/000050/2021-2022 | 1073/JD | 02/07/2021 | 01/08/2021 | BISWAJIT BHADURI | 27.41 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | Providing functional household tap connection (FHTC ) in connetion with jaldhara / jal sapna under Arji Garalbari piped water supply scheme at Jalpaiguri Block under JAlpaiguri Division , PHE,Dte. (Part ¿ E) |  | Junior Engineer | ORD/000122/2021-2022 | 521/RWS | 30/07/2021 | 14/08/2021 | RANJIT KARMAKAR | 4.75 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | Over Hauling of the Iron Elimination plant at H/W site for Garalbari Zone ¿ II W/S/S under Jalpaiguri Division , P.H.E Dte |  | Junior Engineer | ORD/000179/2021-2022 | 684/RWS | 27/09/2021 | 17/10/2021 | BISWAJIT BHADURI | 3.9 | 0 | 0 | 1
6 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | Reparing and renovation of Boundary walls ( 2nd site ),pump house , including O.H.R for Goralbari Zone ¿ II W/S/S under Jalpaiguri Division , P.H.E Dte Jalpaiguri. |  | Junior Engineer | ORD/000175/2021-2022 | 681/RWS | 27/09/2021 | 27/10/2021 | BISWAJIT BHADURI | 4.67 | 0 | 0 | 1
7 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | Providing functional household tap connection (FHTC ) in connetion with jaldhara / jal sapna under garalbari Zone- iii piped water supply scheme at Jalpaiguri Block under JAlpaiguri Division , PHE,Dte. ( part - c) |  | Junior Engineer | ORD/000158/2021-2022 | 479/RWS | 23/07/2021 | 07/08/2021 | NARAYAN SARKAR | 2.53 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | Over Hauling of the Iron Elimination plant at 2nd site for Garalbari Zone ¿ II W/S/S under Jalpaiguri Division , P.H.E Dte |  | Junior Engineer | ORD/000176/2021-2022 | 682/RWS | 27/09/2021 | 17/10/2021 | BISWAJIT BHADURI | 3.9 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Garalbari (Zone-III) piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-H) |  | Junior Engineer | ORD/000269/2021-2022 | 2036/JD | 07/12/2021 | 28/12/2021 | J.M. CONSTRUCTION | 13.14 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Garalbari (Zone-III) piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-G) |  | Junior Engineer | ORD/000268/2021-2022 | 2035/JD | 07/12/2021 | 28/12/2021 | SOMNATH ROY | 17.26 | 0 | 0 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | RETROFITTING WORKS GORALBARI ZONE II |  |  | VCH/001344/2021-2022 | BP-2021-22-413 | 23/03/2022 | 23/03/2022 | BISWAJIT BHADURI | 2.21 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | FHTC GORALBARI |  |  | VCH/001429/2021-2022 | BP-2021-22-450 | 26/03/2022 | 26/03/2022 | BISWAJIT BHADURI | 27 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | RETROFITTING WORKS FHTC GORALBARI ZONE II |  |  | VCH/001800/2020-2021 | BP-2021-22- 414 | 23/03/2022 | 23/03/2022 | BISWAJIT BHADURI | 4.84 | 0 | 0 | 0
14 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | FHTC GORALBARI |  |  | VCH/001093/2021-2022 | BP-2021-22-146 | 14/01/2022 | 14/01/2022 | SAHA CONSTRUCTION | 23.03 | 0 | 0 | 0
15 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | FHTC DABGRAM |  |  | VCH/001181/2021-2022 | BP-2021-22-282 | 23/02/2022 | 23/02/2022 | NARAYAN CHAKRABORTY | 24.81 | 0 | 0 | 0
16 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | FHTC SONGACHI T.GG |  |  | VCH/001184/2021-2022 | BP-2021-22-2291 | 23/02/2022 | 23/02/2022 | M/S M.B. DESIGN | 15.73 | 0 | 0 | 0
17 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | fhtc charer bari |  |  | VCH/001227/2021-2022 | BP-2021-22-337 | 03/03/2022 | 03/03/2022 | NEW KUNDU ENTERPRISE | 2.44 | 0 | 0 | 0
18 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | retrofittinbg work for kajaldighi |  |  | VCH/001168/2021-2022 | BP-2021-22-237 | 22/02/2022 | 22/02/2022 | R.S CONSTRUCTION | 4.54 | 0 | 0 | 0
19 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | providing fhtc yong tong t.g |  |  | VCH/001170/2021-2022 | BP-2021-22-236 | 23/02/2022 | 23/02/2022 | ASHIT KUMAR SINGHA | 8.71 | 0 | 0 | 0
20 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | FHTC GORALBARI |  |  | VCH/001092/2021-2022 | BP-2021-22-145 | 14/01/2022 | 14/01/2022 | M/S SIBU DEY AND CO. | 37.86 | 0 | 0 | 0
21 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | FROVIDING FHTC FOR SAMSING T.G |  |  | VCH/001160/2021-2022 | BP-2021-22-258 | 22/02/2022 | 22/02/2022 | M/S. D.K. DEY & CO.. | 29.06 | 0 | 0 | 0
22 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | FHTC GORALBARI |  |  | VCH/001084/2021-2022 | BP-2021-22-160 | 14/01/2022 | 14/01/2022 | NARAYAN SARKAR | 2.6 | 0 | 0 | 0
23 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | FHTC PURBA MAGURMARI |  |  | VCH/001221/2021-2022 | BP-2021-22-334 | 03/03/2022 | 03/03/2022 | ARATI CONSTRUCTION | 7.42 | 0 | 0 | 0
24 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | FHTC NAYASYLI |  |  | VCH/001222/2021-2022 | BP-2021-22-336 | 03/03/2022 | 03/03/2022 | GAP ENGINEERS ENTERPRISES | 12.52 | 0 | 0 | 0
25 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | fhtc bhangarhat |  |  | VCH/001228/2021-2022 | BP-2021-22-341 | 03/03/2022 | 03/03/2022 | BILTU DAS | 26.16 | 0 | 0 | 0
26 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | water sup[ply arrangement for angawari center |  |  | VCH/001167/2021-2022 | BP-2021-22-277 | 22/02/2022 | 22/02/2022 | R.S CONSTRUCTION | 18.98 | 0 | 0 | 0
27 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | IEP GORALBARI |  |  | VCH/001209/2021-2022 | BP-2021-22-324 | 28/02/2022 | 28/02/2022 | BISWAJIT BHADURI | 3.87 | 0 | 0 | 0
28 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | fhtc rej nagrakata |  |  | VCH/001226/2021-2022 | BP-2021-22-338 | 03/03/2022 | 03/03/2022 | ANUP KUMAR KUNDU | 28.29 | 0 | 0 | 0
29 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | retrofitting work for goralbari pwss |  |  | VCH/001156/2021-2022 | BP-2021-22-253 | 22/02/2022 | 22/02/2022 | NEW KUNDU ENTERPRISE | 1.33 | 0 | 0 | 0
30 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | FHTC PURBA MAGURMARI |  |  | VCH/001220/2021-2022 | BP-2021-22-335 | 03/03/2022 | 03/03/2022 | MONOJ GHOSH | 7.74 | 0 | 0 | 0
31 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | PROVIDING FHTC PORAPARA |  |  | VCH/001164/2021-2022 | BP-2021-22-270 | 22/02/2022 | 22/02/2022 | DEBASISH DEY | 5.57 | 0 | 0 | 0
32 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | Providing fhtc for boalmari pwss |  |  | VCH/001157/2021-2022 | BP-2021-22-254 | 22/02/2022 | 22/02/2022 | KANAI LAL SEN | 3.62 | 0 | 0 | 0
33 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | FHTC GORALBARI |  |  | VCH/001428/2021-2022 | BP-2021-22-448 | 26/03/2022 | 26/03/2022 | ASHIM GUPTA | 62.4 | 0 | 0 | 0
34 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jalsapna under the command area of Garalbari Zone ¿ I . W/S/S under Jalpaiguri Division , P.H.E. Dte ( part ¿ C ) |  |  | ORD/000323/2021-2022 | 874/RWS | 08/12/2021 | 18/12/2021 | SAPTASWA SARKAR | 2.71 | 0 | 0 | 0
35 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal sapna under the command area of Garalbari zone - I. Water Supply Scheme under Jalpaiguri Division , P.H.E. Dte ( Part - D ) |  |  | ORD/000524/2021-2022 | 172/RWS | 03/03/2022 | 18/03/2022 | SAHA CONSTRUCTION | 3.41 | 0 | 0 | 0
36 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | Retrofitting works related to FHTC at Baraghaoria, Bhutiakhola for Garalbari Zone-II W/S/S under Jalpaiguri Division , P.H.E. Dte |  |  | ORD/000519/2021-2022 | 164/RWS | 28/02/2022 | 15/03/2022 | BISWAJIT BHADURI | 2.21 | 0 | 0 | 0
37 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | Retrofitting works related to FHTC at Nijbari,Hazari Para,Ambari,Harinagar for Garalbari Zone-II W/S/S under Jalpaiguri Division , P.H.E. Dte |  |  | ORD/000517/2021-2022 | 161/RWS | 28/02/2022 | 15/03/2022 | BISWAJIT BHADURI | 4.85 | 0 | 0 | 0
38 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | Retrofiting works at Tariapara, Barua para, Nawa para, Khansaheb para related to FHTC for Garalbari Zone ¿I WSS under Jalpaiguri Division , P.H.E. Dte. |  |  | ORD/000523/2021-2022 | 171/RWS | 03/03/2022 | 18/03/2022 | SAPTASWA SARKAR | 3.84 | 0 | 0 | 0
39 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | Retrofitting work related to FHTC at Balipara, Hazaripara and adjacent area within Garalbari zone-II W/S Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000133/2022-2023 | 1552/JD | 05/08/2022 | 26/08/2022 | BISWAJIT BHADURI | 18.01 | 18 | 99.91 | 0
40 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) including Retrofitting at Krishimandi, Petrol pump and adjacent area within Garalbari Zone-III under Jalpaiguri Sadar Block in connection with Jaldhara/ Jal Sapna under Jalpaiguri Division PHE Dte. (Part-L) | Assistant Engineer | Junior Engineer | ORD/000234/2022-2023 | 1862/JD | 20/09/2022 | 15/10/2022 | ASIM GUPTA | 15.65 | 15.64 | 99.95 | 1
41 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | Shifting of pipeline by PWD road widening work from Thuta Pakri to Nirashi Via comperhat at Goralbari Zone- II piped Water Supply Scheme Jalpaiguri Sadar Block under Jalpaiguri |  | Junior Engineer | ORD/000200/2019-2020 | 302/JD | 17/03/2020 | 15/07/2020 | BILTU DAS | 47.59 | 0 | 0 | 0
42 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) including Retrofitting at Jamuribari, Sovabhita, Pakuritala, Chandanidanga, Nayabari, Kohorapara and adjacent area within Garalbari Zone-II under Jalpaiguri Sadar Block in connection with Jaldhara/ Jal Sapna under Jalpaiguri Division PHE Dte. (Part-D) | Assistant Engineer | Junior Engineer | ORD/000202/2022-2023 | 1741/JD | 08/09/2022 | 23/10/2022 | PROVA CONSTRUCTION | 75.59 | 0 | 0 | 100
43 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Goralbari (Zone-III) piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-F) |  | Junior Engineer | ORD/000054/2021-2022 | 1074/JD | 02/07/2021 | 16/08/2021 | M/S SIBU DEY AND CO. | 36.93 | 0 | 0 | 0
Total | [13 empty] | 676.94 | 33.64 | 4.97