## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Basilardanga Piped Water Supply Scheme | SM/08077 | Retrofitting | fhtc basilardanga |  |  | VCH/000464/2021-2022 |  | 21/10/2021 | 21/10/2021 | PARESH CHANDRA GUHA | 16.39 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Basilardanga Piped Water Supply Scheme | SM/08077 | Retrofitting | FHTC BASILARDANGA |  |  | VCH/000794/2021-2022 | BP-2021-22-87 | 01/11/2021 | 01/11/2021 | PARESH CHANDRA GUHA | 16.39 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Basilardanga Piped Water Supply Scheme | SM/08077 | Retrofitting | fhtc basilar danga |  |  | VCH/000343/2021-2022 |  | 05/10/2021 | 05/10/2021 | PARESH CHANDRA GUHA | 15 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Basilardanga Piped Water Supply Scheme | SM/08077 | Retrofitting | FHTC PALASBARI PWSS |  |  | VCH/001395/2021-2022 | BP-2021-22-553 | 30/03/2022 | 30/03/2022 | SANKAR DAS | 4.73 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Basilardanga Piped Water Supply Scheme | SM/08077 | Retrofitting | FHTC BHANGARHAT PWSS |  |  | VCH/001359/2021-2022 | BP-2021-22-497 | 29/03/2022 | 29/03/2022 | M/S DEY & ROY CHOUDHURY | 10.33 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Basilardanga Piped Water Supply Scheme | SM/08077 | Retrofitting | Providing FHTC and Retrofitting works in connection with FHTC works under JJM at Binnaguri colony, Nirendarpur, Tekatuli of Basilardanga W/S/S under Jalpaiguri Division, P.H.E.Dte. Block-Maynaguri, District - Jalpaiguri.(Part-D) |  | Junior Engineer | ORD/000432/2022-2023 | 631/JD | 13/03/2023 | 27/04/2023 | PARESH CHANDRA GUHA | 40.48 | 0 | 0 | 100
Total | [13 empty] | 103.32 | 0 | 0