## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block | SM/08284 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Mathachulka T.G. area PWSS at Matiali Block under Jalpaiguri Division, PHE Dte. (Phase-III) |  | Junior Engineer | ORD/000342/2020-2021 | 570/JSSD | 01/02/2021 | 16/02/2021 | ARUP SARKAR | 4.39 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block | SM/08284 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of MATHACHULKA T.G Area piped Water Supply Scheme at Matially Block under Jalpaiguri Division, PHE Dte. (Phase-IV) |  | Junior Engineer | ORD/000426/2020-2021 | 654/JSSD | 25/02/2021 | 12/03/2021 | DEEP CONSTRUCTION | 4.69 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block | SM/08284 | Retrofitting | Providing Functional Household Tap Connection(FHTC) in connection with Jaldhara/Jal Swapna under Command area of Mathachulka Piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division,PHE Dte(Phase-I) |  | Junior Engineer | ORD/000234/2021-2022 | 510/JSSD | 03/11/2021 | 18/11/2021 | DEEP CONSTRUCTION | 4.65 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block | SM/08284 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Mathachulka T.G. area PWSS at Matiali Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  | Junior Engineer | ORD/000340/2020-2021 | 453JSSD | 30/12/2020 | 14/01/2021 | DEEP CONSTRUCTION | 4.6 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block | SM/08284 | Retrofitting | Retrofitting works related to Functional Household Tap Connection(FHTC) in connection with JJM/Jalswapna under command area of MATHACHULKA pipe water Supply schme at Matialy Block under Jalpaiguri Division, P.H.E Dte.(Phase-IX) | Assistant Engineer | Junior Engineer | ORD/000088/2022-2023 | 76/JSSD | 22/07/2022 | 06/08/2022 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 4.84 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block | SM/08284 | Retrofitting | Retrofitting works related to Functional Household Tap Connection(FHTC) in connection with JJM/Jalswapna under command area of MATHACHULKA (Gobra Busty & Salbari Part) at Mathachulka pipe water supply scheme at Matialy Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000247/2022-2023 | 163/JSSD | 24/08/2022 | 23/09/2022 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 4.78 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block | SM/08284 | Retrofitting | Providing Functional Household tap connection of connection with Jalswapna JJM under command area of Mathachulka (Purba Deema Para ) PWSS at Matiali Block Under Jalpaiguri Division P.H.E Dte. (Phase-VIII) |  |  | ORD/001075/2021-2022 | .1029/W/JSSD | 31/01/2022 | 15/02/2022 | SUBIR GHOSH | 4.82 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block | SM/08284 | Retrofitting | Providing Functional Household tap connection of connection with Jalswapna JJM under command area of Mathachulka ( Purba Deema Para ) PWSS at Matiali Block Under Jalpaiguri Division P.H.E Dte. (Phase - VIII) |  | Junior Engineer | ORD/000890/2021-2022 | 1029/W/JSSD | 31/01/2022 | 15/02/2022 | SUBIR GHOSH | 4.82 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block | SM/08284 | Retrofitting | Retrofitting works related to Functional Household Tap Connection(FHTC) inconnection with JJM/Jalswapna under command area of MATHACHULKA (GOBRABUSTY,UPORDHARA areas) pipe water supply scheme at Matiali Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000116/2022-2023 | 93/JSSD | 22/07/2022 | 21/08/2022 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 3.61 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block | SM/08284 | Retrofitting | Construction of valve and valve Chamber at different location under command area of MATHACHULKA pipe water supply scheme at Matialy Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000119/2022-2023 | 96/JSSD | 22/07/2022 | 21/08/2022 | DEEP CONSTRUCTION | 1.97 | 0 | 0 | 0
Total | [13 empty] | 43.19 | 0 | 0