## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Nagrakata | Northern Mechanical | Supply of potable drinking water to Dharanipur Tea Garden in relation with Chaa Sundari Project. | SM/08578 | New | Supply, installation, commissioning and Trial operation of Electro Mechanical components for water supply scheme at DHARANIPUR TEA GARDEN IN RELATION WITH CHAA SUNDARI PROJECT, Block NAGRAKATA, district Jalpaiguri. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000041/2022-2023 | 356/NMD | 23/05/2022 | 22/06/2022 | SUBODH KUMAR BANIK | 16.28 | 0 | 0 | 0
2 | JALPAIGURI | Nagrakata | Northern Mechanical | Supply of potable drinking water to Dharanipur Tea Garden in relation with Chaa Sundari Project. | SM/08578 | New | "3 P H NEW SERVICE CONNECTION WORK AT DHARANIPUR TG IN RELATION WITH CHA SUNDARI PROJECT TW-II " APPLICATION NO.100000110436 Reference ID : 860302766 |  |  | BILL/00446/2024-2025 | BP/24-25/87 | 18/06/2024 | 18/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.34 | 0 | 0 | 0
3 | JALPAIGURI | Nagrakata | Northern Mechanical | Supply of potable drinking water to Dharanipur Tea Garden in relation with Chaa Sundari Project. | SM/08578 | New | "New Service Connection Charge for DHARANIPUR TG IN RELATION WITH CHA SUNDARI PROJECT " APPLICATION NO.4003435519 Reference ID : 403236673 |  |  | BILL/00445/2024-2025 | BP/24-25/87 | 18/06/2024 | 18/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
4 | JALPAIGURI | Nagrakata | Northern Mechanical | Supply of potable drinking water to Dharanipur Tea Garden in relation with Chaa Sundari Project. | SM/08578 | New | "3 P H NEW SERVICE CONNECTION WORK AT DHARANIPUR TG " APPLICATION NO.100000110433 Reference ID : 860302763 |  |  | BILL/00444/2024-2025 | BP/24-25/87 | 18/06/2024 | 18/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.31 | 0 | 0 | 0
5 | JALPAIGURI | Nagrakata | Northern Mechanical | Supply of potable drinking water to Dharanipur Tea Garden in relation with Chaa Sundari Project. | SM/08578 | New | "New Service Connection Charge for DHARANIPUR TG IN RELATION WITH CHA SUNDARI PROJECT TW-II " APPLICATION NO.4003435908 Reference ID : 403236934 |  |  | BILL/00447/2024-2025 | BP/24-25/87 | 18/06/2024 | 18/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
6 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Supply of potable drinking water to Dharanipur Tea Garden in relation with Chaa Sundari Project. | SM/08578 | New | Laying distribution system and providing FHTC with other allied works under Jal Jeevan Mission for the adjacent area of Dharanipur Cha Sundari piped W/S scheme at Nagrakata Block under Jalpaiguri Sadar Sub Division P.H.E. Dte. (Phase-II) | Assistant Engineer | Junior Engineer | ORD/000143/2024-2025 | 255/JSSD | 24/09/2024 | 02/07/2025 | ARUP SARKAR | 8.59 | 0 | 0 | 100
7 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Supply of potable drinking water to Dharanipur Tea Garden in relation with Chaa Sundari Project. | SM/08578 | New | Construction of Different Components of Supply Of Potable Drinking Water To Dharanipur Tea Garden PWSS In Relation With Chaa Sundari Project i.e. T.W, Pump Houses, Water Distribution Network, Rising Main, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Nagrakata under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000827/2023-2024 | 2755/JD | 15/03/2024 | 29/10/2025 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 71.04 | 35.75 | 50.32 | 55
Total | [13 empty] | 103.03 | 35.75 | 34.69