## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. | SM/08579 | New | Construction of 100 cum OHR as per departmental design & drawing switch room, laying distribution system sinking of tube well etc. supply of potable drinking water to Manabari Tea Garden in relation with CHAA Sundari Project Piped Water Supply Scheme Block. Nagrakata Dist. Jalpaiguri. |  | Junior Engineer | ORD/000335/2020-2021 | 321/JD | 25/02/2021 | 25/06/2021 | RANJIT SINGH BENIWAL | 72.76 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Northern Mechanical | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. | SM/08579 | New | Supply, installation, commissioning and Trial operation of Electro Mechanical components for water supply scheme at MANABARI TEA GARDEN IN RELATION WITH CHAA SUNDARI PROJECT, Block MAL, district Jalpaiguri. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000040/2022-2023 | 355/NMD | 23/05/2022 | 22/06/2022 | S.P. ENTERPRISE | 14.27 | 0 | 0 | 0
3 | JALPAIGURI | Mal | Jalpaiguri Division | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. | SM/08579 | New | Land development of H/W site for Manabari Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000268/2022-2023 | 207/JSSD | 14/09/2022 | 14/10/2022 | M/S A.B.G. CONSTRUCTION | 1.41 | 0 | 0 | 100
4 | JALPAIGURI | Mal | Northern Mechanical | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. | SM/08579 | New | Infrastructure Cost for Manabari TG Chaa Sundari W/S Scheme, T/W No. I, under ODLABARI CCC [APPLICATION NO.100000066241 ; Reference ID : 860255931] |  |  | BILL/00022/2022-2023 | BP/22-23/133 | 10/02/2023 | 10/02/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.12 | 0 | 0 | 0
5 | JALPAIGURI | Mal | Northern Mechanical | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. | SM/08579 | New | New Service Connection Charge for Manabari TG Chaa Sundari W/S Scheme, T/W No. I, under ODLABARI CCC [APPLICATION NO. 4003043871 ; Reference ID : 402922125] |  |  | BILL/00021/2022-2023 | BP/22-23/133 | 10/02/2023 | 10/02/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. | SM/08579 | New | Infrastructure development cost for new service connection at Manabari TG (CHAA SUNDARI) PROJECT, TW NO-II, OODLABARI CCC APPLICATION NO. 100000118548 Reference ID : 860312788 |  |  | BILL/01465/2024-2025 | BP/24-25/246 | 02/12/2024 | 02/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.44 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Northern Mechanical | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. | SM/08579 | New | New Service Connection Charge for MANABARI TG (CHAA SUNDARI) PROJECT, TW NO-II, OODLABARI CCC APPLICATION NO. 4003491173 Reference ID : 403275174 |  |  | BILL/01397/2024-2025 | BP/24-25/237 | 25/10/2024 | 25/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Jalpaiguri Division | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. | SM/08579 | New | Sinking of One No. Tube Well by ODEX-165 Method of drilling and Construction of Pump House (3.60m x 2.40m) size with sanitary plumbing arrangement for direct boosting under the command area of Manabari Chaa Sundari Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000097/2024-2025 | 1293/JD | 05/09/2024 | 04/12/2024 | RANJEET SINGH BENIWAL | 13.9 | 0 | 0 | 100
Total | [13 empty] | 113.3 | 0 | 0