## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | Supply of potable drinking water to Red Bank Tea Garden in relation with Chaa Sundari Project. | SM/08581 | New | Material Requisition To Resource Division |  |  | RTOR000022/2024-2025 | 2104/JD | 25/11/2024 | 25/11/2024 | Resource Division | 3.02 | 0 | 0 | 0
2 | JALPAIGURI | Dhupguri | Northern Mechanical | Supply of potable drinking water to Red Bank Tea Garden in relation with Chaa Sundari Project. | SM/08581 | New | New Service Connection Charge for RED BANK TEA GARDEN IN RELATION WITH CHAA SUNDARI PROJECT, T/W-II, under BANARHAT CCC APPLICATION NO. 4003418390 Reference ID : 403225711 |  |  | BILL/00367/2024-2025 | BP/24-25/73 | 30/05/2024 | 30/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.64 | 0 | 0 | 0
3 | JALPAIGURI | Dhupguri | Northern Mechanical | Supply of potable drinking water to Red Bank Tea Garden in relation with Chaa Sundari Project. | SM/08581 | New | New Service Connection Charge for RED BANK TEA GARDEN (CHAA SUNDARI), T/W No. I, under BANARHAT CCC [APPLICATION NO. 4003333225 , Reference ID : 403157470] |  |  | BILL/02002/2023-2024 | BP/23-24/308 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.76 | 0 | 0 | 0
4 | JALPAIGURI | Dhupguri | Northern Mechanical | Supply of potable drinking water to Red Bank Tea Garden in relation with Chaa Sundari Project. | SM/08581 | New | Supply, installation, commissioning and Trial operation of Electro Mechanical components for water supply scheme at RED BANK TEA GARDEN IN RELATION WITH CHAA SUNDARI PROJECT, Block - DHUPGURI, district Jalpaiguri. | Assistant Engineer , Head Quarters , NMD,Driller-in-Charge | Junior Engineer | ORD/000042/2022-2023 | 357/NMD | 23/05/2022 | 01/08/2025 | M/S BHOWMICK & CO. | 12.59 | 0 | 0 | 90
5 | JALPAIGURI | Dhupguri | Jalpaiguri Division | Supply of potable drinking water to Red Bank Tea Garden in relation with Chaa Sundari Project. | SM/08581 | New | Construction of Different Components of Supply Of Potable Drinking Water To Red Bank Tea Garden PWSS In Relation With Chaa Sundari Project i.e. T.W, Pump Houses, Water Distribution Network, Rising Main, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Nagrakata under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000589/2023-2024 | 2331/JD | 08/02/2024 | 02/05/2025 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 90.89 | 35.71 | 39.29 | 75
Total | [13 empty] | 115.91 | 35.71 | 30.81