## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Procurement of Chemicals, Glassware and Instrument equipment for NABL Accreditation of Jalpaiguri District Laboratory | SM/08681 | Support-WQMSP | Improvement of Lab rooms & ancilliary works at Dhupguri Sub District Lab & excess works of Chalsa Sub District Lab under Jalpaiguri Division , P.H.E. Dte. |  |  | ORD/000322/2021-2022 | 873/RWS | 08/12/2021 | 18/12/2021 | NEW KUNDU ENTERPRISE | 3.79 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Procurement of Chemicals, Glassware and Instrument equipment for NABL Accreditation of Jalpaiguri District Laboratory | SM/08681 | Support-WQMSP | Estimate for procurement of miscellenious items for Jalpaiguri District water testing laboratory for developing the NABL set up under Jalpaiguri Division P.H.E Dte. |  |  | ORD/000387/2021-2022 | 848/RWS | 03/12/2021 | 10/12/2021 | ARUNALOY SCIENTIFIC HOUSE | 3.12 | 3.12 | 100 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Procurement of Chemicals, Glassware and Instrument equipment for NABL Accreditation of Jalpaiguri District Laboratory | SM/08681 | Support-WQMSP | Installation of NABL specified signboard at the entrance of Dhupguri Sub-District Laboratory under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000521/2023-2024 | 1262/RWS | 22/11/2023 | 02/12/2023 | SWAPAN SAHA | 0.1 | 0.1 | 100 | 100
4 | JALPAIGURI |  | Jalpaiguri Division | Procurement of Chemicals, Glassware and Instrument equipment for NABL Accreditation of Jalpaiguri District Laboratory | SM/08681 | Support-WQMSP | Installation of NABL specified signboard at the entrance of Chalsa Sub- District Water Testing Laboratory under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000522/2023-2024 | 1263/RWS | 22/11/2023 | 02/12/2023 | SWAPAN SAHA | 0.1 | 0.1 | 100 | 100
5 | JALPAIGURI |  | Jalpaiguri Division | Procurement of Chemicals, Glassware and Instrument equipment for NABL Accreditation of Jalpaiguri District Laboratory | SM/08681 | Support-WQMSP | Installation of NABL specified signboard at the entrance of Jalpaiguri District Water Testing Laboratory under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000520/2023-2024 | 1261/RWS | 22/11/2023 | 02/12/2023 | SWAPAN SAHA | 0.1 | 0.1 | 100 | 100
Total | [13 empty] | 7.21 | 3.42 | 47.39