## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. | Assistant Engineer | Junior Engineer | ORD/000303/2022-2023 | 2192/JD | 11/11/2022 | 11/12/2022 | M/S MILLENNIUM FUEL CENTRE | 2.97 | 2.97 | 100 | 0
2 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | Construction of Pump House (3.60m x 2.40m) size with sanitary and plumbing arrangement at 2nd Tube well site for Ghasmari PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000726/2021-2022 | 1071/JSSD | 25/01/2022 | 11/03/2022 | ARUP SARKAR | 4.65 | 4.65 | 100 | 0
3 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | Construction of Boundary wall with gate drain and pathway for 2nd tube well site of Ghasmari P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000644/2021-2022 | 1061/JSSD | 24/01/2022 | 13/02/2022 | PRITAM DUTTA | 3.76 | 3.78 | 100.54 | 0
4 | JALPAIGURI | Nagrakata | Northern Mechanical | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector for GHASMARI W/S Scheme at T/W No. II in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000025/2022-2023 | 267/NMD | 22/04/2022 | 13/05/2022 | GURUKRIPA ENTERPRISE | 2.16 | 2.16 | 100 | 0
5 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | Rig approach for Installation of tube well at Ghasmari Piped water supply Scheme head works site & 2nd site under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000120/2022-2023 | 97/JSSD | 22/07/2022 | 21/08/2022 | ALICK DUTTA | 1.22 | 1.22 | 99.73 | 0
6 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | CONST OF OHR FOR UTTAR DANGAPRA DAKSHIN SAKOAJHORA PWSS |  |  | VCH/001260/2021-2022 | BP-2021-22-403 | 23/03/2022 | 23/03/2022 | PARESH CHANDRA GUHA | 25.96 | 0 | 0 | 0
7 | JALPAIGURI | Nagrakata | Northern Mechanical | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | New Service Connection Charge for TW-II of Ghasmari Basty under GHASMARI W/S Scheme under NAGRAKATA CCC [APPLICATION NO. 4002921741, Reference ID : 402816204] |  |  | VCH/000139/2022-2023 | BP/2022-23/19 | 21/06/2022 | 21/06/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.55 | 0 | 0 | 0
8 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | Maintainance of Jalpaiguri division office including RWS/ Sadar Sub-Division |  |  | VCH/000557/2022-2023 | BP-2022-23-180 | 15/09/2022 | 15/09/2022 | SUKUMAR KUNDU | 1.64 | 0 | 0 | 0
9 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | supply of fuel |  |  | VCH/000594/2022-2023 | BP-2022-23-262 | 17/11/2022 | 17/11/2022 | FILL & SMILE | 0.98 | 0 | 0 | 0
10 | JALPAIGURI | Nagrakata | Northern Mechanical | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | New Service Connection Charge for TW-I of Ghasmari Basty under GHASMARI W/S Scheme under NAGRAKATA CCC [APPLICATION NO. 4002921737, Reference ID : 402816203] |  |  | VCH/000138/2022-2023 | BP/2022-23/19 | 21/06/2022 | 21/06/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.85 | 0 | 0 | 0
11 | JALPAIGURI | Nagrakata | Northern Mechanical | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | New Service Connection Charge for R.O. PHE Pump House No. I & II of Ghasmari Basty under GHASMARI W/S Scheme under NAGRAKATA CCC [APPLICATION NO. 100000050449, Reference ID : 860240039] |  |  | VCH/000137/2022-2023 | BP/2022-23/19 | 21/06/2022 | 21/06/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.82 | 0 | 0 | 0
12 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | supply of fuel |  |  | VCH/000593/2022-2023 | BP-2022-23-261 | 17/11/2022 | 17/11/2022 | FILL & SMILE | 1.26 | 0 | 0 | 0
13 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | CONST 250 MM CAPACITY UTTAR DANGA PARA & DAKSHIN SAKOJHORA |  |  | VCH/001309/2021-2022 | BP-2021-22-403 | 23/03/2022 | 23/03/2022 | PARESH CHANDRA GUHA | 25.96 | 0 | 0 | 0
14 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | Installation of R.B.T fixing in boundary wall and other allied works at 2nd site for Ghasmari TG Area Piped Water Supply Scheme under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer | Junior Engineer | ORD/000259/2022-2023 | 183/JSSD | 29/08/2022 | 28/09/2022 | PRITAM DUTTA | 1.78 | 1.77 | 99.64 | 100
15 | JALPAIGURI | Nagrakata | Northern Mechanical | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | Supply, installation, commissioning and trial operation of electro-mechanical components for GHASMARI PWSS, TW no II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000015/2022-2023 | 283/NMD | 26/04/2022 | 26/05/2022 | M/S BHOWMICK & CO. | 8.67 | 8.67 | 100 | 100
16 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 173/JD | 28/04/2023 | 28/04/2023 | Resource Division | 17.75 | 0 | 0 | 0
17 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | HIRE CHARGES |  |  | VCH/000622/2022-2023 | BP-2022-23-348 | 09/12/2022 | 09/12/2022 | APIKUL ALI | 0.29 | 0 | 0 | 0
18 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | fuel charges |  |  | BILL/00253/2022-2023 | BP-2022-23-439 | 06/02/2023 | 06/02/2023 | FILL & SMILE | 0.29 | 0 | 0 | 0
19 | JALPAIGURI | Nagrakata | Northern Mechanical | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector for GHASMARI W/S Scheme at T/W No. I in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD,Driller-in-Charge | Junior Engineer | ORD/000024/2022-2023 | 266/NMD | 22/04/2022 | 13/05/2022 | M/S PALIDEB ENGINEERING WORKS | 2.16 | 2.16 | 99.9 | 100
20 | JALPAIGURI | Nagrakata | Northern Mechanical | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | Supply, installation, commissioning and trial operation of electro-mechanical components for GHASMARI PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000014/2022-2023 | 282/NMD | 26/04/2022 | 26/05/2022 | DEY ENTERPRISE (BALLY) | 8.67 | 7.1 | 81.89 | 100
21 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | Material Requisition To Resource Division |  |  | RTOR000205/2023-2024 | 2064/JD | 10/01/2024 | 10/01/2024 | Resource Division | 4.8 | 0 | 0 | 0
22 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | Construction of 150 CUM Capacity R.C.C. Elevated Reservoir, 20 Mtrs staging Height including pump house (5.4x3.6) size, Boundary wall and Drain for GHASMARI Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000127/2023-2024 | 708/JD | 13/07/2023 | 16/03/2025 | M/S R.N. TRADERS | 76.58 | 20.58 | 26.88 | 85
23 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | Laying distribution system with Rising Main Connection and Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna for Ghasmari Area Piped water supply Scheme under Jalpaiguri Division. P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000346/2021-2022 | 208/JD | 24/01/2022 | 20/02/2025 | M/S R.N. TRADERS | 118.35 | 20.51 | 17.33 | 100
24 | JALPAIGURI | Nagrakata | Northern Mechanical | Ghasmari Piped Water Supply Scheme. | SM/08868 | New | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig unit 32B-R-1302, by Odex-165 method of drilling, at Ghasmari PWSS, TW-II (2nd Site), Block - Nagrakata, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Driller-in-Charge | Junior Engineer | ORD/000728/2021-2022 | 356/DSD | 28/02/2022 | 15/03/2022 | S.P. ENTERPRISE | 0.49 | 0 | 0 | 100
Total | [13 empty] | 316.62 | 75.58 | 23.87