## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | SOIL INVESTIGATION WORK FOR BAGRAKOTE T.G. PIPED WATER SUPPLY SCHEME BLOCK : MAL DISTRICT : JALPAIGURI |  | Junior Engineer | ORD/000398/2021-2022 | 852/RWS | 03/12/2021 | 18/12/2021 | G. TECH INDIA | 2.03 | 1.63 | 80.55 | 1
2 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Sinking of 3 Nos. Tubewell by ODEX-165 method for Bagrakote W/S Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000375/2023-2024 | 1516/JD | 16/10/2023 | 15/11/2023 | RANJEET SINGH BENIWAL | 20.54 | 16.66 | 81.13 | 100
3 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Material Requisition To Resource Division |  |  | RTOR000001/2021-2022 | 1940/JD | 02/12/2021 | 02/12/2021 | Resource Division | 12.32 | 0 | 0 | 0
4 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 172/JD | 28/04/2023 | 28/04/2023 | Resource Division | 82.59 | 0 | 0 | 0
5 | JALPAIGURI | Mal | Northern Mechanical | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Infrastructure Cost for BAGRAKOTE TEA GARDEN, T/W No. III, under ODLABARI CCC, [APPLICATION NO. 100000093885, Reference ID : 860285545] |  |  | BILL/01270/2023-2024 | BP/23-24/151 | 05/12/2023 | 05/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.98 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | New Service Connection Charge for BAGRAKOTE TEA GARDEN, T/W No. III, under ODLABARI CCC, [APPLICATION NO. 4003266408, Reference ID : 403105530] |  |  | BILL/01269/2023-2024 | BP/23-24/150 | 05/12/2023 | 05/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Construction of 400 CuM Capacity R.C.C. Over Head Reservoir (OHR) of 20 Mtr Staging Height at Bagrakote Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000590/2023-2024 | 2410/JD | 19/02/2024 | 17/08/2024 | D.C RAKSHIT AND SONS INDIA PRIVATE LTD. | 106.62 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Construction of Boundary wall, drain and pathway for 2nd Tubewell site of Bagrakote T.G. Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000349/2022-2023 | 134/JD | 17/01/2023 | 16/02/2023 | ETHERIA EDIFICE (OPC) PVT. LTD. | 7.01 | 6.44 | 91.89 | 100
9 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Construction of Pump House ( 3.60M X 2.40M ) Size with sanitary & plumbing arrangement including Boundary wall, drain and pathway for 3rd Tubewell site of Bagrakote T.G. Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000433/2023-2024 | 1674/JD | 24/11/2023 | 08/01/2024 | KAPIL MANI BRAHMAN | 11.66 | 9.48 | 81.27 | 100
10 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Emergency water supply arrangement to the dengue effected area related to Bagrakote water supply Scheme for 45 days . ( from 29.06.2022 to 12.08.2022) | Assistant Engineer | Junior Engineer | ORD/000299/2022-2023 | 437/RWS | 07/07/2022 | 21/08/2022 | SWAPAN SAHA | 4.47 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Material Requisition To Resource Division |  |  | RTOR000208/2023-2024 | 2068/JD | 10/01/2024 | 10/01/2024 | Resource Division | 14.15 | 0 | 0 | 0
12 | JALPAIGURI | Mal | Northern Mechanical | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Infrastructure Cost for BAGRAKOTE TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 100000093883, Reference ID : 860285543] |  |  | BILL/01274/2023-2024 | 23-24/152&161 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.39 | 0 | 0 | 0
13 | JALPAIGURI | Mal | Northern Mechanical | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Infrastructure Cost for BAGRAKOTE TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 100000093777, Reference ID : 860285647] |  |  | BILL/01272/2023-2024 | 23-24/152&161 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.06 | 0 | 0 | 0
14 | JALPAIGURI | Mal | Northern Mechanical | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | New Service Connection Charge for BAGRAKOTE TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 4003266397, Reference ID : 403105521] |  |  | BILL/01273/2023-2024 | 23-24/152&161 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
15 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Laying Distribution system and functional household tap connection for Bagrakote Tea Garden piped Water Supply Scheme Block- Mal District ¿ Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000378/2021-2022 | 351/JD | 03/02/2022 | 31/08/2025 | M/S GARGO TRADERS | 184.25 | 48.31 | 26.22 | 60
16 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Construction of rig approach road for Bagrakote T.G Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. .(2nd Site) .(4th Call) | Assistant Engineer | Junior Engineer | ORD/000439/2023-2024 | 1274/RWS | 24/11/2023 | 08/12/2023 | RANJEET SINGH BENIWAL | 0.8 | 0 | 0 | 100
17 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Construction of rig approach road for Bagrakote T.G Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. .(H/W Site) .(4th Call) | Assistant Engineer | Junior Engineer | ORD/000438/2023-2024 | 1275/RWS | 24/11/2023 | 08/12/2023 | RANJEET SINGH BENIWAL | 1.37 | 0 | 0 | 100
18 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Construction of Pump House (3.60 M X 2.40 M ) Size With Sanitary & Plumbing Arrangement at 2nd tube well site for Bagrakote T.G. W/S/S under Jalpaiguri Division , P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000293/2021-2022 | 825/RWS | 30/11/2021 | 01/03/2025 | BIMAN DAS | 4.65 | 0 | 0 | 100
Total | [13 empty] | 466.37 | 82.53 | 17.7