## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | CONSTRUCTION OF 150M3BOUNDARY WALL KUMLAI T.G WSS |  |  | VCH/001303/2021-2022 | BP-2021-22-435 | 25/03/2022 |  | SANDIP BANIK | 17.63 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | RENOVATION B/W H/W SOUTH BERUBARI WSS |  |  | VCH/001377/2021-2022 | BP-2021-22-540 | 31/03/2022 |  | A.P CONSTRUCTION | 19.8 | 0 | 0 | 0
3 | JALPAIGURI | Mal | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | LDS KUMLAI |  |  | VCH/001388/2021-2022 | BP-2021-22-511 | 30/03/2022 |  | R.S CONSTRUCTION | 26.65 | 0 | 0 | 0
4 | JALPAIGURI | Mal | Northern Mechanical | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | Infrastructure cost for New Service Connection Charge for T/W No. I of KUMLAI T.G. W/S Scheme under ODLABARI CCC [APPLICATION NO. 100000050872, Reference ID : 860240742] |  |  | VCH/000140/2022-2023 | BP/2022-23/13 | 16/06/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.59 | 0 | 0 | 0
5 | JALPAIGURI | Mal | Northern Mechanical | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | New Service Connection Charge for T/W No. I of KUMLAI T.G. W/S Scheme under ODLABARI CCC [APPLICATION NO. 4002922582, Reference ID : 402818172] |  |  | VCH/000142/2022-2023 | BP/2022-23/13 | 16/06/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.32 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | New Service Connection Charge for T/W No. II of KUMLAI T.G. W/S Scheme under ODLABARI CCI [APPLICATION NO. 4002922585, Reference ID : 402817968] |  |  | VCH/000143/2022-2023 | BP/2022-23/13 | 16/06/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.88 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Northern Mechanical | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | Infrastructure cost for New Service Connection Charge for T/W No. II of KUMLAI T.G. W/S Scheme under ODLABARI CCC [APPLICATION NO. 100000050873, Reference ID : 860240743] |  |  | VCH/000141/2022-2023 | BP/2022-23/13 | 16/06/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.05 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Northern Mechanical | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under KUMLAI T.G W/S Scheme, at TW No. I in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000063/2022-2023 | 438/NMD | 14/06/2022 | 05/07/2022 | TAPAN BISWAS | 2.39 | 2.39 | 100 | 0
9 | JALPAIGURI | Mal | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | Model estimate for construction of pump house ( 3.60 m X 2.40 m) Size With Sanitary & Plumbing Arrangement at 2nd tube well site for Kumlai T.G . W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000324/2021-2022 | 875/RWS | 08/12/2021 | 07/01/2022 | BREATHING SPACE DESIGN & VAASTA CONSULTANTS | 4.65 | 4.65 | 100 | 1
10 | JALPAIGURI | Mal | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. | Assistant Engineer | Junior Engineer | ORD/000304/2022-2023 | 2193/JD | 11/11/2022 | 11/12/2022 | M/S MILLENNIUM FUEL CENTRE | 3.42 | 3.42 | 100 | 0
11 | JALPAIGURI | Mal | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | Construction of boundary wall Path way, block drain for 2 nd site of kumlai T.G. piped water supply scheme under Jalpaiguri Division, P.H.E. Die. | Assistant Engineer | Junior Engineer | ORD/000282/2022-2023 | 647/RWS | 21/10/2022 | 10/11/2022 | BREATHING SPACE DESIGN & VAASTA CONSULTANTS | 4.83 | 4.83 | 99.84 | 1
12 | JALPAIGURI | Mal | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | Construction of 150 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing RCC including pipe connection and cost of pipes, specials, Construction of Pump House (5.4m x 3.60 m) & Boundary wall at H/W site Kumlai Tea Garden Area Piped Water Supply Scheme, Block- Mal, Dist. Jalpaiguri. Under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000354/2021-2022 | 252/JD | 31/01/2022 | 30/06/2022 | SANDIP BANIK | 64.43 | 47.08 | 73.08 | 1
13 | JALPAIGURI | Mal | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | Providing Functional Household Tap Connection (FHTC) in connection for Jaldhara/Jal Sapna under the command area of Jabramali piped Water Supply Scheme at MATIALI Block under Jalpaiguri Division, PHE Dte. (Part-E) | Assistant Engineer | Junior Engineer | ORD/000186/2022-2023 | 565/RWS | 01/09/2022 | 01/10/2022 | B.M CONSTRUCTION | 2.65 | 2.58 | 97.2 | 0
14 | JALPAIGURI | Mal | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jalsapna under the command area of Mohit Nagar W/S/S under Jalpaiguri Division , P.H.E. Dte ( part ¿ F ) |  | Junior Engineer | ORD/000325/2021-2022 | 879/RWS | 10/12/2021 | 20/12/2021 | M/S DEY & ROY CHOUDHURY | 1.28 | 0.13 | 9.89 | 1
15 | JALPAIGURI | Mal | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 174/JD | 28/04/2023 |  | Resource Division | 21.11 | 0 | 0 | 0
16 | JALPAIGURI | Mal | Northern Mechanical | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under KUMLAI T.G W/S Scheme, at TW No. II in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000064/2022-2023 | 439/NMD | 14/06/2022 | 05/07/2022 | M/S B.ENTERPRISE | 2.37 | 2.37 | 100 | 0
17 | JALPAIGURI | Mal | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | PAYMENT FOR FUEL BILL |  |  | BILL/00360/2023-2024 | BP-2023-24-315 | 18/08/2023 |  | FILL & SMILE | 3.34 | 0 | 0 | 0
18 | JALPAIGURI | Mal | Northern Mechanical | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | Supply, installation, commissioning and trial operation of electro-mechanical components for KUMLAI T.G W/S Scheme, TW No. I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000112/2022-2023 | 861/NMD | 18/07/2022 | 17/08/2022 | PRATIK ROY | 9.2 | 9.2 | 100 | 100
19 | JALPAIGURI | Mal | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | SOIL INVESTIGATION WORK FOR KUMLAI T.G. PIPED WATER SUPPLY SCHEME BLOCK : MAL DISTRICT : JALPAIGURI |  |  | ORD/000401/2021-2022 | 853/RWS | 03/12/2021 | 18/12/2021 | G. TECH INDIA | 2.03 | 0 | 0 | 0
20 | JALPAIGURI | Mal | Northern Mechanical | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | Carrying out Development works and Yield Test for a BDTW at Kumlai TG W/S Scheme, TW-I & II, Bhagatpur TG PWSS (Zone-II), TW-I & II, Ghasmari PWSS, TW-I & II , Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/000820/2021-2022 | 328/DSD | 07/02/2022 | 28/02/2022 | M/S ANJALI ENTERPRISE | 0.63 | 0.32 | 50 | 100
21 | JALPAIGURI | Mal | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | Material Requisition To Resource Division |  |  | RTOR000207/2023-2024 | 2066/JD | 10/01/2024 |  | Resource Division | 6.1 | 0 | 0 | 0
22 | JALPAIGURI | Mal | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | Rising main connection for Kumlai TG PWSS including supply of Sluice valve/ Jeffy coupling ,C.I.D.F. Specials etc. under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000334/2022-2023 | 27/JD | 05/01/2023 | 26/01/2023 | ADITRI ENTERPRISE | 4.81 | 3.6 | 74.7 | 100
23 | JALPAIGURI | Mal | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | Laying Distribution system and functional household tap connection for Kumlai Tea Garden piped Water Supply Scheme Block- Mal District ¿ Jalpaiguri. |  | Junior Engineer | ORD/000340/2021-2022 | 192/JD | 21/01/2022 | 22/03/2022 | R.S CONSTRUCTION | 116.87 | 65.99 | 56.46 | 70
24 | JALPAIGURI | Mal | Northern Mechanical | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | New | Supply, installation, commissioning and trial operation of electro-mechanical components for KUMLAI T.G W/S Scheme, TW No. II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000078/2022-2023 | 536/NMD | 08/07/2022 | 07/08/2022 | RAJEEV RANJAN OJHA | 9.62 | 1.99 | 20.65 | 70
Total | [13 empty] | 335.69 | 148.54 | 44.25