## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | New Service Connection Charge for CHAMURCHI TEA GARDEN W/S SCHEME, T/W No. I, Zone I under BANARHAT CCC [APPLICATION NO. 4003023651 ; Reference ID : 402902659] |  |  | BILL/00004/2022-2023 | BP/22-23/107 | 08/12/2022 | 08/12/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.83 | 0 | 0 | 0
2 | JALPAIGURI |  | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Installation of Infrastructure COST at CHAMURCHI TEA GARDEN W/S SCHEME, T/W No. I, Zone I under BANARHAT CCC [APPLICATION NO. 100000064277 ; Reference ID : 860253067] |  |  | BILL/00003/2022-2023 | BP/22-23/107 | 08/12/2022 | 08/12/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.12 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | CHAMURCHI BAZAR |  |  | VCH/000085/2022-2023 | BP-2022-2023-42 | 24/05/2022 | 24/05/2022 | RANA DEY | 3.83 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | New Service Connection Charge for CHAMURCHI TEA GARDEN W/S SCHEME, T/W No. II, Zone I under BANARHAT CCC [APPLICATION NO. 4003019807 ; Reference ID : 402902658] |  |  | BILL/00006/2022-2023 | BP/22-23/107 | 08/12/2022 | 08/12/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.83 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Resistivity Test for Four Nos.Tube Well for Chamurchi Tea Garden area Augmentation Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000576/2021-2022 | 142/JD | 18/01/2022 | 02/02/2022 | PARAMJYOTI ENTERPRISE | 0.6 | 0.6 | 100 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Construction of rig approach road for the various zone of augmentation Chamurchi T.G.PWSS under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000159/2022-2023 | 1500/JD | 27/07/2022 | 11/08/2022 | PARAMJYOTI ENTERPRISE | 1.77 | 1.78 | 100.7 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 2nd tube well site for Augmentation of Chamurchi T.G. P.W.S.S. zone-I under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000224/2022-2023 | 1853/JD | 16/09/2022 | 31/10/2022 | PARAMJYOTI ENTERPRISE | 4.65 | 4.78 | 102.73 | 0
8 | JALPAIGURI |  | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CHAMURCHI TG PWSS, ZONE-I, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000690/2022-2023 | 1449/NMD | 21/12/2022 | 20/01/2023 | SARKAR ELECTRIC | 26.26 | 26.26 | 100 | 100
9 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Shifting of Rising main due to widening and Construction of New Culvert at Hatinala and other ancillary works related to the Rising main inside the Head works site of Chamurchi Bazar P.W.S.S. under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000217/2022-2023 | 1807/JD | 14/09/2022 | 05/10/2022 | RANA DEY | 3.57 | 3.56 | 99.83 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Special repairing of RCC Over Head Reservoir for Chamurchi Bazar Water Supply Scheme under Jalpaiguri Division P.H.E. Dte.. | Assistant Engineer | Junior Engineer | ORD/000443/2021-2022 | 284/JD | 02/02/2022 | 03/04/2022 | SUKES BASU MAJUMDAR | 8.29 | 8.32 | 100.25 | 1
11 | JALPAIGURI |  | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig m/c ITH-20, by Odex-165 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Driller-in-Charge | Junior Engineer | ORD/000872/2021-2022 | 327/DSD | 07/02/2022 | 22/02/2022 | SAHA ENTERPRISE | 0.49 | 0.16 | 33.54 | 0
12 | JALPAIGURI |  | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig m/c ITH-20, by Odex-165 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Driller-in-Charge | Junior Engineer | ORD/000823/2021-2022 | 313/DSD | 24/01/2022 | 08/02/2022 | SAHA ENTERPRISE | 0.49 | 0.16 | 33.54 | 0
13 | JALPAIGURI |  | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig m/c ITH-20, by Odex-165 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-II (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Driller-in-Charge | Junior Engineer | ORD/000824/2021-2022 | 315/DSD | 25/01/2022 | 09/02/2022 | SAHA ENTERPRISE | 0.49 | 0.49 | 100 | 0
14 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Construction of 200 Cu.M. R.C.C. Over Head Reservoir of 16 Mtr. Staging Height one No Pump House (5.40m x 3.60m) and other related works at Zone - I of Chamurchi Tea Garden Area Augmentation P.W.S.S. udner Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000147/2022-2023 | 1540/JD | 04/08/2022 | 31/01/2023 | SAPTASWA SARKAR | 63.69 | 62.46 | 98.06 | 100
15 | JALPAIGURI |  | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Tubewell (BDTW) by deparmental Rig M/C ITH-20, by Odex-115 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Driller-in-Charge | Junior Engineer | ORD/000908/2021-2022 | 346/DSD | 22/02/2022 | 09/03/2022 | SAHA ENTERPRISE | 0.16 | 0.09 | 54.29 | 0
16 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Two nos Pump House with restoration of Sanitary Plumbing System including repairing of C.W.R. raising of valve chamber height and making of Cement Concrete Pathway at Chamurchi Forest Busty Head Works Site under Augmentation of Chamurchi T.G. Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000218/2022-2023 | 1808/JD | 14/09/2022 | 05/10/2022 | M/S KARMAKAR CONSTRACTION | 4.17 | 3.69 | 88.56 | 100
17 | JALPAIGURI |  | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig M/C ITH-20, by Odex-165 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Driller-in-Charge | Junior Engineer | ORD/000558/2022-2023 | 64/DSD | 23/05/2022 | 07/06/2022 | M/S ROYAL ENTERPRISE | 0.71 | 0.49 | 68.42 | 0
18 | JALPAIGURI |  | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig M/C ITH-20, by Odex-165 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Driller-in-Charge | Junior Engineer | ORD/000583/2022-2023 | 29/DSD | 21/04/2022 | 06/05/2022 | SAHA ENTERPRISE | 0.71 | 0.21 | 29.26 | 0
19 | JALPAIGURI |  | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Carrying out Surging, Development and Yield Testing works for a Rig Bored Big Dia Tube well (BDTW) by Odex-165 method of drilling for Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/000642/2022-2023 | 152/DSD | 26/07/2022 | 02/08/2022 | SUMON ELECTRICAL | 0.41 | 0.41 | 100 | 0
20 | JALPAIGURI |  | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Carrying out Surging, Development and Yield Testing works for a Rig Bored Big Dia Tube well (BDTW) by Odex-165 method of drilling for Augmentation of Chamurchi TG W/S Scheme, TW-II (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/000643/2022-2023 | 183/DSD | 18/08/2022 | 25/08/2022 | SUMON ELECTRICAL | 0.41 | 0.41 | 100 | 0
21 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Laying distribution system for Chamurchi Tea Garden Area Augmentation Piped Water Supply Scheme (Zone-I) udner Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000033/2022-2023 | 967/JD | 20/04/2022 | 19/07/2022 | NARAYAN CHANDRA SAHA | 85.51 | 59.46 | 69.54 | 100
22 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2023-2024 | 1105/JD | 24/08/2023 | 24/08/2023 | Resource Division | 160.42 | 0 | 0 | 0
23 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Sinking of two nos. Big dia Tube Well (200 x 150mm dia) by Modified DTH - ODEX method of drilling at Siv Mandir area of Chamurchi zone-II under ¿Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour colony)¿ under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000164/2023-2024 | 802/JD. | 24/07/2023 | 23/08/2023 | EFFLUENT AND WATTERTREATEMENT ENGINEERS(P) LTD. | 33.1 | 32.57 | 98.41 | 54
24 | JALPAIGURI |  | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CHAMURCHI TEA GARDEN (CHAMURCHI BAZAR and CHAMURCHI FOREST BUSTY and LABOUR COLONY) PWSS, ZONE-II, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000441/2023-2024 | 1380/NMD | 09/08/2023 | 08/09/2023 | THE BANERJEE CONCERN | 26.24 | 11.08 | 42.24 | 40
25 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Continuation order for the work "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) (w.e.f. 14.01.2024) | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000600/2023-2024 | 1982/JD | 03/01/2024 | 03/07/2024 | APIKUL ALI | 0.88 | 1.01 | 113.95 | 30
26 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) (w.e.f. 14.01.2024) | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000601/2023-2024 | 1983/JD | 03/01/2024 | 03/07/2024 | RAKESH SARKAR | 0.88 | 1.11 | 126.17 | 30
27 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Continuation order for the work "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) (w.e.f. 15.07.2024 to 14.10.2024) | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000020/2024-2025 | 561/JD | 03/07/2024 | 03/10/2024 | APIKUL ALI | 0.44 | 0.27 | 61.39 | 0
28 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Laying distribution system for Chamurchi Tea Garden Area Augmentation Piped Water Supply Scheme (Zone-III) under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000041/2022-2023 | 864/JD | 01/04/2022 | 02/01/2025 | M/S. D.K. DEY & CO.. | 63.77 | 35.4 | 55.52 | 100
29 | JALPAIGURI |  | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Tubewell (BDTW) by deparmental Rig M/C ITH-20, by Odex-115 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Driller-in-Charge | Junior Engineer | ORD/000911/2021-2022 | 360/DSD | 02/03/2022 | 17/03/2022 | SAHA ENTERPRISE | 0.16 | 0.09 | 54.29 | 100
30 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Laying of Individual D.I. Rising Main Including common manifold from 1st Tube Well to 2nd Tube Well and to Head Works site including internal connection of 1st and 2nd Tube Well site with Functional Household Tap Connection in connection with Jal Jeevan Mission under Augmentation of Chamurchi T.G. Piped Water Supply Scheme (Zone-I) under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000399/2022-2023 | 627/JD | 13/03/2023 | 27/04/2023 | SANKAR DAS | 47.49 | 35.55 | 74.85 | 50
31 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Sinking of one no. Big dia Tube Well (200 x 150mm dia) by Modified DTH - ODEX method of drilling at chunavati chamurchi Zone-III under ¿Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour colony)¿ under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000163/2023-2024 | 801/JD. | 24/07/2023 | 23/08/2023 | EFFLUENT AND WATTERTREATEMENT ENGINEERS(P) LTD. | 16.55 | 16.03 | 96.88 | 80
32 | JALPAIGURI |  | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Additional work in connection Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of CHAMURCHI TG (Z-I) PWSS, at TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000793/2023-2024 | 228/HQ/NMD | 15/09/2023 | 30/09/2023 | SARKAR ELECTRIC | 1.44 | 1.43 | 99.1 | 100
33 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Construction of Two Nos Boundary Wall (at OHR site and alternate 1 st tube well Site) including construction of surface drain,making of pathway,Land development work,with supplying fitting fixing CIDF pipe,modification of pump house and constructionof rest rooms with construction of culvert along with scouring prevention work on the approach way including development of approach way with other allied works for the various site within the command area of augmentation of Chamurchi T.G. Area P.W.S.S.Zone - I under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000523/2023-2024 | 1819/JD | 14/12/2023 | 28/01/2024 | SAPTASWA SARKAR | 64.94 | 54.31 | 83.63 | 100
34 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Construction of 3rd Tubewell site Pump House (3.60 m X 2.40 m) size with sanitary & Plumbing arrangement at Chunavati Chamurchi Zone-II under "Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour Colony)" under Jalpaiguri division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000602/2023-2024 | 2303/JD | 07/02/2024 | 23/03/2024 | DITIPRIYA CHOWDHURY | 4.9 | 4.9 | 100 | 100
35 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Construction of 2nd Tubewell site Pump House (3.60 m X 2.40 m) size with sanitary & Plumbing arrangement for at airtel site of Chunavati Chamurchi Zone-II under "Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour Colony)" under Jalpaiguri division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000603/2023-2024 | 2304/JD | 07/02/2024 | 23/03/2024 | MAA SHANTI BUILDERS | 4.9 | 4.9 | 100 | 100
36 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Sinking of Big Dia Tube well by Modified DTH - ODEX Method at 2nd tube well site of Chamurchi Piped Water Supply Scheme (Zone-III, Chunabhati) of Banarhat Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000063/2024-2025 | 932/JD | 07/08/2024 | 22/08/2024 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 17.61 | 17.99 | 102.16 | 100
37 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000091/2024-2025 | 2222/JD | 01/12/2024 | 01/12/2024 | Resource Division | 21.08 | 0 | 0 | 0
38 | JALPAIGURI |  | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | New Service Connection Charge for AUG CHAMURCHI TEA GARDEN, T/W No. I, ZONE II under BANARHAT CCC [APPLICATION NO. 4003333005 , Reference ID : 403157463] |  |  | BILL/02005/2023-2024 | BP/23-24/308 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 16 | 0 | 0 | 0
39 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Supply of Fuel (Diesel) of Vehicle No WB 76 9978 for the Month of July 2024. |  |  | BILL/00589/2024-2025 | BP-2024-25-338 | 30/08/2024 | 30/08/2024 | FILL & SMILE | 0.23 | 0 | 0 | 0
40 | JALPAIGURI |  | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | New Service Connection Charge for AUG CHAMURCHI TEA GARDEN, T/W No. II, ZONE II under BANARHAT CCC [APPLICATION NO. 4003333013 , Reference ID : 403157465] |  |  | BILL/02004/2023-2024 | BP/23-24/308 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.18 | 0 | 0 | 0
41 | JALPAIGURI |  | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | New Service Connection Charge for CHAMURCHI (CHUNABHATI) ZONE:-III, T/W-III, under BANARHAT CCC APPLICATION NO. 4003418431 Reference ID : 403225913 |  |  | BILL/00394/2024-2025 | BP/24-25/81 | 07/06/2024 | 07/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.07 | 0 | 0 | 0
42 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Laying distribution system for Chamurchi Tea Garden Area Augmentation Piped Water Supply Scheme (Zone-II) under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000149/2022-2023 | 1423/JD | 15/07/2022 | 02/01/2026 | M/S A.B.G. CONSTRUCTION | 151.77 | 50.68 | 33.39 | 10
43 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Providing Functional Household Tap Connection (Phase - II ) in connection with Jal Jeevan Mission for Augmentation of Chamurchi T.G. P.W.S.S (Zone -III) under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000368/2023-2024 | 1463/JD | 06/10/2023 | 02/09/2025 | MALAY BHOWMIK | 27.18 | 0 | 0 | 50
44 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Construction of Boundary Wall at 3rd T/W site of Chamurchi Tea Garden Piped W/S scheme (Zone-II, Gumpha Line) along with pipeline repairing and other allied works in connection with JJM at Banarhat Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000190/2025-2026 | 2156/JD | 29/10/2025 | 28/11/2025 | DITIPRIYA CHOWDHURY | 11.72 | 0 | 0 | 0
Total | [13 empty] | 896.94 | 440.66 | 49.13