## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | Water Supply Arrangement for Anganwadi Center in different location within Maynaguri Block (Other than PWSS) under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000265/2021-2022 | 2043/JD | 07/12/2021 | 28/12/2021 | R.S CONSTRUCTION | 23.13 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | Drinking Water Supply Arrangement in Anganwadi Centers in other than PWSS different location within Rungamuttee Gram Panchayat under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000444/2021-2022 | 245/JD | 27/01/2022 | 28/03/2022 | B.M CONSTRUCTION | 95.02 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | Providing drinking water arrangement in (all type) / Health Centre under Matialy Block(Phase-II) under Mal Sub-Division under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000598/2021-2022 | 1056/JSSD | 24/01/2022 | 08/02/2022 | ALICK DUTTA | 4.31 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | Providing Drinking water arrangement in AWC/School (all type) Health Centre under Matialy Block (Phase - I) under Mal Sub-Division, under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000591/2021-2022 | 1045/JSSD | 24/01/2022 | 08/02/2022 | DREAM CONSTRUCTION | 4.65 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | Providing Functional Household Tap Connection (FHTC) in connection for Jal sapna in AWC,Govt.School & others institution under the command area of different piped Water Supply Scheme in Maynaguri Block under Jalpaiguri Division , P.H.E. Dte ( PHASE-II ) |  |  | ORD/000586/2021-2022 | 177/RWS | 03/03/2022 | 18/03/2022 | DREAM CONSTRUCTION | 4.84 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | Providing Functional House Hold Tap Connection in connection with Jalswapna in School ICDS Centre and Health Centre at various water supply scheme at Matiali Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000724/2021-2022 | 996/JSSD | 05/01/2022 | 20/01/2022 | ALICK DUTTA | 4.49 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | Drinking Water Supply Arrangement in Anganwadi Centers in other than PWSS different location within Oodlabari Gram Panchayat under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000458/2021-2022 | 129/JD | 14/01/2022 | 15/03/2022 | M/S R.N. TRADERS | 94.96 | 8.59 | 9.04 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | Drinking Water Supply Arrangement in Anganwadi Centres other than PWSS in different Location Within Chengmari Gram Panchayet under Jalpaiguri Division, P.H.E. Dte.(Phase-II) |  |  | ORD/000667/2021-2022 | 1062/JSSD | 24/01/2022 | 23/02/2022 | DINABANDHU ROY | 4.57 | 4.53 | 99.17 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | Drinking Water Supply Arrangement in Anganwadi Centers in other than PWSS different location within Tesimla Gram Panchayat under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000589/2021-2022 | 736/JD | 17/03/2022 | 01/05/2022 | PROSENJIT BASAK | 62.1 | 25.34 | 40.81 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | WATER SUPPLY ARRANGE MENT FOR ANGANWADI CENTER |  |  | VCH/001240/2021-2022 |  | 15/03/2022 | 15/03/2022 | SUKES BASU MAJUMDAR | 92 | 0 | 0 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | WATER SUPPLY ANGANWADI SADAR BLOCK |  |  | VCH/001799/2020-2021 | BP-2021-22-411 | 23/03/2022 | 23/03/2022 | SUKES BASU MAJUMDAR | 21.02 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | ANGANWADI CENTER |  |  | VCH/000320/2022-2023 | BP-2022-23-132 | 25/08/2022 | 25/08/2022 | ALICK DUTTA | 4.34 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | DRINKING WATER SUPPLY ANGANWADI RUNGAMUTTE GP |  |  | VCH/001339/2021-2022 | BP-2021-22-397 | 22/03/2022 | 22/03/2022 | B.M CONSTRUCTION | 94.71 | 0 | 0 | 0
14 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | WATER SUPPLY ARRANGE MENT FOR ANGANWADI CENTER |  |  | VCH/001237/2021-2022 |  | 15/03/2022 | 15/03/2022 | RAGHU DAS | 4.99 | 0 | 0 | 0
15 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | WATER SUPPLY ARRANGE MENT FOR ANGANWADI CENTER |  |  | VCH/001239/2021-2022 |  | 15/03/2022 | 15/03/2022 | M/S R.N. TRADERS | 92.97 | 0 | 0 | 0
16 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | LDS FHTC BHUSKADANGA |  |  | VCH/001267/2021-2022 | BP-2021-22-529 | 30/03/2022 | 30/03/2022 | MRINMOY KANTI DUTTA | 13.77 | 0 | 0 | 0
17 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | WATER SUPPLY ARRANGE MENT FOR ANGANWADI CENTER |  |  | VCH/001238/2021-2022 |  | 15/03/2022 | 15/03/2022 | GOUTAM DAS | 4.99 | 0 | 0 | 0
18 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | WATER SUPPLY ARRANGE MENT FOR ANGANWADI CENTER |  |  | VCH/001236/2021-2022 |  | 15/03/2022 | 15/03/2022 | PRADIP SAHA | 4.99 | 0 | 0 | 0
19 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | DRINKING WATER SUPPLY ARRANGEMENT AWC UNDER TISIMLA GP |  |  | VCH/000047/2022-2023 | BP-2021-22-30 | 28/04/2022 | 28/04/2022 | PROSENJIT BASAK | 11.61 | 0 | 0 | 0
20 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | DRINKING WATER SUPPLY ARRANGEMENT FOR AWC WITH IN ODLABARI G.P |  |  | VCH/000054/2022-2023 | BP-2021-22-11 | 25/04/2022 | 25/04/2022 | M/S R.N. TRADERS | 82.53 | 0 | 0 | 0
21 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | WATER SUPPLY ARRANGEMENT FOR ANGANWADI CENTER |  |  | VCH/000312/2022-2023 | BP-2022-23-133 | 25/08/2022 | 25/08/2022 | ALICK DUTTA | 4.28 | 0 | 0 | 0
22 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | Providing Functional Household Tap Connection (FHTC) at different Institutions within Jalpaiguri Sadar Block in connection with Jalsapna under Jalpaiguri Division , P.H.E. Dte . |  |  | ORD/000522/2021-2022 | 162/RWS | 28/02/2022 | 30/03/2022 | BISWAJIT BHADURI | 4.79 | 0 | 0 | 0
23 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | Providing Tap water supply connection in connection related to Jalswapna in school, ICDS Centre and Health Centre at Oodlbari, Syli T.G. Aibhil TG. Karbala TG & Malbazar Municipality Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  |  | ORD/000542/2021-2022 | 988/JSSD | 03/01/2022 | 18/01/2022 | SOUVIK SAHA | 4.64 | 0 | 0 | 0
24 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | Drinking water supply arrangement in anganwadi centers other than PWSS in different location within Chapadanga Gram Panchayet under Jalpaiguri Division, P.H.E. Dte. (Phase-I) |  |  | ORD/000605/2021-2022 | 1058/JSSD | 24/01/2022 | 08/02/2022 | D. S. ENTERPRISE | 4.56 | 0 | 0 | 0
25 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | Repairing of Rig Bore Tubewell/Tara Tubewell/Hand Pump Tubewell of different School and Anganwadi Centres under Mal & Kranti Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000389/2022-2023 | 364/JD | 20/02/2023 | 06/03/2023 | RAGHU DAS | 1.63 | 1.63 | 100 | 0
26 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | Providing Functional Household Tap Connection (FHTC) at Anganwadis, Health Centres and Schools in connection with Jal Swapna under the command area of different piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000252/2021-2022 | 1993/JD | 03/12/2021 | 18/12/2021 | SAPTASWA SARKAR | 19.19 | 18.02 | 93.89 | 0
27 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | Drinking water supply arrangement in anganwadi Centres other than PWSS in different location within Chapadanga Gram Panchayet under Jalpaiguri Division, P.H.E. Dte. (Phase-II) |  | Junior Engineer | ORD/000670/2021-2022 | 1063/JSSD | 24/01/2022 | 13/02/2022 | N.M. CONSTRUCTION | 4.57 | 4.45 | 97.38 | 0
28 | JALPAIGURI |  | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). | SM/08965 | Anganwadi | Dringking water supply arrangement in Anganwadi Center other than PWSS in different location Chengmari Gram Panchayat under Jalpaiguri Division PHE.Dte (PHASE - I) |  |  | ORD/000816/2021-2022 | 1110/W/JSSD | 27/01/2022 | 16/02/2022 | GOURAB GUHA ROY | 4.57 | 4.63 | 101.31 | 0
Total | [13 empty] | 774.21 | 67.18 | 8.68