## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. | SM/09099 | Retrofitting | UTTAR BHUSKA DANGA |  |  | VCH/000924/2021-2022 | BP-2021-22-114 | 03/12/2021 |  | BALARAM GHOSH | 4.8 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. | SM/09099 | Retrofitting | Retrofitting works in connection with FHTC of Natun para , Borobari and Malar Math under Uttar Bhuskadanga W/S/S under Jalpaiguri Division , P.H.E Dte |  | Junior Engineer | ORD/000332/2021-2022 | 743/RWS | 08/10/2021 | 23/10/2021 | BALARAM GHOSH | 2.86 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. | SM/09099 | Retrofitting | OHR UTTARBHUSKA DANGA PWSS |  |  | VCH/000262/2022-2023 | BP-2022-23-70 | 06/07/2022 |  | UNIBRO INFRASERV PRIVATE LIMITED | 13.07 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. | SM/09099 | Retrofitting | LDS AND FHTC FOR AUG OF UTTAR BHUSKADANGA PWSS |  |  | VCH/000310/2022-2023 | BP-2022-23-86 | 02/08/2022 |  | MRINMOY KANTI DUTTA | 29.73 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. | SM/09099 | Retrofitting | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF UTTAR BHUSKADANGA PIPED WATER SUPPLY SCHEME BLOCK : MAYNAGURI DISTRICT : JALPAIGURI |  | Junior Engineer | ORD/000356/2021-2022 | 254/JD | 31/01/2022 | 01/04/2022 | MRINMOY KANTI DUTTA | 79.88 | 5.52 | 6.91 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. | SM/09099 | Retrofitting | Retrofitting works in connection with FHTC works for the habitation of Monosha Mandir para & Bura Amtolar Gali under Bhuskadanga W/S/S under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000018/2022-2023 | 307/RWS | 28/04/2022 | 13/05/2022 | BALARAM GHOSH | 0.77 | 0.77 | 99.98 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. | SM/09099 | Retrofitting | Laying distribution system for Piped Water Supply Scheme for Jogesh Chandra Tea Garden at Malbazar Block under Jalpaiguri Division, P.H.E. Dte. (Part-G)" |  | Junior Engineer | ORD/000193/2019-2020 | 1209/JD | 28/11/2019 | 28/12/2019 | KNIGHT CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 8.97 | 2.01 | 22.42 | 1
8 | JALPAIGURI |  | Jalpaiguri Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. | SM/09099 | Retrofitting | Construction of cement concrete drain , pathway , store below OHR and culvert etc. at H/W site campus of Dakshin Salbari W/S/S under Jalpaiguri Division , P.H.E Dte. |  | Junior Engineer | ORD/000170/2021-2022 | 679/RWS | 27/09/2021 | 27/10/2021 | R.S CONSTRUCTION | 4.85 | 4.86 | 100.27 | 1
9 | JALPAIGURI |  | Jalpaiguri Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. | SM/09099 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within Garalbari Zone- III under Jalpaiguri Sadar Block in connection with Jal Sapna under Jalpaiguri Division PHE Dte. (Part-J) | Assistant Engineer | Junior Engineer | ORD/000277/2022-2023 | 642/RWS | 21/10/2022 | 10/11/2022 | SOMNATH ROY | 4.82 | 4.68 | 97.04 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. | SM/09099 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within Garalbari Zone-III under Jalpaiguri Sadar Block in connection with Jal Sapna under Jalpaiguri Division PHE Dte. (Part-K) | Assistant Engineer | Junior Engineer | ORD/000278/2022-2023 | 643/RWS | 21/10/2022 | 10/11/2022 | J.M. CONSTRUCTION | 3.73 | 3.1 | 83.19 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. | SM/09099 | Retrofitting | Continuation Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer R.W.S Sub-Division PHE Dte Jalpaiguri (with valid Taxi permit). Period from 01/02/2023 to 31/05/2023. |  | Junior Engineer | ORD/000496/2022-2023 | 72/RWS | 31/01/2023 | 31/05/2023 | APIKUL ALI | 0.59 | 0.59 | 100 | 100
12 | JALPAIGURI |  | Jalpaiguri Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. | SM/09099 | Retrofitting | Construction of 250 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for REJUVENATION OF UTTAR BHUSKADANGA & GARTALI JALPESH PIPED WATER SUPPLY SCHEME, under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000030/2022-2023 | 976/JD | 20/04/2022 | 18/08/2022 | UNIBRO INFRASERV PRIVATE LIMITED | 57.66 | 41.67 | 72.28 | 100
Total | [13 empty] | 211.74 | 63.21 | 29.85