## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | SM/09100 | Retrofitting | FHTC GRASSMORE T.G PWSS |  |  | VCH/001330/2021-2022 | BP-2021-22-469 | 28/03/2022 | 28/03/2022 | SWAPAN SAHA | 9.59 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | SM/09100 | Retrofitting | FHTC MALLICKSOVA PWSS |  |  | VCH/001353/2021-2022 | BP-2021-22-466 | 27/03/2022 | 27/03/2022 | BOSE ENTERPRISE | 65.35 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | SM/09100 | Retrofitting | Providing Functional Household Tap Connection (FHTC) including retrofitting works in connection with Jal Sapna under the command area of Mallicksova Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Part-A) |  | Junior Engineer | ORD/000338/2021-2022 | 193/JD | 21/01/2022 | 22/03/2022 | BOSE ENTERPRISE | 172.88 | 62.22 | 35.99 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | SM/09100 | Retrofitting | Providing Functional Household Tap Connection (FHTC) including retrofitting works in connection with Jal Sapna under the command area of Mallicksova Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Part-B) | Assistant Engineer,HQ | Junior Engineer | ORD/000002/2022-2023 | 882/JD | 05/04/2022 | 04/06/2022 | M/S NANDY ENTERPRISE | 182.16 | 69.91 | 38.38 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | SM/09100 | Retrofitting | Construction of 250 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for REJUVENATION OF KILKOT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME, Block- Matiali, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000377/2021-2022 | 350/JD | 03/02/2022 | 03/06/2022 | NARENDRA KUMAR | 57.75 | 8.61 | 14.9 | 100
6 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | SM/09100 | Retrofitting | Partial Retrofitting work for Riabari T.G.Area with repairing of rising main, including damaged/Chokage line repairing due to local developmnet works, direct Pumping arrangement from 2nd pump within the command area of Riabari T.G. P.W.S.S. under Jalsapna programme at Dhupguri Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000203/2022-2023 | 1742/JD | 08/09/2022 | 29/09/2022 | SAPTASWA SARKAR | 15.65 | 15.81 | 101 | 1
7 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | SM/09100 | Retrofitting | Shifting of pipeline by PWD road widening work from Thuta Pakri to Nirashi Via comperhat at Goralbari Zone- II piped Water Supply Scheme Jalpaiguri Sadar Block under Jalpaiguri |  | Junior Engineer | ORD/000200/2019-2020 | 302/JD | 17/03/2020 | 15/07/2020 | BILTU DAS | 47.59 | 15.74 | 33.07 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | SM/09100 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000008/2021-2022 | 180/JD | 21/01/2022 | 21/01/2022 | Resource Division | 2.99 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | SM/09100 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000075/2024-2025 | 2206/JD | 01/12/2024 | 01/12/2024 | Resource Division | 26.77 | 0 | 0 | 0
Total | [13 empty] | 580.72 | 172.28 | 29.67