## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | Laying distribution system for Augmentation of Binnaguri Piped water Supply Scheme at Rajganj Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000453/2021-2022 | 332/JD | 02/02/2022 | 02/06/2022 | M/S NANDY ENTERPRISE | 458.51 | 274.45 | 59.86 | 1
2 | JALPAIGURI |  | Northern Mechanical | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under Binnaguri (Rajganj Block) W/S Scheme at T/W No. I & II in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000005/2022-2023 | 208/NMD | 04/04/2022 | 25/04/2022 | BONANZA ENTERPRISE | 4.78 | 4.78 | 100 | 0
3 | JALPAIGURI |  | Central Drilling | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AUG. OF BINNAGURI (W/S SCHEME) , RAJGANJ BLOCK, UNDER JALPAIGURI DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000112/2022-2023 | 395/CMSD-II (D) | 01/08/2022 | 16/08/2022 | PADMA ENGINEERING & CO. | 4.53 | 4.13 | 91.15 | 0
4 | JALPAIGURI |  | Central Drilling | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | ADDITIONAL WORK FOR DRILLING BOLDER/SAND STONE ZONE AT AUG. OF BINNAGURI W/S SCH, UNDER JALPAIGURI DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000145/2022-2023 | 407/CMSD-II | 12/08/2022 | 22/08/2022 | PADMA ENGINEERING & CO. | 0.97 | 0.97 | 100 | 0
5 | JALPAIGURI |  | Central Drilling | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | PROVIDING DRILLING CREWS INCLUDING OTHERS MATERIALS & WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 100 MTR DEPTH) BY DEPARTMENTAL RIG MACHINE FOR AUG. OF BINNAGURI (W/S SCHEME) , RAJGANJ BLOCK UNDER JALPAIGURI DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000113/2022-2023 | 394/CMSD-II (D) | 01/08/2022 | 16/08/2022 | PADMA ENGINEERING & CO. | 4.3 | 2.82 | 65.55 | 0
6 | JALPAIGURI |  | Northern Mechanical | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under BINNAGURI (AUG) W/S Scheme, at TW No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000067/2022-2023 | 442/NMD | 14/06/2022 | 05/07/2022 | MALAY KUMAR SAHA | 2.77 | 2.77 | 100 | 0
7 | JALPAIGURI |  | Central Drilling | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | PROVIDING ADDITIONAL BENTONITE & OTHER ADDITIONAL WORKS FOR CONSTRUCTION OF TUBE WELL AT AUG. OF BINNAGURI W/S SCH UNDER JALPAIGURI DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000144/2022-2023 | 408/CMSD-II | 12/08/2022 | 22/08/2022 | PADMA ENGINEERING & CO. | 0.96 | 0.96 | 100 | 0
8 | JALPAIGURI |  | Northern Mechanical | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | New Service Connection Charge for T/W No. V of MORAGHAT TEA GARDEN NEAR HOSPITAL W/S Scheme under BANRHAT CCC [APPLICATION NO.4002888889, Reference ID : 402788875] |  |  | VCH/000149/2022-2023 | BP/2022-23/14 | 16/06/2022 | 16/06/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | Installation of Iron Elimination Plant (Capacity 20m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain for augmentation at 3 rd Tubewell site of BINNAGURI piped water supply scheme under JALPAIGURI Division PHE Dte . BLOCK - RAJGANJ DISTRICT - JALPAIGURI. | Assistant Engineer,HQ | Junior Engineer | ORD/000348/2022-2023 | 136/JD | 17/01/2023 | 03/03/2023 | SUBIR GHOSH | 14.72 | 11.2 | 76.07 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | Supply of Sluice valve C.I. Specials at Binnaguri for laying of DI line from OHR to UPVC Pipe line in connection with Augmentation of Binnaguri W/S Scheme under Jalpaiguri Division, PHE Dte. |  |  | ORD/000036/2023-2024 | 389/RWS | 25/04/2023 | 09/05/2023 | B.M CONSTRUCTION | 3.31 | 3.31 | 100 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | Construction of Boundary Wall with gate, drain for 3rd Tube well site of Binnaguri Piped water supply scheme under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000101/2023-2024 | 444/JD. | 08/06/2023 | 29/06/2023 | ETHERIA EDIFICE (OPC) PVT. LTD. | 5.29 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | Extra Laying of Water Distribution System, construction of valve chamber and other ancillary works for Augmentation of Binnaguri PWSS at Binnaguri at Block - Rajganj under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000136/2023-2024 | 706/JD | 13/07/2023 | 03/08/2023 | M/S KARMAKAR CONSTRUCTION | 29.75 | 25.32 | 85.11 | 80
13 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission under the command area of Binnaguri (Fulbari-II) for Augmentation of Binnaguri Piped Water Supply Scheme at Block- Rajganj under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000532/2023-2024 | 1852/JD | 15/12/2023 | 29/01/2024 | SUNIL ROY | 17.04 | 0 | 0 | 0
14 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) with sanitary & plumbing arrangement at 3rd Tube well site for Binnaguri (Fulbari) Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000350/2022-2023 | 133/JD | 17/01/2023 | 03/03/2023 | ETHERIA EDIFICE (OPC) PVT. LTD. | 4.65 | 4.65 | 100 | 100
15 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | Installation of Iron Elimination Plant (capacity-50m3/hr.) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain for augmentation at head work site of BINNAGURI piped water supply scheme under JALPAIGURI Division PHE Dte . BLOCK - RAJGANJ DISTRICT JALPAIGURI | Assistant Engineer,HQ | Junior Engineer | ORD/000353/2022-2023 | 165/JD | 19/01/2023 | 05/03/2023 | KANAI LAL SEN | 19.8 | 19.46 | 98.29 | 100
16 | JALPAIGURI |  | Northern Mechanical | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BINNAGURI PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000753/2022-2023 | 53/NMD | 24/01/2023 | 23/02/2023 | SUNLIT | 10.1 | 8.37 | 82.9 | 100
17 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | Repairing of OHR and repairing valve chamber & other ancillary works Binnaguri Head Work site under Binnaguri Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000316/2023-2024 | 1228/JD | 11/09/2023 | 02/10/2023 | KANAI LAL SEN | 6.87 | 6.54 | 95.2 | 100
18 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | SUPPLY OF FUEL |  |  | BILL/00398/2022-2023 | BP-2022-23-522 | 15/03/2023 | 15/03/2023 | FILL & SMILE | 0.33 | 0 | 0 | 0
19 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | Laying of Water Distribution System and other ancillary works for Augmentation of Binnaguri PWSS at Block-Rajganj under Jalpaiguri Division, P.H.E. Dte. (Part-A) | Assistant Engineer,HQ | Junior Engineer | ORD/000482/2024-2025 | 2408./JD | 20/12/2024 | 01/08/2025 | M/S KARMAKAR CONSTRUCTION | 40.9 | 0 | 0 | 100
20 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | Repairing of pump house, boundary wall, land development and construction of drain, repairing valve chamber & other ancillary works at Augmentation of Binnaguri head works site under Binnaguri piped water supply scheme under Jalpaiguri Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000543/2023-2024 | 1934/JD | 02/01/2024 | 23/01/2024 | GOPRO CONSTRUCTION | 4.2 | 4.12 | 98.03 | 100
21 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | Laying Interconnection Network Between Iron Elimination Plant and Overhead Reservoir, Land Development and Construction of C.C. Road at Head Work Site of Binnaguri PWSS (Fulbari-II) at Raiganj Block, under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000135/2024-2025 | 1301/JD | 05/09/2024 | 31/07/2025 | KANAI LAL SEN | 6.43 | 0 | 0 | 100
22 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2024-2025 | 2102/JD | 25/11/2024 | 25/11/2024 | Resource Division | 101.9 | 0 | 0 | 0
23 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | Augmentation | SUPPLY OF FUEL (DIESEL) FOR VEHICLES UNDER JALPAIGURI DIVISION PHE DTE. FOR THE MONTH OF DECEMBER 2023 AND JANUARY 2024 |  |  | BILL/01247/2023-2024 | BP-2023-24-665 | 22/02/2024 | 22/02/2024 | FILL & SMILE | 1.9 | 0 | 0 | 0
Total | [13 empty] | 744.71 | 373.88 | 50.2