## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | Providing Functional Household Tap Connection in connection with Jal Swapna/JJM with minor retrofitting works under Domohani Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Phase-V) | Assistant Engineer,HQ | Junior Engineer | ORD/000232/2022-2023 | 2008/JD | 01/11/2022 | 01/12/2022 | ALOKE DEY | 40.21 | 33.14 | 82.41 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | Providing Functional Household Tap Connection (FHTC) with retrofitting works in connection with Jaldhara / Jal Sapna under the command area of Domohani Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, P.H.E Dte. (Phase-IV) | Assistant Engineer,HQ | Junior Engineer | ORD/000055/2022-2023 | 939/JD | 18/04/2022 | 02/06/2022 | PRADIP KR SEN | 4.85 | 4.85 | 99.98 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | fhtc domohani |  |  | VCH/000024/2022-2023 | BP-2021-23-1 | 21/04/2022 | 21/04/2022 | PRADIP KR SEN | 4.57 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | DPR PREPARATION |  |  | VCH/001143/2021-2022 | BP-2021-22-262 | 16/02/2022 | 16/02/2022 | SUBHANKAR GHOSH | 2.37 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | FHTC MOGOLKATA T.G PWSS |  |  | VCH/001383/2021-2022 | BP-2021-22-498 | 29/03/2022 | 29/03/2022 | PROFULLA GHOSH | 30.06 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | LDS INDONG T.G |  |  | VCH/001412/2021-2022 | BP-2021-22-546 | 31/03/2022 | 31/03/2022 | KANAI LAL SEN | 16.3 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | SINKING REJ CHOUHADDI |  |  | VCH/001379/2021-2022 | BP-2021-22-545 | 31/03/2022 | 31/03/2022 | J.M. CONSTRUCTION | 7 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | Laying Distribution System for Augmentation of Domohani Piped Water Supply Scheme at Moynaguri Block under Jalpaiguri Division, PHE Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000546/2021-2022 | 661/JD | 09/03/2022 | 07/06/2022 | SUKES BASU MAJUMDAR | 335.53 | 345.54 | 102.98 | 1
9 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | Shifting of pipeline in connection with PWD road widning work from Domohani PWSS at Moynaguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000027/2022-2023 | 975/JD | 20/04/2022 | 04/06/2022 | PROVA CONSTRUCTION | 38.07 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | Renovation of front side boundary wall and construction of shade over front door of the pump house and ancillary works of the 2nd tube well site of Domohani Water Supply Scheme under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000213/2022-2023 | 1803/JD | 14/09/2022 | 05/10/2022 | M/S SURAJIT DEY AND CO. | 2.41 | 0 | 0 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | Construction of Pump (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement at 3rd tube well site of Augmentation Domohoni W/S Scheme under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000048/2022-2023 | 1193/JD | 20/05/2022 | 04/07/2022 | GANAPATI CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 4.65 | 4.65 | 100 | 100
12 | JALPAIGURI |  | Central Drilling | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 123 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR DOMOHANI PWSS, JALPAIGURI DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000339/2022-2023 | 1775/CDD | 02/01/2023 | 01/02/2023 | PADMA ENGINEERING & CO. | 11.99 | 10.56 | 88.13 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2021-2022 | 54/JD | 05/01/2022 | 05/01/2022 | Resource Division | 5.5 | 0 | 0 | 0
14 | JALPAIGURI |  | Northern Mechanical | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | Infrastructure Cost for DOMOHANI MAYNAGURI, T/W III, under MAYNAGURI CCC, [APPLICATION NO. 100000084156, Reference ID : 860276006] |  |  | BILL/00571/2023-2024 | BP/23-24/68 | 09/08/2023 | 09/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.96 | 0 | 0 | 0
15 | JALPAIGURI |  | Northern Mechanical | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | New Service Connection Charge for DOMOHANI MAYNAGURI, T/W III, under MAYNAGURI CCC, [APPLICATION NO. 4003107329, Reference ID : 402974759] |  |  | BILL/00570/2023-2024 | BP/23-24/68 | 09/08/2023 | 09/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
16 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Domohani piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Phase-III) | Assistant Engineer,HQ | Junior Engineer | ORD/000051/2021-2022 | 1066/JD | 02/07/2021 | 23/07/2021 | PRADIP KR SEN | 4.82 | 4.57 | 94.76 | 0
17 | JALPAIGURI |  | Northern Mechanical | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of DOMOHANI PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000851/2022-2023 | 266/NMD | 21/03/2023 | 20/04/2023 | HARAGOURI ENTERPRISE | 10.12 | 10.12 | 99.95 | 50
18 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | Construction of Boundary wall, Blower Room, IEP of 3rd Pump House & Providing FHTC of Domohani PWSS, in connection with Augmentation of Domohani PWSS under Jal Jeevan Mission at Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000390/2023-2024 | 1554/JD | 01/11/2023 | 31/12/2023 | B.M CONSTRUCTION | 67.78 | 68.45 | 101 | 100
19 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | Rejuvenation of different components of Head Work Site of Domohani PWSS under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000537/2023-2024 | 1972/JD | 03/01/2024 | 17/02/2024 | SUKES BASU MAJUMDAR | 39.34 | 40.38 | 102.65 | 100
20 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | Engagement of Block Level Staff (Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Maynaguri block in Connection with JJM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000804/2023-2024 | 256/RWS | 07/03/2024 | 06/04/2024 | B.M CONSTRUCTION | 3.11 | 3.11 | 100 | 100
21 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2024-2025 | 2099/JD | 25/11/2024 | 25/11/2024 | Resource Division | 80.22 | 0 | 0 | 0
22 | JALPAIGURI |  | Central Drilling | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | Continuation for Hiring of Diesel Driven Motor Cab (BS-IV & Above) (Non AC) having contract carriage permit along with driver for the office of The Assistant Engineer, Mech./Elect. Planning Wing, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000056/2024-2025 | 244/S&WSD | 30/12/2024 | 02/07/2025 | NEMAI CHANDRA NAIYA | 0.87 | 1.98 | 226.55 | 0
23 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | Construction of Blower Room with Rejuvenation of IEP in connection with JJM of Augmentation of Domohani Water Supply Scheme at Maynaguri Development Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000438/2024-2025 | 2313./JD | 11/12/2024 | 10/04/2025 | SUKES BASU MAJUMDAR | 20.93 | 0 | 0 | 100
24 | JALPAIGURI |  | Northern Mechanical | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF DOMOHANI PWSS at TW No. IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000528/2024-2025 | 2122/NMD | 26/12/2024 | 01/07/2025 | M/S DILIP MITRA | 11.24 | 0 | 0 | 80
Total | [13 empty] | 752.59 | 527.36 | 70.07