## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | Retrofitting works including FHTC at Shubhachandi, Futkibari Including FHTC for Garalbari Zone ¿ II . W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000274/2021-2022 | 818/RWS | 30/11/2021 | 15/12/2021 | BISWAJIT BHADURI | 4.38 | 0 | 0 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Garalbari Zone-I W/S Scheme under Jalpaiguri Division PHE Dte. (Part-E) |  | Junior Engineer | ORD/000541/2021-2022 | 545/JD | 28/02/2022 | 21/03/2022 | RABINDRANATH DUTTA | 15.82 | 0 | 0 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | FHTC BHANDANI |  |  | VCH/000250/2022-2023 | BP-2022-23-71 | 04/07/2022 | 04/07/2022 | DULAL CHOUDHURY | 3.34 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | IEP GORAL BARI |  |  | VCH/001206/2021-2022 | BP-2021-22-319 | 28/02/2022 | 28/02/2022 | BISWAJIT BHADURI | 3.85 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | REP OF PUMP HOUSE FOR GORALBARI PWSS |  |  | VCH/000324/2022-2023 | BP-2022-23-128 | 23/08/2022 | 23/08/2022 | BISWAJIT BHADURI | 0.42 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | REJ, GORALBARI |  |  | VCH/000908/2021-2022 | BP-2021-22-139 | 14/12/2021 | 14/12/2021 | BISWAJIT BHADURI | 2.66 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | REJ. GORALBARI PWSS |  |  | VCH/000913/2021-2022 | BP-2021-22-136 | 14/12/2021 | 14/12/2021 | RANJIT KARMAKAR | 4.88 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | REPAIRING & RENOVATION OHR GORALBARI ZONE -II |  |  | VCH/001376/2021-2022 | BP-2021-22-539 | 31/03/2022 | 31/03/2022 | BISWAJIT BHADURI | 3.76 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | REP OF PUMP HOUSE FOR GORALBARI PWSS |  |  | VCH/000318/2022-2023 | BP-2022-23-127 | 25/08/2022 | 25/08/2022 | ASIT PAUL | 0.48 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | FHTC GORALBARI PWSS |  |  | VCH/000242/2022-2023 | bp2022-23-52 | 08/06/2022 | 08/06/2022 | BISWAJIT BHADURI | 14.47 | 0 | 0 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | IEP GORALBARI |  |  | VCH/001204/2021-2022 | BP-2021-22-322 | 28/02/2022 | 28/02/2022 | DREAM CONSTRACTION | 3.85 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | REPAIRING H/W GORALBARI ZONE -II |  |  | VCH/001375/2021-2022 | BP-2021-22-538 | 31/03/2022 | 31/03/2022 | ASIT PAUL | 4.35 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | REPAIRING & MAINTENANCE GORALBARI WSS |  |  | VCH/001378/2021-2022 | BP-2021-22-537 | 31/03/2022 | 31/03/2022 | PRADIP SAHA | 4.2 | 0 | 0 | 0
14 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | FHTC GORALBARI ZONE-I |  |  | VCH/001387/2021-2022 | BP-2021-22-548 | 31/03/2022 | 31/03/2022 | RABINDRANATH DUTTA | 14.9 | 0 | 0 | 0
15 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | rep. and renovetion of garalbari zone-ii |  |  | VCH/000045/2022-2023 | BP-2021-22-17 | 26/04/2022 | 26/04/2022 | ASIT PAUL | 4.35 | 0 | 0 | 0
16 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | LDS FHTC AUG BAIKUR PART V |  |  | VCH/001317/2021-2022 | BP-2021-22-438 | 26/03/2022 | 26/03/2022 | MINTU CHAKRABORTY | 78.25 | 0 | 0 | 0
17 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | REJ. GORALBARI PWSS |  |  | VCH/000907/2021-2022 | BP-2021-22-138 | 14/12/2021 | 14/12/2021 | BISWAJIT BHADURI | 3.12 | 0 | 0 | 0
18 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | IEP GORAL BARI |  |  | VCH/001205/2021-2022 | BP-2021-22-323 | 28/02/2022 | 28/02/2022 | RAGHU DAS | 3.87 | 0 | 0 | 0
19 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | RE OF PUMP HOUSE B-WAAL FOR GORALBARI PWSS |  |  | VCH/000323/2022-2023 | bp2022-23 | 25/08/2022 | 25/08/2022 | PRADIP SAHA | 0.47 | 0 | 0 | 0
20 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | Sinking of 3 No. 250 mm x 150 mm x 132 m deep Rig Bored tube well by Reverse Rotary method of drilling for Rejuvenation of Goralbari Piped Water Supply Scheme (I, II, III) under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000061/2022-2023 | 1217/JD | 26/05/2022 | 25/06/2022 | JAYANTA GHOSH | 22.7 | 0 | 0 | 0
21 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | Providing Functional Household Tap Connection (FHTC) including Retrofitting at Pradhan Para, Choudhury Para, Haripukuri, Uttar & Dakshin Danga para, Jamuri bari and Camperhat within Garalbari Zone-II W/S Scheme under Jalpaiguri Sadar Block in connection with Jal Sapna under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000515/2021-2022 | 539/JD | 25/02/2022 | 27/03/2022 | BISWAJIT BHADURI | 29.32 | 0 | 0 | 100
22 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | Providing Functional Household Tap Connection (FHTC) including Retrofitting at Sarkar Para, along PWD Road, Pranabananda Para, Baruapara, Moulani, Konpakri, Berubari More, Dangapara, Dhapganj etc. within Garalbari Zone-III W/S Scheme under Jalpaiguri Sadar Block in connection with Jal Sapna under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000514/2021-2022 | 538/JD | 25/02/2022 | 26/04/2022 | ASIM GUPTA | 92.47 | 0 | 0 | 1
23 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | Retrofitting at Barodhighi,CWC Road, Baroghoria, Koharapara and adjacent area within Garalbari Zone-II under Jalpaiguri Sadar Block in connection with Jaldhara/ Jal Sapna under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000238/2022-2023 | 1890/JD | 22/09/2022 | 22/10/2022 | MONOJ GHOSH | 26.94 | 0 | 0 | 100
24 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | Infrastructure Cost for GARALBARI, ZONE-I , T/W III, under MASKALAIBARI CCC, [APPLICATION NO. 100000078007, Reference ID : 860269067] |  |  | BILL/00589/2023-2024 | BP/23-24/73 | 11/08/2023 | 11/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 23.18 | 0 | 0 | 0
25 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | New Service Connection Charge for GARALBARI, ZONE-I , T/W III, under MASKALAIBARI CCC, [APPLICATION NO. 4003154244, Reference ID : 403015424] |  |  | BILL/00588/2023-2024 | BP/23-24/73 | 11/08/2023 | 11/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
26 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | New Service Connection Charge for GARALBARI , T/W III,ZONE-II under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4003119639, Reference ID : 403023006] |  |  | BILL/00507/2023-2024 | BP/23-24/56 | 14/07/2023 | 14/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
27 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | New Service Connection Charge for GARALBARI , T/W III,ZONE-III under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4003132474, Reference ID : 403012261] |  |  | BILL/00511/2023-2024 | BP/23-24/56 | 14/07/2023 | 14/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
28 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | Infrastructure Cost for GARALBARI , T/W III,ZONE-II under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 100000079173, Reference ID : 860270383] |  |  | BILL/00506/2023-2024 | BP/23-24/56 | 14/07/2023 | 14/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.58 | 0 | 0 | 0
29 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | Infrastructure Cost for GARALBARI , T/W III,ZONE-III under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 100000077688, Reference ID : 860269318] |  |  | BILL/00510/2023-2024 | BP/23-24/56 | 14/07/2023 | 14/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.89 | 0 | 0 | 0
30 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | Supply, Installation, Commissioning (Trial run for 3 months) including testing of 3 Nos. 20.00 cum per hour capacity pressure type IEP with accessories including construction of Blower Rooms (3.60MX3.00M ) Size, concrete platform & drain ...etc for Rejuvenation of Garalbari water supply scheme (for Zone-I, Zone-II & Zone-III) under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000438/2022-2023 | 678/JD | 16/03/2023 | 30/04/2023 | D. S. ENTERPRISE | 53.46 | 0 | 0 | 100
31 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | Rising Main Connections(3 Nos.) including other necessary arrangement for Rejuvenation of Goralbari Piped Water Supply Scheme( Zone-I, Zone-II & Zone-III) under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000491/2022-2023 | 290/RWS | 29/03/2023 | 19/04/2023 | BAJRANG ENTERPRISE | 5.97 | 0 | 0 | 100
32 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF GARALBARI PWSS, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000878/2022-2023 | 342/NMD | 29/03/2023 | 28/04/2023 | SUMON ELECTRICAL | 31.97 | 0 | 0 | 100
33 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | Repair works of O.H.R. Pump Houses and Boundary walls .at Goralbari Zone-III Piped Water Supply Scheme Under Jalpaiguri Division PHE Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000154/2023-2024 | 814/RWS | 14/07/2023 | 04/08/2023 | TAPASH MOHANTA | 4.33 | 0 | 0 | 100
34 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 1027.92 | 0 | 0