## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Sajnapara Piped Water Supply Scheme | SM/09391 | Augmentation | Providing Functional Household Tap Connection in connection with Jal Swapna under the command area of Sajnapara Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, P.H.E. Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000211/2022-2023 | 1801/JD | 14/09/2022 | 05/10/2022 | RAGHU DAS | 4.37 | 0 | 0 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Sajnapara Piped Water Supply Scheme | SM/09391 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Sajnapara P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. |  | Junior Engineer | ORD/000502/2021-2022 | 97/JD | 10/01/2022 | 11/03/2022 | DEEP CONSTRUCTION | 4.65 | 0 | 0 | 0
3 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Sajnapara Piped Water Supply Scheme | SM/09391 | Augmentation | New Service Connection Charge for SAJNAPARA, TW No. III, DHUPGURI CCC, [APPLICATION NO. 4003147721, Reference ID : 403014075] |  |  | BILL/00061/2023-2024 | BP/23-24/15 | 24/05/2023 | 24/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Sajnapara Piped Water Supply Scheme | SM/09391 | Augmentation | Infrastructure Cost for SAJNAPARA, TW No. III, DHUPGURI CCC, [APPLICATION NO. 100000077914, Reference ID : 860269054] |  |  | BILL/00062/2023-2024 | BP/23-24/15 | 24/05/2023 | 24/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.52 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Sajnapara Piped Water Supply Scheme | SM/09391 | Augmentation | New Service Connection Charge for SAJNAPARA (REJU), T/W III, under DHUPGURI CCC, [APPLICATION NO. 4003123372, Reference ID : 402997124] |  |  | BILL/00029/2023-2024 |  | 04/05/2023 | 04/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Sajnapara Piped Water Supply Scheme | SM/09391 | Augmentation | Infrastructure Cost for SAJNAPARA (REJU), T/W III, under DHUPGURI CCC, [APPLICATION NO. 100000076670, Reference ID : 860268400] |  |  | BILL/00030/2023-2024 |  | 04/05/2023 | 04/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.41 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Sajnapara Piped Water Supply Scheme | SM/09391 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF SAJNAPARA PWSS, TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Driller-in-Charge | Junior Engineer | ORD/000888/2022-2023 | 371/NMD | 29/03/2023 | 28/04/2023 | M/S MATRI CONSTRUCTION | 11.25 | 0 | 0 | 100
8 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Sajnapara Piped Water Supply Scheme | SM/09391 | Augmentation | Fuel ,Lubricant ,Gear Oil & steering oil charges for Government Inspection vehicle under NMD PHE Dte. invoice No- 0063/2023-2024 , Dt. 31.10.2023 |  |  | BILL/01018/2024-2025 | BP/24-25/199 | 12/09/2024 | 12/09/2024 | M/S MILLENNIUM FUEL CENTRE | 0.24 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Sajnapara Piped Water Supply Scheme | SM/09391 | Augmentation | fuel Charges for Government Inspection Vehicle under NMD PHE Dte. Invoice No- 0033/2023-24 ,Dt. 1.07.2023 |  |  | BILL/01019/2024-2025 | BP/24-25/199 | 12/09/2024 | 12/09/2024 | M/S MILLENNIUM FUEL CENTRE | 0.06 | 0 | 0 | 0
10 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Sajnapara Piped Water Supply Scheme | SM/09391 | Augmentation | Fuel, Lubricant & coolant charges for Government Inspection vehicle under NMD PHE Dte. invoice No- 00047/2023-2024 , Dt. 31.08.2023 |  |  | BILL/01020/2024-2025 | BP/24-25/199 | 12/09/2024 | 12/09/2024 | M/S MILLENNIUM FUEL CENTRE | 0.21 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Sajnapara Piped Water Supply Scheme | SM/09391 | Augmentation | Fuel & Lubricant oil charges for Government Inspection vehicle under NMD PHE Dte. invoice No- 0069/2023-2024 , Dt. 30.11.2023 |  |  | BILL/01021/2024-2025 | BP/24-25/199 | 12/09/2024 | 12/09/2024 | M/S MILLENNIUM FUEL CENTRE | 0.32 | 0 | 0 | 0
12 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Sajnapara Piped Water Supply Scheme | SM/09391 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 578.39 | 0 | 0