## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | SM/09392 | Augmentation | LDS BARADIGHI |  |  | VCH/001385/2021-2022 | BP-2021-22-528 | 30/03/2022 | 30/03/2022 | GOUTAM DAS | 4.52 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | SM/09392 | Augmentation | LDS FHTC AUG KRANTI (ZONE -I) |  |  | VCH/001372/2021-2022 | BP-2021-22-527 | 30/03/2022 | 30/03/2022 | M/S SIBU DEY AND CO. | 9.39 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | SM/09392 | Augmentation | Providing Functional Household Tap Connection in connection with Jal Swapna/ JJM at various House hold and Govt. Aided Educational/ Health Institute under the command area of Rejuvenation of Kathalguri T.G. Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (Phase-III) | Assistant Engineer,HQ | Junior Engineer | ORD/000094/2022-2023 | 1300/JD | 14/06/2022 | 29/06/2022 | SAHA CONSTRUCTION | 2.15 | 2.18 | 101.2 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | SM/09392 | Augmentation | Repairing of Damaged distribution line due to drain construction by T.G. authority, Land development, re modification of distribution main along with other ancillary works within the command area of rejuvenation of Kathalguri T.G. P.W.S.S. under Jalpaiguri Division, P.H.E.Dte.and I.E.Plant etc. under Jalpaiguri Division, P.H.E.Dte. (from 01.08.2022 to 31.01.2023) | Assistant Engineer,HQ | Junior Engineer | ORD/000215/2022-2023 | 1805/JD | 14/09/2022 | 05/10/2022 | RABINDRANATH DUTTA | 4.83 | 4.83 | 99.98 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | SM/09392 | Augmentation | Resistivity test at two alternative Site and two reserved sites for sinking of Tube Well at Zone-II for Augmentation of Chamurchi Tea Garden Area Piped Water Supply Scheme and at Two Sites for Rejuvenation of Khthalguri T.G. P.W.S.S. under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000227/2022-2023 | 1856/JD | 16/09/2022 | 07/10/2022 | PARAMJYOTI ENTERPRISE | 1.25 | 1.25 | 99.81 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | SM/09392 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Kathalguri P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000508/2021-2022 | 107/JD | 11/01/2022 | 12/03/2022 | JITENDRA NATH ROY | 4.65 | 4.65 | 100 | 100
7 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | SM/09392 | Augmentation | Construction of 200 Cu.M. capacity R.C.C. Over Head Reservoir of 20 Mtr. Staging Height, Construction of One No. Pump House (5.40m x 3.60m) Boundary wall for the Head Works Site and other related works including pump connection of different pump for Rejuvenation of Kathalguri Tea Garden area piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000512/2021-2022 | 352/JD | 03/03/2022 | 30/08/2022 | NEW KUNDU ENTERPRISE | 81.56 | 72.38 | 88.74 | 100
8 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | SM/09392 | Augmentation | Shifting of existing pipeline of Khalaigram W/S Scheme between the Khalaigram Khetifullbari P.W.D. Road under Jalpaiguri Division P.H.E. Dte. (PART - A) |  |  | ORD/000633/2020-2021 | 423/JD | 04/06/2020 | 02/09/2020 | LOKNATH CONSTRUCTION | 28.18 | 1.75 | 6.22 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | SM/09392 | Augmentation | Arrangement for disposal of waste water of IEP at H/W site of Paschim Salbari(zone-II) W/S/S under Jalpaiguri Division , P.H.E. Dte. |  |  | ORD/000284/2022-2023 | 649/RWS | 21/10/2022 | 10/11/2022 | PARAMJYOTI ENTERPRISE | 4.32 | 4.32 | 99.8 | 1
10 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | SM/09392 | Augmentation | New Service Connection Charge for KATHALGURI T.G (REJU) W/S Scheme, T/W No. I, under BANARHAT CCC [APPLICATION NO. 4003103082 ; Reference ID : 402976414] |  |  | BILL/00805/2022-2023 | BP/22-23/169 | 29/03/2023 | 29/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | SM/09392 | Augmentation | New Service Connection Charge for KATHALGURI TG,T/W II, under BANARHAT CCC [APPLICATION NO. 4003103099 ; Reference ID : 402976404] |  |  | BILL/00801/2022-2023 | BP/22-23/169 | 29/03/2023 | 29/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
12 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | SM/09392 | Augmentation | Infrastructure Cost for KATHALGURI TG,T/W II, under BANARHAT CCC [APPLICATION NO. 100000073456 ; Reference ID : 860265206] |  |  | BILL/00802/2022-2023 | BP/22-23/169 | 29/03/2023 | 29/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.11 | 0 | 0 | 0
13 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | SM/09392 | Augmentation | Infrastructure Cost for KATHALGURI T.G (REJU) W/S Scheme, T/W No. I, under BANARHAT CCC [APPLICATION NO.100000074460 ; Reference ID : 860265550] |  |  | BILL/00806/2022-2023 | BP/22-23/169 | 29/03/2023 | 29/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.72 | 0 | 0 | 0
14 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | SM/09392 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF KATHALGURI TG PWSS, TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Driller-in-Charge | Junior Engineer | ORD/000873/2022-2023 | 337/NMD | 29/03/2023 | 28/04/2023 | SUBODH KUMAR BANIK | 29.9 | 23.93 | 80.03 | 60
15 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | SM/09392 | Augmentation | Construction of Pump House (5.40m x 3.60m) with sanitary & plumbing arrangement including Rising Main & interconnections at Head Work site for Augmentation of Kathalguri Water Supply Scheme at Banarhat Block in connection with Jal Jeevan Mission under Jalpaiguri Division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000604/2023-2024 | 2305/JD | 07/02/2024 | 23/03/2024 | NEW KUNDU ENTERPRISE | 7.39 | 6.62 | 89.65 | 100
16 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | SM/09392 | Augmentation | Construction of Foot Path, Drain including rising main interconnections at HW site of Kathalguri PWSS in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000813/2023-2024 | 2634/JD | 07/03/2024 | 28/03/2024 | NEW KUNDU ENTERPRISE | 13.52 | 8.51 | 62.91 | 100
17 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | SM/09392 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
18 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | SM/09392 | Augmentation | Sinking of five nos Tube Well by Odex- 165 method of drilling at different Tube Well site in connection with jal jeevan mission under Augmentation/Rejuvenation of Kathalguri TG PWSS (Two Nos), Devpara TG PWSS (One No), Banarhat Bazar PWSS (One No), Sajna Para PWSS (One No) under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000374/2023-2024 | 1520/JD | 16/10/2023 | 30/04/2025 | ROY ENGINEERS | 41.28 | 13.47 | 32.62 | 100
19 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | SM/09392 | Augmentation | Laying of Distribution Line, Along with Rising Main Connection between Head works pump House site and Additional tube well site including common manifold with balanced Functional Household Tap Connection (Phase -IV) in connection with Jal Jeevan Mission under Rejuvenation of Kathalguri T.G. Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000429/2022-2023 | 630/JD | 13/03/2023 | 02/07/2026 | J.M. CONSTRUCTION | 46.3 | 0 | 0 | 90
Total | [13 empty] | 839.03 | 143.87 | 17.15