## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Kajaldighi piped water supply scheme. | SM/09457 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of KAJALDIGHI PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000839/2022-2023 | 268/NMD | 21/03/2023 | 20/04/2023 | INDTECH ASSOCIATES | 21.38 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kajaldighi piped water supply scheme. | SM/09457 | Augmentation | Sinking of 250mm x 150mm dia Two nos tube well by Reverse Rotary method of drilling for Augmentation at 3rd & 4th Tube well site of Kajaldighi PWSS within Maynaguri Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 850/JD | 06/04/2023 | 21/05/2023 | M/S S. G. ENTERPRISE | 16.86 | 15.78 | 93.62 | 100
3 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Kajaldighi piped water supply scheme. | SM/09457 | Augmentation | New Service Connection Charge for KAJALDHIGHI MAYNAGURI, T/W IV, under MAYNAGURI CCC, [APPLICATION NO. 4003164175, Reference ID : 403024433] |  |  | BILL/00578/2023-2024 | BP/23-24/69 | 09/08/2023 | 09/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Kajaldighi piped water supply scheme. | SM/09457 | Augmentation | Infrastructure Cost for KAJALDHIGHI MAYNAGURI, T/W III, under MAYNAGURI CCC, [APPLICATION NO. 100000084435, Reference ID : 860276015] |  |  | BILL/00573/2023-2024 | BP/23-24/69 | 09/08/2023 | 09/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.17 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Kajaldighi piped water supply scheme. | SM/09457 | Augmentation | Infrastructure Cost for KAJALDHIGHI MAYNAGURI, T/W IV, under MAYNAGURI CCC, [APPLICATION NO. 100000084436, Reference ID : 860276016] |  |  | BILL/00579/2023-2024 | BP/23-24/69 | 09/08/2023 | 09/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.27 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Kajaldighi piped water supply scheme. | SM/09457 | Augmentation | New Service Connection Charge for KAJALDHIGHI MAYNAGURI, T/W III, under MAYNAGURI CCC, [APPLICATION NO. 4003164171, Reference ID : 403024432] |  |  | BILL/00572/2023-2024 | BP/23-24/69 | 09/08/2023 | 09/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kajaldighi piped water supply scheme. | SM/09457 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th tube well site of Rejuvenation of Kajaldighi water supply scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000145/2022-2023 | 1562/JD | 08/08/2022 | 01/03/2025 | DEBASISH DEY | 13.78 | 10.4 | 75.51 | 80
8 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kajaldighi piped water supply scheme. | SM/09457 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 4th Tube well site of Rejuvenation of Kajaldighi Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000482/2021-2022 | 2215/JD | 27/12/2021 | 25/02/2022 | M/S TRINATH CONSTRUCTION AND CO. | 11.44 | 11.43 | 99.92 | 100
9 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kajaldighi piped water supply scheme. | SM/09457 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 3rd Tube well site of Rejuvenation of Kajaldighi Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000481/2021-2022 | 2214/JD | 27/12/2021 | 25/02/2022 | SUBIR GHOSH | 11.45 | 11.44 | 99.89 | 100
10 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Kajaldighi piped water supply scheme. | SM/09457 | Augmentation | Supply and Delivery of C.I special as when as required at T/W No-I of KAJALDIGI and other adjacent W/S Scheme under in the Dist. of JALPAIGURI. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000071/2024-2025 | 1060/HQ/NMD | 21/06/2024 | 28/06/2024 | SARKAR ELECTRIC | 0.75 | 0.75 | 100 | 100
11 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kajaldighi piped water supply scheme. | SM/09457 | Augmentation | Construction of approach Road for 3rd & 4th site for Kajaldighi Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000098/2025-2026 | 477/RWS | 29/05/2025 | 28/06/2025 | M/S S. G. ENTERPRISE | 0.5 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kajaldighi piped water supply scheme. | SM/09457 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site of Rejuvenation of Kajaldighi water supply scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000199/2022-2023 | 1740/JD | 08/09/2022 | 01/06/2025 | SAHA CONSTRUCTION | 14.44 | 10.87 | 75.25 | 100
Total | [13 empty] | 96.41 | 60.68 | 62.93