## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Charerbari piped water supply scheme. | SM/09458 | Augmentation | Sinking of 2 No. 250 mm x 150 mm x 132 m deep Rig Bored Tube Well by Reverse Rotary method of drilling for Rejuvenation of Charerbari Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000730/2021-2022 | 634/JD | 07/03/2022 | 06/04/2022 | MECHANO TRADING CO. | 15.51 | 12.5 | 80.63 | 1
2 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Charerbari piped water supply scheme. | SM/09458 | Augmentation | New Service Connection Charge for TW-IV of CHARERBARI W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 4002941281 , Reference ID : 402831979] |  |  | VCH/000333/2022-2023 | RTGS 01 | 07/07/2022 | 07/07/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Charerbari piped water supply scheme. | SM/09458 | Augmentation | Infrastructure cost for New Service Connection Charge for TW-IV of CHARERBARI W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000053963 ; Reference ID : 860243613] |  |  | VCH/000334/2022-2023 | RTGS 01 | 07/07/2022 | 07/07/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.92 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Charerbari piped water supply scheme. | SM/09458 | Augmentation | New Service Connection Charge for TW-III of CHARERBARI W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 4002941279 ; Reference ID : 402831974] |  |  | VCH/000335/2022-2023 | RTGS 01 | 07/07/2022 | 07/07/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Charerbari piped water supply scheme. | SM/09458 | Augmentation | Infrastructure cost for New Service Connection Charge for TW-III of CHARERBARI W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000053962 ; Reference ID : 860243612] |  |  | VCH/000336/2022-2023 | RTGS 01 | 07/07/2022 | 07/07/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.21 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Charerbari piped water supply scheme. | SM/09458 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for CHARERBARI PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000120/2022-2023 | 857/NMD | 18/07/2022 | 17/08/2022 | DAWA DUKPA | 7.87 | 0 | 0 | 80
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Charerbari piped water supply scheme. | SM/09458 | Augmentation | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of Charerbari Piped W/S Scheme at T/W No. III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000100/2022-2023 | 568/NMD | 14/07/2022 | 04/08/2022 | SUNLIT | 2.16 | 2.16 | 100 | 50
8 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Charerbari piped water supply scheme. | SM/09458 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th tube well site of Rejuvenation of Charerbari water supply scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000144/2022-2023 | 1578/JD | 12/08/2022 | 26/09/2022 | NEW KUNDU ENTERPRISE | 14.43 | 13.22 | 91.63 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Charerbari piped water supply scheme. | SM/09458 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site of Rejuvenation of Charerbari water supply scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000150/2022-2023 | 1563/JD | 10/08/2022 | 24/09/2022 | A.P CONSTRUCTION | 14.45 | 13.19 | 91.24 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Charerbari piped water supply scheme. | SM/09458 | Augmentation | Minor Repairing work for OHR, Pump Houses, Boundary walls, Blower Room, IEP etc. for Charerbari Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000400/2022-2023 | 605/JD | 09/03/2023 | 24/03/2023 | M/S DEY & ROY CHOUDHURY | 3.69 | 0 | 0 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Charerbari piped water supply scheme. | SM/09458 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 4th Tube well site of Rejuvenation of Charerbari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000480/2021-2022 | 2213/JD | 27/12/2021 | 25/02/2022 | JAYA SARKAR | 11.42 | 11.38 | 99.62 | 1
12 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Charerbari piped water supply scheme. | SM/09458 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 3rd tube well site of Rejuvenation of Charerbari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000479/2021-2022 | 2212/JD | 27/12/2021 | 25/02/2022 | M/S DEY & ROY CHOUDHURY | 11.44 | 11.38 | 99.45 | 1
13 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Charerbari piped water supply scheme. | SM/09458 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for CHARERBARI PWSS, at TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000121/2022-2023 | 858/NMD | 18/07/2022 | 17/08/2022 | SUBHRANGSHU GUHARAJA | 7.87 | 7.87 | 100 | 0
14 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Charerbari piped water supply scheme. | SM/09458 | Augmentation | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of Charerbari Piped W/S Scheme at T/W No. IV in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000102/2022-2023 | 569/NMD | 14/07/2022 | 04/08/2022 | SUDIP DUTTA | 2.16 | 2.16 | 100 | 0
15 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Charerbari piped water supply scheme. | SM/09458 | Augmentation | Interconnection with Delivery Line of Tube Well ( 3rd and 4th ) to Distribution Pipeline & Backwash line at Charerbari Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000288/2022-2023 | 2012/JD | 01/11/2022 | 16/11/2022 | M/S DEY & ROY CHOUDHURY | 3.7 | 3.1 | 83.95 | 1
16 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Charerbari piped water supply scheme. | SM/09458 | Augmentation | Construction of Approach road by Paver Block inside the Reservior Compound at Charerbari Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000402/2022-2023 | 603/JD | 09/03/2023 | 24/03/2023 | M/S DEY & ROY CHOUDHURY | 3.92 | 3.84 | 98.13 | 100
17 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Charerbari piped water supply scheme. | SM/09458 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000083/2023-2024 | 1059/JD | 24/08/2023 | 24/08/2023 | Resource Division | 3.24 | 0 | 0 | 0
18 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Charerbari piped water supply scheme. | SM/09458 | Augmentation | Drainage arrangement for back wash water from Iron Elemation Plant at 3rd & 4th tube well site of Charerbari Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000033/2023-2024 | 387/RWS | 25/04/2023 | 09/05/2023 | PRITAM DUTTA | 2.73 | 2.73 | 100 | 100
Total | [13 empty] | 114.07 | 83.53 | 73.23