## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Basilardanga piped water supply scheme. | SM/09460 | Augmentation | Sinking of 2 No. 250 mm x 150 mm x 132 m deep Rig Bored Tube Well by Reverse Rotary method of drilling for Rejuvenation of Basilardanga Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000731/2021-2022 | 642/JD | 08/03/2022 | 07/04/2022 | MECHANO TRADING CO. | 15.51 | 12.87 | 83 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Basilardanga piped water supply scheme. | SM/09460 | Augmentation | Interconnection with Delivery Line of Tube Well ( 3rd and 4th ) to Distribution Pipeline & Backwash line at Basilardanga Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000274/2022-2023 | 2011/JD | 01/11/2022 | 16/11/2022 | SANKAR DAS | 6.64 | 4.9 | 73.78 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Basilardanga piped water supply scheme. | SM/09460 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 3rd Tube well site of Rejuvenation of Basilardanga Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000485/2021-2022 | 2218/JD | 27/12/2021 | 25/02/2022 | M/S DEY & ROY CHOUDHURY | 11.44 | 11.43 | 99.89 | 1
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. | SM/09460 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for BASILARDANGA PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000113/2022-2023 | 850/NMD | 18/07/2022 | 17/08/2022 | S.P. ENTERPRISE | 7.74 | 7.74 | 100 | 0
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. | SM/09460 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for BASILARDANGA PWSS, at TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000114/2022-2023 | 851/NMD | 18/07/2022 | 17/08/2022 | M/S ANJALI ENTERPRISE | 7.6 | 7.6 | 100 | 0
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. | SM/09460 | Augmentation | Supply, delivery & installation of 10KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of Basilardanga Piped W/S Scheme at T/W No. III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000103/2022-2023 | 570/NMD | 14/07/2022 | 04/08/2022 | GURUKRIPA ENTERPRISE | 1.87 | 1.87 | 100 | 0
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. | SM/09460 | Augmentation | Supply, delivery & installation of 10KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of Basilardanga Piped W/S Scheme at T/W No. IV in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000104/2022-2023 | 571/NMD | 14/07/2022 | 04/08/2022 | HARAGOURI ENTERPRISE | 1.87 | 1.87 | 100 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Basilardanga piped water supply scheme. | SM/09460 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 4th Tube well site of Rejuvenation of Basilardanga Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000473/2021-2022 | 2219/JD | 27/12/2021 | 25/02/2022 | PARESH CHANDRA ROY | 11.45 | 11.44 | 99.93 | 1
9 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. | SM/09460 | Augmentation | Infrastructure cost for New Service Connection Charge for TW-III of BASILARDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000053960 ; Reference ID : 860243610] |  |  | VCH/000338/2022-2023 | RTGS 01 | 07/07/2022 | 07/07/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.06 | 0 | 0 | 0
10 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. | SM/09460 | Augmentation | Infrastructure cost for New Service Connection Charge for TW-IV of BASILARDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000053938 ; Reference ID : 860243608] |  |  | VCH/000340/2022-2023 | RTGS 01 | 07/07/2022 | 07/07/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.92 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. | SM/09460 | Augmentation | New Service Connection Charge for TW-III of BASILARDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 4002941265 ; Reference ID : 402831972] |  |  | VCH/000337/2022-2023 | RTGS 01 | 07/07/2022 | 07/07/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
12 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. | SM/09460 | Augmentation | Infrastructure cost for New Service Connection Charge for TW-III, of BASILARDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000057050 , Reference ID : 860246650] |  |  | VCH/000774/2022-2023 | BP/2022-23/30 | 16/08/2022 | 16/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.57 | 0 | 0 | 0
13 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. | SM/09460 | Augmentation | New Service Connection Charge for TW-IV of BASILARDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 4002941268 ; Reference ID : 402831980] |  |  | VCH/000339/2022-2023 | RTGS 01 | 07/07/2022 | 07/07/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
14 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Basilardanga piped water supply scheme. | SM/09460 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain etc. at 3rd tube well site of Rejuvenation of Basilardanga water supply scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000140/2022-2023 | 1603/JD | 18/08/2022 | 02/10/2022 | SANDIP BANIK | 13.65 | 12.43 | 91.08 | 0
15 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. | SM/09460 | Augmentation | Hiring of Maxi Cab vehicle (Non-Airconditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000725/2023-2024 | 146/HQ/NMD | 31/07/2023 | 31/10/2023 | UTTAM PAUL | 0.95 | 0 | 0 | 0
16 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Basilardanga piped water supply scheme. | SM/09460 | Augmentation | Reparing on OHR , pump house , IEP Room , boundary wall , construction of pathway , & other ancillary works for Basilardanga piped W/S/S under Jalpaiguri Division , P.H.E. Dte |  |  | ORD/000588/2021-2022 | 178/RWS | 03/03/2022 | 02/04/2022 | PARESH CHANDRA GUHA | 4.85 | 4.02 | 82.84 | 0
17 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Basilardanga piped water supply scheme. | SM/09460 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th tube well site of Rejuvenation of Basilardanga water supply scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000294/2022-2023 | 2067/JD | 04/11/2022 | 19/12/2022 | R.S CONSTRUCTION | 13.65 | 13.6 | 99.63 | 100
18 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Basilardanga piped water supply scheme. | SM/09460 | Augmentation | Providing FHTC and Retrofitting works in connection with FHTC works under JJM at Binnaguri colony, Nirendarpur, Tekatuli of Basilardanga W/S/S under Jalpaiguri Division, P.H.E.Dte. Block-Maynaguri, District - Jalpaiguri.(Part-D) |  | Junior Engineer | ORD/000432/2022-2023 | 631/JD | 13/03/2023 | 27/04/2023 | PARESH CHANDRA GUHA | 40.48 | 1.67 | 4.13 | 100
19 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Basilardanga piped water supply scheme. | SM/09460 | Augmentation | Retrofitting works & other ancillary works related to FHTC at different places of Basilardanga PWSS under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000383/2022-2023 | 368/JD | 20/02/2023 | 07/03/2023 | DIPAK KUMAR CHAKRABORTY | 1.81 | 1.81 | 99.77 | 0
20 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. | SM/09460 | Augmentation | Hiring of Maxi Cab vehicle (Non-Airconditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000042/2023-2024 | 21/HQ/NMD | 20/04/2023 | 20/07/2023 | UTTAM PAUL | 0.95 | 0.85 | 89.4 | 100
Total | [13 empty] | 151.37 | 94.09 | 62.16