## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Boalmari piped water supply scheme. | SM/09462 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Boalmari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000301/2021-2022 | 42/JD | 04/01/2022 | 05/03/2022 | NARESH SEN | 11.16 | 10.95 | 98.08 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Boalmari piped water supply scheme. | SM/09462 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Boalmari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000300/2021-2022 | 73/JD | 06/01/2022 | 07/03/2022 | NARESH SEN | 11.21 | 11.2 | 99.86 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Boalmari piped water supply scheme. | SM/09462 | Augmentation | Maintenance O.H.R.Boundary walls and pump house for rejuvenation of Boalmari W/S/S under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000694/2021-2022 | 212/RWS | 11/03/2022 | 10/04/2022 | NARAYAN CHAKRABORTY | 4.8 | 4.91 | 102.23 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Boalmari piped water supply scheme. | SM/09462 | Augmentation | Sinking of 2 No. 300 mm x 200 mm x 123 m deep Rig Bored tubewell by Reverse Rotary method of drilling for Augmentation of Boalmari Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000062/2022-2023 | 1231/JD | 02/06/2022 | 02/07/2022 | JAYANTA GHOSH | 17.43 | 16.72 | 95.96 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Boalmari piped water supply scheme. | SM/09462 | Augmentation | Supply, Installation, Commissioning (Trial run for 3 months) including testing of 2Nos. 15.00 cum per hour capacity pressure type IEP with accessories including construction of Blower Rooms (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd & 4th tube well site for Rejuvenation of Boalmari water supply scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000428/2022-2023 | 624/JD | 13/03/2023 | 27/04/2023 | KANAI LAL SEN | 33.83 | 30.02 | 88.72 | 100
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Boalmari piped water supply scheme. | SM/09462 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF BOALMARI PWSS, TW no III AND IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000872/2022-2023 | 336/NMD | 29/03/2023 | 28/04/2023 | DEY ENTERPRISE(MALDA) | 20.32 | 20.29 | 99.88 | 100
7 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Boalmari piped water supply scheme. | SM/09462 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000050/2023-2024 | 1101/JD | 24/08/2023 | 24/08/2023 | Resource Division | 3.45 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Boalmari piped water supply scheme. | SM/09462 | Augmentation | New Service Connection Charge for BOALMARI (REJU) W/S Scheme, T/W No. IV, under PANDAPARA CCC, [APPLICATION NO. 4003078086, Reference ID : 402978692] |  |  | BILL/00779/2022-2023 | BP/22-23/167 | 28/03/2023 | 28/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Boalmari piped water supply scheme. | SM/09462 | Augmentation | Infrastructure Cost for BOALMARI, T/W No - III W/S Scheme, under HALDIBARI CCC |  |  | BILL/00711/2022-2023 | BP/23-24/02 | 18/04/2023 | 18/04/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.15 | 0 | 0 | 0
10 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Boalmari piped water supply scheme. | SM/09462 | Augmentation | New Service Connection Charge for BOALMARI, T/W No - III W/S Scheme, under HALDIBARI CCC |  |  | BILL/00709/2022-2023 | BP/23-24/02 | 18/04/2023 | 18/04/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Boalmari piped water supply scheme. | SM/09462 | Augmentation | Infrastructure Cost for BOALMARI (REJU) W/S Scheme, T/W No. IV, under PANDAPARA CCC, [APPLICATION NO.100000073857, Reference ID : 860264957] |  |  | BILL/00780/2022-2023 | BP/22-23/167 | 28/03/2023 | 28/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.92 | 0 | 0 | 0
Total | [13 empty] | 112.69 | 94.09 | 83.5