## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Madhya Khutttimari Piped Water Supply Scheme | SM/09483 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Madhya Khattiamri P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000501/2021-2022 | 96/JD | 10/01/2022 | 11/03/2022 | ALICK DUTTA | 4.65 | 4.75 | 102.12 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Madhya Khutttimari Piped Water Supply Scheme | SM/09483 | Augmentation | Sinking of 250mm x 150mm dia tube well by Reverse Rotary method of drilling for Rejuvenation of Madhya Khattimari PWSS at Dhupguri Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000449/2021-2022 | 197/JD | 21/01/2022 | 20/02/2022 | UNIBRO INFRASERV PRIVATE LIMITED | 8.02 | 7.1 | 88.61 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Madhya Khutttimari Piped Water Supply Scheme | SM/09483 | Augmentation | Laying Rising Main at 3rd Tubewell site of Madhya Khuttimari PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000061/2023-2024 | 325/JD | 18/05/2023 | 01/06/2023 | CHOWDHURY CONSTRUCTION | 4.63 | 3.34 | 72.1 | 10
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Madhya Khutttimari Piped Water Supply Scheme | SM/09483 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF MADHYA KHUTTIMARI PWSS, TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000892/2022-2023 | 391/NMD | 29/03/2023 | 28/04/2023 | M/S DILIP MITRA | 11.07 | 11.07 | 100 | 100
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Madhya Khutttimari Piped Water Supply Scheme | SM/09483 | Augmentation | New Service Connection Charge for Rejuvenation of Madhya Khutttimari, T/W III, under DHUPGURI CCC, [APPLICATION NO. 4003123382, Reference ID : 402998142] |  |  | BILL/00027/2023-2024 | BP/23-24/09 | 16/05/2023 | 16/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Madhya Khutttimari Piped Water Supply Scheme | SM/09483 | Augmentation | Infrastructure Cost for Rejuvenation of Madhya Khutttimari, T/W III, under DHUPGURI CCC, [APPLICATION NO. 100000076479, Reference ID : 860267199] |  |  | BILL/00028/2023-2024 | BP/23-24/09 | 16/05/2023 | 16/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.22 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Madhya Khutttimari Piped Water Supply Scheme | SM/09483 | Augmentation | Laying of higher dia. pipeline within the Command Area of Madhya Khuttimary and adjoining mouzas Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000237/2025-2026 | 2163/JD | 30/10/2025 | 13/01/2026 | BILTU DAS | 152.02 | 0 | 0 | 0
Total | [13 empty] | 184 | 26.27 | 14.28