## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/09484 | Augmentation | Sinking of 1 No. 250mm x 150mm x 135 m deep Rig Bored tube well by Reverse Rotary method of drilling for Rejuvenation of Chauhaddi Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000476/2021-2022 | 348/JD | 03/02/2022 | 05/03/2022 | J.M. CONSTRUCTION | 7.85 | 0 | 0 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/09484 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Chauhaddi P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000507/2021-2022 | 106/JD | 11/01/2022 | 12/03/2022 | J.M. CONSTRUCTION | 4.65 | 0 | 0 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/09484 | Augmentation | Repairing of damaged line near Harinkhwa School with other ancillary repairing work related to the Laying Distribution System at Chauhaddi P.W.S.S. under Jalpaiguri Division, | Assistant Engineer,HQ | Junior Engineer | ORD/000580/2021-2022 | 166/JD | 20/01/2022 | 10/02/2022 | HARIPADA BANERJEE | 3.68 | 0 | 0 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/09484 | Augmentation | FUEL BILL |  |  | VCH/000281/2022-2023 | BP-2022-23-137 | 25/08/2022 | 25/08/2022 | FILL & SMILE | 0.74 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/09484 | Augmentation | BOUNDARY WALL 2ND T/WELL SITE RED BANK T.G |  |  | VCH/001308/2021-2022 | BP-2021-22- 459 | 27/03/2022 | 27/03/2022 | DEEP CONSTRUCTION | 3.58 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/09484 | Augmentation | Repairing of choakaged and damaged branch lines due to road development and widening of near by area of Garialtari within the command area of Chauhaddi and adjoining mouzas Piped Water Supply Scheme under Jalpaiguri Division. P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000163/2022-2023 | 1435/JD | 18/07/2022 | 08/08/2022 | HARIPADA BANERJEE | 4.84 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/09484 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) | Assistant Engineer | Junior Engineer | ORD/000359/2022-2023 | 1415/JD | 14/07/2022 | 14/07/2023 | APIKUL ALI | 1.76 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/09484 | Augmentation | Providing Functional Household Tap Connection (Phase - VI) in connection with Jal Jeevan Mission for Rejuvenation of Chouhaddi and adjoining Mouzas P.W.S.S under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000431/2022-2023 | 626/JD | 13/03/2023 | 12/04/2023 | SOMNATH ROY | 17.57 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/09484 | Augmentation | Retrofitting works in connection with Rejuvination of Chauhaddi PWSS for FHTC work of Jal Swapna at Dhupguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000015/2022-2023 | 971/JD | 20/04/2022 | 19/07/2022 | SCEC BOENTER KDAS JOINT VENTURE | 168.05 | 0 | 0 | 1
10 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/09484 | Augmentation | Construction of Pathway inside the Head Works Site of Chauhaddi and adjoining mouzas .P.W.S.S. under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000161/2022-2023 | 1468/JD | 25/07/2022 | 15/08/2022 | HARIPADA BANERJEE | 3.53 | 0 | 0 | 100
11 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/09484 | Augmentation | Continuation Order for the work "Supply of 1 (one) Maxi Cab with engine capacity more than 2000 C.C. on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi permit) from 01.01.2023 to 31.03.2023 |  |  | ORD/000597/2022-2023 | 348/JSSD | 27/12/2022 | 27/03/2023 | TANMOY CHOUDHURY | 0.45 | 0 | 0 | 0
12 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/09484 | Augmentation | New Service Connection Charge for CARITALTARI,CHUHADDI W/S Scheme, T/W No. III, under DHUPGURI CCC, [APPLICATION NO. 4003018642, Reference ID : 402927988] |  |  | BILL/00032/2022-2023 | BP/22-23/129 | 20/01/2023 | 20/01/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
13 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/09484 | Augmentation | Infrastructure Cost for CARITALTARI,CHUHADDI W/S Scheme, T/W No. III, under DHUPGURI CCC, [APPLICATION NO.100000066801, Reference ID : 860257021] |  |  | BILL/00033/2022-2023 | BP/22-23/129 | 20/01/2023 | 20/01/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.81 | 0 | 0 | 0
14 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/09484 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for CHAUHADDI (REJU) PWSS, at TW no. III, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000581/2022-2023 | 1122/NMD | 12/09/2022 | 12/10/2022 | SUMON ELECTRICAL | 8.14 | 0 | 0 | 100
15 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/09484 | Augmentation | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under CHAUHADDI (Reju) WS Scheme at TW No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Driller-in-Charge | Junior Engineer | ORD/000781/2022-2023 | 102/NMD | 03/02/2023 | 24/02/2023 | SUMON ELECTRICAL | 2.94 | 0 | 0 | 100
16 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/09484 | Augmentation | Fuel,lubricant charges for Government Inspection vehicle under NMD ,PHE,DTE Invoice No :0091/2023-2024 ,Dt - 29/02/24 |  |  | BILL/01052/2024-2025 | BP/24-25/199 | 12/09/2024 | 12/09/2024 | M/S MILLENNIUM FUEL CENTRE | 0.41 | 0 | 0 | 0
17 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/09484 | Augmentation | Fuel,lubricant charges for Government Inspection vehicle under NMD ,PHE,DTE Invoice No :0092/2023-2024 ,Dt - 31/03/24 |  |  | BILL/01053/2024-2025 | BP/24-25/199 | 12/09/2024 | 12/09/2024 | M/S MILLENNIUM FUEL CENTRE | 0.34 | 0 | 0 | 0
Total | [13 empty] | 233.73 | 0 | 0