## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mallicksova Piped water Supply Scheme | SM/09485 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jalswapna of Khathiar line, Girza line and Chamru line within the command area of Jogesh Ch. T.G. PWSS at Mal Block under Jalpaiguri Division, P.H.E. Dte. (Part-C) | Assistant Engineer | Junior Engineer | ORD/000573/2021-2022 | 730/JD | 17/03/2022 | 07/04/2022 | SANDIP BANIK | 17.59 | 16.99 | 96.55 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mallicksova Piped water Supply Scheme | SM/09485 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 4th Tube well site for Mallicksova P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000510/2021-2022 | 93/JD | 10/01/2022 | 11/03/2022 | TECHNO CRACY | 4.65 | 4.69 | 100.91 | 100
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mallicksova Piped water Supply Scheme | SM/09485 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 5th Tube well site for Mallicksova P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000511/2021-2022 | 94/JD | 10/01/2022 | 11/03/2022 | DEBABRATA SARKAR | 4.64 | 4.73 | 101.82 | 100
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mallicksova Piped water Supply Scheme | SM/09485 | Augmentation | Sinking of 250 mm x 150mm dia 3rd tube well by Reverse Rotary method of drilling for Rejuvenation of Mallicksova PWSS at Dhupguri Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000031/2022-2023 | 977/JD | 20/04/2022 | 20/05/2022 | UNIBRO INFRASERV PRIVATE LIMITED | 7.95 | 7.45 | 93.72 | 1
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mallicksova Piped water Supply Scheme | SM/09485 | Augmentation | Sinking of 250 mm x 150mm dia 4th tube well by Reverse Rotary method of drilling for Rejuvenation of Mallicksova PWSS at Dhupguri Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000032/2022-2023 | 985/JD | 21/04/2022 | 21/05/2022 | UNIBRO INFRASERV PRIVATE LIMITED | 7.95 | 7.14 | 89.84 | 1
6 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mallicksova Piped water Supply Scheme | SM/09485 | Augmentation | Sinking of 2 Nos. 183 mm x 125mm dia 120 m Deep tube well by ODEX-165 method of drilling at Chilaoni TG area Piped Water Supply Scheme under PHE Dte. Jalpaiguri Division. | Assistant Engineer | Junior Engineer | ORD/000075/2022-2023 | 1314/JD | 16/06/2022 | 16/07/2022 | S. N. POLYMERS PVT. LTD. | 13.84 | 11.69 | 84.5 | 1
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme | SM/09485 | Augmentation | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under MALLICKSOBHA (Reju) WS Scheme at TW No. V in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000780/2022-2023 | 101/NMD | 03/02/2023 | 24/02/2023 | BLUE PINE | 2.91 | 2.91 | 100 | 100
8 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme | SM/09485 | Augmentation | New Service Connection Charge for MALLIK SOBHA, TW No. V, DHUPGURI CCC, [APPLICATION NO. 4003123385, Reference ID : 402994381] |  |  | BILL/00059/2023-2024 | BP/23-24/16 | 24/05/2023 | 24/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme | SM/09485 | Augmentation | Infrastructure Cost for MALLIK SOBHA, TW No. V, DHUPGURI CCC, [APPLICATION NO. 100000076675, Reference ID : 860268405] |  |  | BILL/00060/2023-2024 | BP/23-24/16 | 24/05/2023 | 24/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.21 | 0 | 0 | 0
10 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme | SM/09485 | Augmentation | Infrastructure Cost for MALLICK SOVA, T/W IV, under DHUPGURI CCC [APPLICATION NO. 100000076670 , Reference ID : 860268400] |  |  | BILL/00249/2023-2024 | BP/23-24/27 | 09/06/2023 | 09/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.41 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme | SM/09485 | Augmentation | New Service Connection Charge for MALLICK SOVA, T/W IV, under DHUPGURI CCC, [APPLICATION NO. 4003123372, Reference ID : 402997124] |  |  | BILL/00505/2023-2024 | BP/23-24/55 | 14/07/2023 | 14/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
12 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme | SM/09485 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for MALLICKSOBHA (REJU) PWSS, at TW no. V, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000575/2022-2023 | 1127/NMD | 12/09/2022 | 12/10/2022 | BLUE PINE | 8.26 | 8.23 | 99.69 | 100
13 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme | SM/09485 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for MALLICKSOBHA (REJU) PWSS, at TW no. IV, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000577/2022-2023 | 1126/NMD | 12/09/2022 | 12/10/2022 | DAS CONSTRUCTION | 8.25 | 8.22 | 99.61 | 91
14 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme | SM/09485 | Augmentation | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under MALLICKSOBHA (Reju) WS Scheme at TW No. IV in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Driller-in-Charge | Junior Engineer | ORD/000779/2022-2023 | 100/NMD | 03/02/2023 | 24/02/2023 | M/S ROYAL ENTERPRISE | 2.91 | 2.91 | 100 | 100
15 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mallicksova Piped water Supply Scheme | SM/09485 | Augmentation | Laying Rising Main at 5th Tubewell site of Mallicksova PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000024/2023-2024 | 124/JD | 28/04/2023 | 12/05/2023 | PINTU DAS | 5.01 | 1.76 | 35.03 | 100
16 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme | SM/09485 | Augmentation | Fuel,lubricant charges for Government Inspection vehicle under NMD ,PHE,DTE Invoice No :0090/2023-2024 ,Dt - 31/01/2024 |  |  | BILL/01051/2024-2025 | BP/24-25/199 | 12/09/2024 | 12/09/2024 | M/S MILLENNIUM FUEL CENTRE | 0.28 | 0 | 0 | 0
17 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme | SM/09485 | Augmentation | Fuel,lubricants charges for Government Inspection vehicle under NMD ,PHE,DTE Invoice No :0001/2023-2024 ,Dt - 30/04/24 |  |  | BILL/01054/2024-2025 | BP/24-25/199 | 12/09/2024 | 12/09/2024 | M/S MILLENNIUM FUEL CENTRE | 0.29 | 0 | 0 | 0
18 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme | SM/09485 | Augmentation | Fuel charges for Government Inspection vehicle under NMD ,PHE,DTE Invoice No :004/2024-2025 ,Dt - 31/07/2024 |  |  | BILL/01050/2024-2025 | BP/24-25/199 | 12/09/2024 | 12/09/2024 | M/S MILLENNIUM FUEL CENTRE | 0.34 | 0 | 0 | 0
19 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mallicksova Piped water Supply Scheme | SM/09485 | Augmentation | Rejuvenation of 3rd Tube Well Site, 2nd Tube Well Site and Head Work Site Pump House at Mallicksova Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000496/2024-2025 | 2374/JD | 18/12/2024 | 07/01/2025 | SUKUMAR KUNDU | 2.88 | 0 | 0 | 0
20 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme | SM/09485 | Augmentation | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Driller-in-Charge |  | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 25/03/2025 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
21 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mallicksova Piped water Supply Scheme | SM/09485 | Augmentation | Laying Rising Main at 4th Tubewell site of Mallicksova PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000030/2023-2024 | 125/JD | 28/04/2023 | 01/02/2025 | M/S KARMAKAR CONSTRACTION | 6.14 | 0 | 0 | 100
Total | [13 empty] | 106.74 | 76.72 | 71.87