## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Khalaigram Piped Water Supply Scheme | SM/09486 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 3rd tube well site for Khalaigram P.W.S.S. under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000222/2022-2023 | 1851/JD | 16/09/2022 | 31/10/2022 | MANAB BAKSHI | 4.65 | 4.72 | 101.52 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Khalaigram Piped Water Supply Scheme | SM/09486 | Augmentation | Sinking of 250 mm x 150mm dia tube well by Reverse Rotary method of drilling for Rejuvenation of Khalaigram PWSS at Dhupguri Block under PHE Dte. Jalpaiguri Division. |  | Junior Engineer | ORD/000451/2021-2022 | 199/JD | 21/01/2022 | 20/02/2022 | UNIBRO INFRASERV PRIVATE LIMITED | 8.02 | 7.05 | 87.99 | 1
3 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Khalaigram Piped Water Supply Scheme | SM/09486 | Augmentation | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under KHALAIGRAM (Reju) WS Scheme at TW No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000667/2022-2023 | 1400/NMD | 09/12/2022 | 08/01/2023 | S.D. CONCERN | 2.91 | 2.91 | 100 | 100
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Khalaigram Piped Water Supply Scheme | SM/09486 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for KHALAIGRAM (REJU) PWSS, at TW no. III, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000580/2022-2023 | 1123/NMD | 12/09/2022 | 12/10/2022 | S.P. ENTERPRISE (KOLKATA) | 8.13 | 8.13 | 100 | 100
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Khalaigram Piped Water Supply Scheme | SM/09486 | Augmentation | Laying Rising Main at 3rd Tube Well site of Khalaigram PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000023/2023-2024 | 123/JD | 28/04/2023 | 12/05/2023 | PRIYABRATA KARMAKAR | 8.33 | 6.11 | 73.33 | 80
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Khalaigram Piped Water Supply Scheme | SM/09486 | Augmentation | Infrastructure Cost for KHALAIGRAM,DHUBGURU W/S Scheme, T/W No. III, under DHUPGURI CCC, [APPLICATION NO.100000066803, Reference ID : 860257023] |  |  | BILL/00035/2022-2023 | BP/22-23/130 | 20/01/2023 | 20/01/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.24 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Khalaigram Piped Water Supply Scheme | SM/09486 | Augmentation | New Service Connection Charge for KHALAIGRAM,DHUBGURU W/S Scheme, T/W No. III, under DHUPGURI CCC, [APPLICATION NO. 4003018666, Reference ID : 402928492] |  |  | BILL/00034/2022-2023 | BP/22-23/130 | 20/01/2023 | 20/01/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Khalaigram Piped Water Supply Scheme | SM/09486 | Augmentation | ADDITIONAL WORK Infrastructure Cost for KHALAIGRAM, T/W III, under DHUPGURI CCC [APPLICATION NO. 100000090647, Reference ID : 860281557] |  |  | BILL/01118/2023-2024 | BP/23-24/124 | 10/10/2023 | 10/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.64 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Khalaigram Piped Water Supply Scheme | SM/09486 | Augmentation | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Driller-in-Charge |  | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 25/03/2025 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
Total | [13 empty] | 38.77 | 28.93 | 74.62