## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | SM/09487 | Augmentation | Sinking of 300mm x 200mm dia tube well by Reverse Rotary method of drilling for 3rd Tube well for Rejuvenation of Ambari Falakata PWSS at Rajganj Block under PHE Dte. Jalpaiguri Division. |  | Junior Engineer | ORD/000613/2021-2022 | 665/JD | 09/03/2022 | 08/04/2022 | STAR CONSTRUCTION | 9.34 | 0 | 0 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | SM/09487 | Augmentation | Sinking of 300mm x 200mm dia tube well by Reverse Rotary method of drilling for 4th Tube well for Rejuvenation of Ambari Falakata PWSS at Rajganj Block under PHE Dte. Jalpaiguri Division. |  | Junior Engineer | ORD/000614/2021-2022 | 666/JD | 09/03/2022 | 08/04/2022 | BONANZA ENTERPRISE | 9.34 | 0 | 0 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | SM/09487 | Augmentation | Retrofitting works in connection with Functional Household Tap Connection for Sitaguri of Ambari Falakata Water Supply Scheme i.c.w. Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000372/2022-2023 | 297/JD | 10/02/2023 | 24/02/2023 | RAGHU DAS | 2.53 | 0 | 0 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | SM/09487 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2023-2024 | 1103/JD | 24/08/2023 | 24/08/2023 | Resource Division | 2.95 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | SM/09487 | Augmentation | Infrastructure Cost for AMBARI FALAKATA, T/W IV, under FULBARIHAT CCC, [APPLICATION NO. 100000076455, Reference ID : 860267595] |  |  | BILL/00466/2023-2024 |  | 07/06/2023 | 07/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.49 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | SM/09487 | Augmentation | Infrastructure Cost for AMBARI FALAKATA, T/W III, under FULBARIHAT CCC, [APPLICATION NO. 100000076457, Reference ID : 860267597] |  |  | BILL/00467/2023-2024 |  | 07/06/2023 | 07/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.05 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | SM/09487 | Augmentation | New Service Connection Charge for AMBARI FALAKATA, T/W III, under FULBARIHAT CCC [APPLICATION NO. 4003135787 ; Reference ID : 403001372] |  |  | BILL/00014/2023-2024 | BP/23-24/30 | 09/06/2023 | 09/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | SM/09487 | Augmentation | New Service Connection Charge for AMBARI FALAKATA, T/W IV, under FULBARIHAT CCC [APPLICATION NO. 4003135750 ; Reference ID : 403001370] |  |  | BILL/00012/2023-2024 | BP/23-24/30 | 09/06/2023 | 09/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | SM/09487 | Augmentation | Infrastructure Cost for AMBARI FALAKATA, T/W IV, under FULBARIHAT CCC [APPLICATION NO. 100000076455 ; Reference ID : 860267595] |  |  | BILL/00013/2023-2024 | BP/23-24/45 | 04/07/2023 | 04/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.49 | 0 | 0 | 0
10 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | SM/09487 | Augmentation | Infrastructure Cost for AMBARI FALAKATA, T/W III, under FULBARIHAT CCC, [APPLICATION NO. 100000087936, Reference ID : 860279647] |  |  | BILL/01161/2023-2024 | BP/23-24/145 | 06/11/2023 | 06/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.92 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | SM/09487 | Augmentation | Infrastructure Cost for AMBARI FALAKATA, T/W III, under FULBARIHAT CCC [APPLICATION NO. 100000076457 ; Reference ID : 860267597] |  |  | BILL/00015/2023-2024 | BP/23-24/45 | 04/07/2023 | 04/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.05 | 0 | 0 | 0
12 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | SM/09487 | Augmentation | Infrastructure Cost for AMBARI FALAKATA, T/W IV, under FULBARIHAT CCC, [APPLICATION NO. 100000087938, Reference ID : 860279649] |  |  | BILL/01162/2023-2024 | BP/23-24/145 | 06/11/2023 | 06/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.1 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | SM/09487 | Augmentation | Retrofittings works in connection with Functional House Hold Tap connection and 4th Pump House under "JAL JEEVAN MISSION " for Boloram, Bandhurngar ,Vandarigacch of Ambari Falakata Water Supply Scheme under Jalpaiguri Division , P.H.E. Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000443/2022-2023 | 702/JD | 17/03/2023 | 01/05/2023 | SUBIR GHOSH | 52.54 | 0 | 0 | 20
14 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | SM/09487 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF AMBARI FALAKATA PWSS, TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000751/2022-2023 | 51/NMD | 24/01/2023 | 23/02/2023 | BONANZA ENTERPRISE | 11.68 | 0 | 0 | 100
15 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | SM/09487 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF AMBARI FALAKATA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000750/2022-2023 | 50/NMD | 24/01/2023 | 23/02/2023 | SAIKAT SINHA | 11.68 | 0 | 0 | 100
16 | JALPAIGURI |  | Central Drilling | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | SM/09487 | Augmentation | Providing drilling crews for construction of Tube Well (250mmX150mmX 127 Mtrs depth) by Utilizing Departmental Machineries for Ambari Falakata W/S Scheme (T/W-II ), Rajganj Block under Jalpaiguri District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000503/2022-2023 | 1777/CDD | 02/01/2023 | 27/03/2024 | PADMA ENGINEERING & CO. | 12.19 | 0 | 0 | 100
17 | JALPAIGURI |  | Central Drilling | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | SM/09487 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Ambari Falakata W/S Scheme (T/W-I ), Rajganj Block under Jalpaiguri District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000160/2023-2024 | 1343/CDD | 13/09/2023 | 11/03/2024 | PADMA ENGINEERING & CO. | 16.67 | 0 | 0 | 100
18 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | SM/09487 | Augmentation | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 3rd tubewell site at Ambari Falakata piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000616/2023-2024 | 2313/JD | 07/02/2024 | 08/03/2024 | SOUVIK SAHA | 8.28 | 0 | 0 | 100
19 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | SM/09487 | Augmentation | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 4th tubewell site at Ambari Falakata piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000617/2023-2024 | 2314/JD | 07/02/2024 | 08/03/2024 | ARUP SARKAR | 8.34 | 0 | 0 | 100
20 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | SM/09487 | Augmentation | Construction of boundary wall with gate,drain and pathway including laying pipe line for 5th tubewell at Amabari Falakata piped water supply scheme under Jalpaiguri Division, P.H.E. Dte i.c.w. JJM . | Assistant Engineer,HQ |  | ORD/000511/2024-2025 | 1214 | 24/12/2024 | 23/01/2025 | KANAI LAL SEN | 0 | 0 | NAN | 0
21 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | SM/09487 | Augmentation | Providing Functional Household Tap Connection (FHTC) in Connection with Jal Jeevan Mission under the command area of Ambari Falakata Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000006/2024-2025 | 472/JD | 20/06/2024 | 10/07/2024 | SUBIR GHOSH | 63.03 | 0 | 0 | 0
Total | [13 empty] | 225.14 | 0 | 0