## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. | SM/09518 | Augmentation | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under ARJI MARIA KAMALA PUKHARI W/S Scheme at T/W No. I in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000007/2022-2023 | 210/NMD | 04/04/2022 | 25/04/2022 | SAIKAT SINHA | 1.92 | 0 | 0 | 0
2 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. | SM/09518 | Augmentation | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT ARAJI MARIA KAMALA PUKHARI (REJU) W/S SCHEME, T/W No. IV, under PANDAPARA CCC, [APPLICATION NO. 10000057368, Reference ID :860239578] |  |  | VCH/000849/2022-2023 | BP/22-23/45 | 08/09/2022 | 08/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.45 | 0 | 0 | 0
3 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. | SM/09518 | Augmentation | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT ARAJI MARIA KAMALA PUKHARI (REJU) W/S SCHEME, T/W No. III, under PANDAPARA CCC, [APPLICATION NO. 10000057368, Reference ID :860239578] |  |  | VCH/000847/2022-2023 | BP/22-23/45 | 08/09/2022 | 08/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.48 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. | SM/09518 | Augmentation | New Service Connection Charge for ARAJI MARIA KAMALA PUKHARI (REJU) W/S SCHEME, T/W No. IV, under PANDAPARA CCC, [APPLICATION NO. 4002964712, Reference ID : 402852793] |  |  | VCH/000848/2022-2023 | BP/22-23/45 | 08/09/2022 | 08/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. | SM/09518 | Augmentation | REJ. ARAJIMARIA KAMLA PUKARI PWSS |  |  | VCH/000912/2021-2022 | BP-2021-22-137 | 14/12/2021 | 14/12/2021 | R.S CONSTRUCTION | 5.05 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. | SM/09518 | Augmentation | New Service Connection Charge for ARAJI MARIA KAMALA PUKHARI (REJU) W/S SCHEME, T/W No. III, under PANDAPARA CCC, [APPLICATION NO. 400296685, Reference ID : 402852995] |  |  | VCH/000846/2022-2023 | BP/22-23/45 | 08/09/2022 | 08/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.46 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. | SM/09518 | Augmentation | Supply, delivery & installation of 10KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of ARJI MARIA KAMALA PUKHARI W/S Scheme at T/W No. III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000269/2022-2023 | 1013/NMD | 28/07/2022 | 18/08/2022 | MAA ENTERPRISES | 1.87 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. | SM/09518 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of ARGIMARIA KAMOLAPOKORI piped Water Supply Scheme at Jalpaiguri Block under under Jalpaiguri Division, PHE Dte. (PART-E) |  |  | ORD/000640/2020-2021 | 19/JD | 14/01/2021 | 15/03/2021 | BILTU DAS | 36.92 | 0 | 0 | 1
9 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. | SM/09518 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Argimaria Kamolapokori Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000716/2021-2022 | 2229/JD | 27/12/2021 | 25/02/2022 | SABITA ENTERPRISE | 11.43 | 0 | 0 | 1
10 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. | SM/09518 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for TW NO. III, ARJI MARIA KAMALA PUKHARI (REJU) PIPED WATER SUPPLY SCHEME, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000122/2022-2023 | 859/NMD | 18/07/2022 | 17/08/2022 | THE BANERJEE CONCERN | 7.61 | 0 | 0 | 100
11 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. | SM/09518 | Augmentation | Supply delivery of the different UPVC materials for Reverse Rotary Circulation method of drilling for construction of BDTW for the Rejuvenation of Arji Maria Kamala Pukhari PWSS, Block - Jalpaiguri, Dist.- Jalpaiguri, at deptt. Stack-Yard at Fulbari under NMSD (D), PHE, Dte. | Driller-in-Charge | Junior Engineer | ORD/000654/2022-2023 | 1363/NMD | 02/12/2022 | 01/01/2023 | SARKAR ELECTRIC | 11.59 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. | SM/09518 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 1086/JD | 24/08/2023 | 24/08/2023 | Resource Division | 3.45 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. | SM/09518 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Argimaria Kamolapokori Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000884/2021-2022 | 386/JD | 10/02/2022 | 11/04/2022 | SUSANTA GHOSH | 11.44 | 0 | 0 | 100
14 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. | SM/09518 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for TW NO. IV, ARJI MARIA KAMALA PUKHARI (REJU) PIPED WATER SUPPLY SCHEME, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000123/2022-2023 | 860/NMD | 18/07/2022 | 17/08/2022 | M/S UTPAL CHAKRABORTY & CO. | 7.6 | 0 | 0 | 100
15 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. | SM/09518 | Augmentation | Supply, delivery & installation of 10KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of ARJI MARIA KAMALA PUKHARI W/S Scheme at T/W No. IV in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer ,Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000270/2022-2023 | 1014/NMD | 28/07/2022 | 18/08/2022 | M/S ANJALI ENTERPRISE | 1.89 | 0 | 0 | 100
16 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. | SM/09518 | Augmentation | Construction Of approach roads for Arjimaria Kamala Pokhari Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. .(3rd & 4thSite) | Assistant Engineer | Junior Engineer | ORD/000411/2022-2023 | 166/RWS | 28/02/2023 | 14/03/2023 | R.S CONSTRUCTION | 1.61 | 0 | 0 | 1
17 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. | SM/09518 | Augmentation | Rising Main Connections(at 3rd & 4th TW site) including other necessary arrangement for Rejuvenation of Araji Maria Kamala Pukhari Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000489/2022-2023 | 288/RWS | 29/03/2023 | 19/04/2023 | JAYDEB SAHA | 3.54 | 0 | 0 | 100
Total | [13 empty] | 113.07 | 0 | 0