## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Mohitnagar Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001068/2021-2022 | 39/JD | 04/12/2021 | 02/02/2022 | NARESH SEN | 11.12 | 11.45 | 103 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jalsapna under the command area of Mohit Nagar W/S/S under Jalpaiguri Division , P.H.E. Dte ( part ¿ F ) |  | Junior Engineer | ORD/000325/2021-2022 | 879/RWS | 10/12/2021 | 20/12/2021 | M/S DEY & ROY CHOUDHURY | 1.28 | 0 | 0 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Mohit Nagar Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. (Part-G) |  | Junior Engineer | ORD/000513/2021-2022 | 537/JD | 25/02/2022 | 27/03/2022 | M/S DEY & ROY CHOUDHURY | 21.77 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. | Assistant Engineer | Junior Engineer | ORD/000305/2022-2023 | 2194/JD | 11/11/2022 | 11/12/2022 | M/S MILLENNIUM FUEL CENTRE | 3.56 | 3.56 | 100 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. | Assistant Engineer | Junior Engineer | ORD/000301/2022-2023 | 2190/JD | 11/11/2022 | 11/12/2022 | M/S MILLENNIUM FUEL CENTRE | 3.32 | 3.32 | 100 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Mohitnagar Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000296/2021-2022 | 38/JD | 04/01/2022 | 05/03/2022 | SAUMENDU DUTTA | 10.87 | 0 | 0 | 100
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for REJUVENATION OF MAHITNAGAR PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000036/2022-2023 | 351/NMD | 23/05/2022 | 22/06/2022 | M/S SAJAHAN CHOWDHURY | 9.19 | 9.19 | 100 | 0
8 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for REJUVENATION OF MAHITNAGAR PWSS, TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000037/2022-2023 | 352/NMD | 23/05/2022 | 22/06/2022 | ALPHA ENTERPRISE | 9.18 | 9.18 | 100 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Restoration of pipe line at different places including construction of sluice valve chamber with supply of sluice valv etc.at head work site campus under Mohitnagar W/S/S under Jalpaiguri Division , P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000017/2022-2023 | 306/RWS | 28/04/2022 | 13/05/2022 | M/S DEY & ROY CHOUDHURY | 4.83 | 4.83 | 99.89 | 1
10 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector for REJUVENATION of MAHITNAGAR W/S Scheme at T/W No. IV in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000027/2022-2023 | 269/NMD | 22/04/2022 | 13/05/2022 | SARKAR ELECTRIC | 2.77 | 2.77 | 100 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Mohitnagar Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001074/2021-2022 | 38/JD | 04/01/2022 | 05/03/2022 | SAUMENDU DUTTA | 10.87 | 0.28 | 2.59 | 1
12 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector for REJUVENATION of MAHITNAGAR W/S Scheme at T/W No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000026/2022-2023 | 268/NMD | 22/04/2022 | 13/05/2022 | S.P. ENTERPRISE | 2.77 | 2.77 | 100 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Renovation of Boundary wall including Approach Road, Earth filling, Valve Chambers at Head Work Site of Mohitnagar Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000236/2022-2023 | 1813/JD | 14/09/2022 | 05/10/2022 | M/S DEY & ROY CHOUDHURY | 8.1 | 7.79 | 96.18 | 1
14 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Supply, delivery of Pea-size Gravels (Local Variety) for the contruction of Big Dia Tubewell by Reverse Rotary Circulation Method of Drilling at Rejuvenation of Mahitnagar PWSS TW-III, Dist- Jalpaiguri, under N.M.S.D.(D), P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/000718/2021-2022 | 283/DSD | 03/01/2022 | 10/01/2022 | SUMON ELECTRICAL | 0.95 | 0 | 0 | 100
15 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Carrying out Surging, Development and Y.T. works for a Rig Bored Big Dia Tube well (BDTW) by reverse rotary method of drilling for Rejuvenation of Porapara PWSS TW-III, Rejuvenation of Mahitnagar PWSS TW-III & IV, Rejuvenation of Arji Maria Kamala Pukhari PWSS TW-III & IV, Block - Jalpaiguri, Dist.- Jalpaiguri under different water supply scheme under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/000821/2021-2022 | 311/DSD | 21/01/2022 | 11/02/2022 | UTTAM PAUL | 0.73 | 0.73 | 100 | 100
16 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Supply, delivery of Pea-size Gravels (Local Variety) for the contruction of Big Dia Tubewell by Reverse Rotary Circulation Method of Drilling at Rejuvenation of Mahitnagar PWSS TW-IV, Dist- Jalpaiguri, under N.M.S.D.(D), P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/000743/2021-2022 | 330/DSD | 08/02/2022 | 15/02/2022 | S.P. ENTERPRISE | 0.95 | 0 | 0 | 100
17 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | New Service Connection Charge for T/W No. III of MAHITNAGAR (REJU) W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO.4002923192, Reference ID : 402817972] |  |  | VCH/000147/2022-2023 | BP/2022-23/15 | 16/06/2022 | 16/06/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.95 | 0 | 0 | 0
18 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | FHTC SAMSING |  |  | VCH/001149/2021-2022 | BP-2021-22-235 | 16/02/2022 | 16/02/2022 | SUJAN LAMA | 4.79 | 0 | 0 | 0
19 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | New Service Connection Charge for T/W No. IV of MAHITNAGAR (REJU) W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 4002923185, Reference ID : 402817973] |  |  | VCH/000145/2022-2023 | BP/2022-23/15 | 16/06/2022 | 16/06/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.95 | 0 | 0 | 0
20 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | LDS FHTC LIKSAN BAZAR (ZONE - III) |  |  | VCH/001394/2021-2022 | BP-2021-22515 | 30/03/2022 | 30/03/2022 | ALICK DUTTA | 13.19 | 0 | 0 | 0
21 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | DEV LAND & REPAIRING SANITARY & PLUMBING ARRANGEMENT |  |  | VCH/001402/2021-2022 | BP-2021-22-506 | 30/03/2022 | 30/03/2022 | SANDIP BANIK | 4.55 | 0 | 0 | 0
22 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Installation of Infrastructure IRO NSC Application 4002923185 at T/W No. IV of MAHITNAGAR (REJU) W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 100000050946, Reference ID : 860240066] |  |  | VCH/000146/2022-2023 | BP/2022-23/15 | 16/06/2022 | 16/06/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.62 | 0 | 0 | 0
23 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Installtion of Infrastructure IRO NSC application 4002923192 at T/W No. III of MAHITNAGAR (REJU) W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 100000050946, Reference ID : 860240066] |  |  | VCH/000148/2022-2023 | BP/2022-23/15 | 16/06/2022 | 16/06/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.09 | 0 | 0 | 0
24 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Supply, Installation, Commissioning (Trial run for 3 months) including testing of 2Nos. 25.00 cum per hour capacity pressure type IEP with accessories including construction of Blower Rooms (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd & 4th tube well site for Rejuvenation of Mohitnagar water supply scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000347/2022-2023 | 132/JD | 17/01/2023 | 03/03/2023 | R.S CONSTRUCTION | 30.33 | 18.18 | 59.92 | 100
25 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Retrofitting at Sebagram in connection with JJM under the command area of Mohit Nagar W/S Scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 598/JD | 09/03/2023 | 24/03/2023 | M/S DEY & ROY CHOUDHURY | 4.79 | 0 | 0 | 100
26 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Providing Functional Household Tap Connection (FHTC) at Gomosta Para in connection with JJM under the command area of Mohit Nagar W/S Scheme under Jalpaiguri Division PHE Dte. (PART-I) | Assistant Engineer | Junior Engineer | ORD/000410/2022-2023 | 601/JD | 09/03/2023 | 30/03/2023 | M/S DEY & ROY CHOUDHURY | 4.84 | 0 | 0 | 100
27 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Providing Functional Household Tap Connection (FHTC) at Sebagram in connection with JJM under the command area of Mohit Nagar W/S Scheme under Jalpaiguri Division PHE Dte. (PART-H) | Assistant Engineer | Junior Engineer | ORD/000409/2022-2023 | 599/JD | 09/03/2023 | 30/03/2023 | M/S DEY & ROY CHOUDHURY | 4.51 | 0 | 0 | 100
28 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Providing Guard wall including additional part of Boundary wall at 3rd Tubewell Site of Mohitnagar Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000457/2022-2023 | 743/JD | 23/03/2023 | 07/04/2023 | SAUMENDU DUTTA | 1.76 | 0 | 0 | 0
29 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Retrofitting at Gomosta Para in connection with JJM under the command area of Mohit Nagar W/S Scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000408/2022-2023 | 602/JD | 09/03/2023 | 24/03/2023 | M/S DEY & ROY CHOUDHURY | 3.33 | 0 | 0 | 100
30 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Rising Main Connections (at 3rd & 4th TW site) including other necessary arrangement for Rejuvenation of Mohit Nagar Water Supply Scheme under Jalpaiguri Division P.H.E.Dte Jalpaiguri. |  | Junior Engineer | ORD/000405/2022-2023 | 165/RWS | 28/02/2023 | 21/03/2023 | SOUVIK SAHA | 3.28 | 3.24 | 98.91 | 100
31 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 1117/JD | 24/08/2023 | 24/08/2023 | Resource Division | 3.55 | 0 | 0 | 0
Total | [13 empty] | 189.8 | 77.3 | 40.73