## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme | SM/09560 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Purba Daukimari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  |  | ORD/000289/2021-2022 | 1258/JD | 10/08/2021 | 25/08/2021 | RABINDRANATH DUTTA | 4.81 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme | SM/09560 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna at Purba Daukimari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. Phase-III | Assistant Engineer,HQ | Junior Engineer | ORD/000532/2021-2022 | 130/JD | 14/01/2022 | 04/02/2022 | RABINDRANATH DUTTA | 4.84 | 0 | 0 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme | SM/09560 | Augmentation | Laying distribution system with FHTC work for Augmentation of Purba Daukimari Piped water Supply Scheme , at Dhupguri Block under Jalpaiguri Division.P.H.E. Dte. (Part-A) |  | Junior Engineer | ORD/000373/2021-2022 | 333/JD | 02/02/2022 | 02/06/2022 | SUKES BASU MAJUMDAR | 328.7 | 0 | 0 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme | SM/09560 | Augmentation | Soil Investigation work for 300 CuM OHR for Augmentation of Purba Batabari PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000690/2021-2022 | 1064/JSSD | 24/01/2022 | 13/02/2022 | G. TECH INDIA | 1.83 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme | SM/09560 | Augmentation | IEP MAYNAGURI ZONE II |  |  | VCH/001319/2021-2022 | BP-2021-22-388 | 17/03/2022 | 17/03/2022 | SUKES BASU MAJUMDAR | 26.7 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme | SM/09560 | Augmentation | REJUNATION 2ND TUBE WELL SITE CHALSA |  |  | VCH/001291/2021-2022 | BP-2021-22-422 | 25/03/2022 | 25/03/2022 | SUKUMAR KUNDU | 0.94 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme | SM/09560 | Augmentation | IEP FOR MAYNAGURI PWSS |  |  | VCH/001249/2021-2022 | BP-2021-22-388 | 17/03/2022 | 17/03/2022 | SUKES BASU MAJUMDAR | 26.7 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme | SM/09560 | Augmentation | b-wall for kharija berubari pwsss |  |  | VCH/000023/2022-2023 | BP-2021-23-4 | 21/04/2022 | 21/04/2022 | GANAPATI ENGINEERS CO-OPERATIVE SOCIETY LTD. | 21.41 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme | SM/09560 | Augmentation | Construction of 250 CuM. Capacity R.C.C. Over Head Reservoir of 20 Mtr. Staging Height, Construction of One No. Pump House (5.40m x 3.60m) for the Head Works Site and other related works including pump connection of different pump for Augmentation of Purba Daukimari Piped Water Supply Scheme of Dhupguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000374/2021-2022 | 196/JD | 21/01/2022 | 20/07/2022 | PRADIP SAHA | 75.21 | 0 | 0 | 1
10 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme | SM/09560 | Augmentation | Laying of Paver Block with development of approach pathway as a restoration work due to delivery main and Rising main laying for Augmentation of Purba Daukimari Piped water supply scheme under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000102/2023-2024 | 445/JD. | 08/06/2023 | 29/06/2023 | TARAKESWAR PRASAD | 4.59 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | Augmentation of Purba Daukimari Piped Water Supply Scheme | SM/09560 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF DAUKIMARI PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000234/2023-2024 | 1248/NMD | 31/07/2023 | 30/08/2023 | MAA ENTERPRISES | 10.87 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme | SM/09560 | Augmentation | Retrofitting works related to FHTC in connection with Jalsapna at different locations of Chanadipa Mouza of Dakshin Salbari W/S/S Under Jalpaiguri Division ,P.H.E. Dte. |  |  | ORD/000521/2021-2022 | 157/RWS | 24/02/2022 | 11/03/2022 | ANUP SARKAR | 4.73 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme | SM/09560 | Augmentation | Sinking of 1 No. 250mm x 150mm x 133 m deep Rig Bored tube well by Reverse Rotary method of drilling for Augmentation of Purba Daukimari Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000561/2021-2022 | 441/JD | 17/02/2022 | 19/03/2022 | MALAY BHOWMIK | 7.92 | 0 | 0 | 100
14 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme | SM/09560 | Augmentation | Retrofitting works related to FHTC in connection with Jalsapna at different locations of Madhya Salbari Mouza of Dakshin Salbari water Supply Scheme under Jalpaiguri Division , P.H.E. Dte |  |  | ORD/000520/2021-2022 | 156/RWS | 24/02/2022 | 11/03/2022 | ANUP SARKAR | 4.73 | 0 | 0 | 0
15 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme | SM/09560 | Augmentation | Laying Distribution System including road boaring, Supplying and fitting fixing specials, Jeffy Coupling and other miscelleneous works for Augmentation of Purba Daukimari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Part-C) |  |  | ORD/000391/2023-2024 | 1555/JD | 01/11/2023 | 01/12/2023 | B.M CONSTRUCTION | 14.3 | 0 | 0 | 100
16 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme | SM/09560 | Augmentation | Laying Distribution System including culvert crossing and road restoration for Augmentation of Purba Daukimari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Part-B) |  |  | ORD/000389/2023-2024 | 1553/JD | 01/11/2023 | 22/11/2023 | B.M CONSTRUCTION | 9.41 | 0 | 0 | 100
17 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme | SM/09560 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2021-2022 | 556/JD | 01/03/2022 | 01/03/2022 | Resource Division | 17.98 | 0 | 0 | 0
18 | JALPAIGURI |  | Northern Mechanical | Augmentation of Purba Daukimari Piped Water Supply Scheme | SM/09560 | Augmentation | New Service Connection Charge for AUGMENTATION OF DAUKIMARI PWSS, TW no I, under DHUPGURI CCC APPLICATION NO. 4003391338 Reference ID : 403203884 |  |  | BILL/00510/2024-2025 | BP/24-25/111 | 05/07/2024 | 05/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.32 | 0 | 0 | 0
Total | [13 empty] | 578.99 | 0 | 0