## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | PREPARATION OF DPR DAKHIN CHAKMOULANI |  |  | VCH/001282/2021-2022 | BP-2021-22-490 | 09/04/2022 | 09/04/2022 | SUBHANKAR GHOSH | 1.56 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | Continuation Order for the work "Supply of (one) Maxi Cab with engine capacity more than 2000 C.C on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Sub-Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi Permit)" from 01.01.2023 to 31.03.2023 | Assistant Engineer | Junior Engineer | ORD/000368/2022-2023 | 348/JSSD | 27/12/2022 | 27/03/2023 | TANMOY CHOUDHURY | 0.44 | 0.4 | 90.98 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | Continuation Order for the work ¿Supply of (one) Maxi Cab with engine capacity more than 2000 C.C on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Sub- Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi Permit)¿ from 01.10.2022 to 31.12.2022. | Assistant Engineer | Junior Engineer | ORD/000358/2022-2023 | 248/JSSD | 28/09/2022 | 30/12/2022 | TANMOY CHOUDHURY | 0.46 | 0.33 | 72.47 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | Sinking of 1 No. 250mm x 150mm x 138m deep Rig Bored tube well by Reverse Rotary method of drilling for Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000010/2022-2023 | 871/JD | 04/04/2022 | 25/04/2022 | UNIBRO INFRASERV PRIVATE LIMITED | 8 | 7.72 | 96.47 | 100
5 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | Soil Investigation work for 300 CuM Over Head Reservoir (OHR) for Augmentation of Dakshin Chalk Moulani P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000691/2021-2022 | 1066/JSSD | 24/01/2022 | 13/02/2022 | ASIS ENTERPRISE | 1.83 | 1.81 | 98.94 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size including Sanitary and Plumbing works at 3rd TubeWell site for Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000831/2021-2022 | 1109/W/JSSD | 27/01/2022 | 13/03/2022 | M/S M G CONSTRUCTION | 4.76 | 4.71 | 98.82 | 100
7 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | Construction of Rig approach for Installation of tubewell 3rd Tube Well site for Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000108/2022-2023 | 85/JSSD | 22/07/2022 | 29/07/2022 | ALICK DUTTA | 0.81 | 0.81 | 99.45 | 100
8 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | SUPPLY OF SHARP TONNER CARTRIDGE |  |  | BILL/00131/2022-2023 | BP-2022-23-404 | 17/01/2023 | 17/01/2023 | QUATTRON | 0.17 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | hire chages |  |  | BILL/00247/2022-2023 | BP-2022-23-438 | 03/02/2023 | 03/02/2023 | LOKNATH CONSTRUCTION | 0.52 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | ETDS |  |  | BILL/00130/2022-2023 | BP-2022-23-406 | 17/01/2023 | 17/01/2023 | SUSHIL KUMAR SINGHA | 0.13 | 0 | 0 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | ETDS |  |  | BILL/00129/2022-2023 | BP-2022-23-405 | 17/01/2023 | 17/01/2023 | SUSHIL KUMAR SINGHA | 0.08 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | FUEL SUPPLY |  |  | BILL/00128/2022-2023 | BP-2022-23-403 | 17/01/2023 | 17/01/2023 | FILL & SMILE | 1.71 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | Laying Distribution System providing with Functional Household Tap Connection (FHTC) in connection with Jal Swapna / JJM for Augmentation of Dakhin Chak Moulani Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000348/2021-2022 | 211/JD | 24/01/2022 | 25/03/2022 | UNIBRO INFRASERV PRIVATE LIMITED | 426.83 | 307.35 | 72.01 | 80
14 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme i.c.w. Jal Jeevan Mission under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer | Junior Engineer | ORD/000811/2023-2024 | 566/JSSD | 05/03/2024 | 04/04/2024 | GOURAV CONSTRUCTION CO. | 4.03 | 2.32 | 57.46 | 90
15 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | Balance work i.c.w Laying Rising Main from 1st, 2nd & 3rd Tubewell site OHR Aug. of Dakshin Chak Moulani PWSS in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000117/2024-2025 | 230/JSSD | 10/09/2024 | 20/09/2024 | SADHAN KARMAKAR | 0.64 | 0 | 0 | 0
16 | JALPAIGURI |  | Northern Mechanical | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF DAKSHIN CHAK MOULANI PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000444/2023-2024 | 1383/NMD | 09/08/2023 | 08/09/2023 | M/S ROYAL ENTERPRISE | 10.32 | 10.31 | 99.97 | 60
17 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | Construction of Boundary Wall at 3rd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Dakshin Chakmoulani Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000107/2022-2023 | 83/JSSD | 22/07/2022 | 11/08/2022 | CHANDAN GHOSH | 4.56 | 4.41 | 96.59 | 100
18 | JALPAIGURI |  | Northern Mechanical | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | New Service Connection Charge for AUGMENTATION OF DAKSHIN CHAK MOULANI, T/W No. III, under KRANTI CCC, [APPLICATION NO. 4003266328, Reference ID : 403105517] |  |  | BILL/01275/2023-2024 | 23-24/153&162 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
19 | JALPAIGURI |  | Northern Mechanical | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | Infrastructure Cost for AUGMENTATION OF DAKSHIN CHAK MOULANI, T/W No. III, under KRANTI CCC, [APPLICATION NO. 100000093179, Reference ID : 860284829] |  |  | BILL/01276/2023-2024 | 23-24/153&162 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.87 | 0 | 0 | 0
20 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing with land development works for Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000349/2023-2024 | 1437/JD | 05/10/2023 | 02/08/2025 | M/S. D.K. DEY & CO.. | 91.09 | 29.66 | 32.56 | 35
21 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | Construction of Boundary Wall with Pump House (3.6mx2.4m) and Sinking of tube well by reverse rotary method of Drilling for 4th TW including Delivery main for Augmentation of Dakshin Chak Moulani PWSS under Jal Jeevan Mission under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000022/2024-2025 | 671/JD | 16/07/2024 | 02/04/2026 | M/S S. G. ENTERPRISE | 19.97 | 3.26 | 16.33 | 80
22 | JALPAIGURI |  | Northern Mechanical | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | New Service Connection Charge for DAKSHIN CHAK MOULANI,TW NO-IV, KRANTI CCC APPLICATION NO. 4003563031 Reference ID : 403328660 |  |  | BILL/02197/2024-2025 | BP/24-25/251 | 05/02/2025 | 05/02/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
23 | JALPAIGURI |  | Northern Mechanical | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | SM/09561 | Augmentation | Infrastructure development cost for new service connection at DAKSHIN CHAK MOULANI,TW NO-IV, KRANTI CCC APPLICATION NO. 100000126896 Reference ID : 860321656 |  |  | BILL/02196/2024-2025 |  | 14/01/2025 | 14/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.89 | 0 | 0 | 0
Total | [13 empty] | 593.03 | 373.09 | 62.91