## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme | SM/09562 | Augmentation | Sinking of 250mm x 150mm dia tube well by Reverse Rotary method of drilling for 3rd Tube well for Augmentation of Shikarpur PWSS at Rajganj Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000560/2021-2022 | 440/JD | 17/02/2022 | 19/03/2022 | MALAY BHOWMIK | 7.23 | 7 | 96.81 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme | SM/09562 | Augmentation | Soil Investigation for the work of Construction of R.C.C Over head Reservoir (350 cum) at Shikarpur under Shikarpur piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000170/2022-2023 | 1411/JD | 12/07/2022 | 27/07/2022 | MABCO CONSULTANT | 2.26 | 2.11 | 93.51 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme | SM/09562 | Augmentation | Thorough repair and overhauling of the Iron Elimination Plant installed at Shikarpur Water Supply Scheme, under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000207/2022-2023 | 1797/JD | 14/09/2022 | 05/10/2022 | KANAI LAL SEN | 3.04 | 2.89 | 95.15 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme | SM/09562 | Augmentation | Construction of Pump House (3.60m x 2.40m) size with sanitary & plumbing arrangement at 3rd Tube Well site of Shikarpur PWSS i.c.w. Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000373/2022-2023 | 298/JD | 10/02/2023 | 27/03/2023 | DOMOHANI YOUNG CO-OPLAB.CONT.&CONST SO. LTD | 4.69 | 4.69 | 100 | 1
5 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme | SM/09562 | Augmentation | Construction of Room and other ancillary work at Belakoba primary school near H/W site for Shikarpur piped water supply schemer at Rajganj block under Jalpaiguri division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000112/2023-2024 | 447/JD. | 08/06/2023 | 23/07/2023 | DEBABRATA SARKAR | 2.94 | 2.99 | 101.68 | 100
6 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme | SM/09562 | Augmentation | Dismantiling old IEP, old Pump house and filling old CWR and other ancillary works at Sikarpur under Sikarpur piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000111/2023-2024 | 446/JD. | 08/06/2023 | 22/06/2023 | GOUTAM DAS | 6 | 6 | 99.99 | 100
7 | JALPAIGURI |  | Northern Mechanical | Augmentation of Shikarpur Piped Water Supply Scheme | SM/09562 | Augmentation | New Service Connection Charge for SHIKARPUR W/S Scheme, T/W No. III, under BELAKOBA CCC [APPLICATION NO. 4003114721 ; Reference ID : 402982646] |  |  | BILL/00807/2022-2023 | BP/22-23/170 | 29/03/2023 | 29/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | Augmentation of Shikarpur Piped Water Supply Scheme | SM/09562 | Augmentation | Infrastructure Cost for SHIKARPUR W/S Scheme, T/W No. III, under BELAKOBA CCC [APPLICATION NO.100000074416 ; Reference ID : 860265926] |  |  | BILL/00808/2022-2023 | BP/22-23/170 | 29/03/2023 | 29/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.9 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | Augmentation of Shikarpur Piped Water Supply Scheme | SM/09562 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF SHIKARPUR PWSS, at TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000879/2022-2023 | 362/NMD | 29/03/2023 | 28/04/2023 | SAIKAT SINHA | 11.07 | 11.06 | 99.87 | 100
10 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme | SM/09562 | Augmentation | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 3rd tubewell site at Shikarpur piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000619/2023-2024 | 2315/JD | 07/02/2024 | 08/03/2024 | DOMOHANI YOUNG CO-OPLAB.CONT.&CONST SO. LTD | 8.28 | 7.21 | 87.01 | 100
11 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme | SM/09562 | Augmentation | Rejuvenation work for Pump houses and laying UPVC pipe line at H/W site of Augmentation of Shikarpur Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000019/2024-2025 | 519/JD | 27/06/2024 | 20/10/2024 | KANAI LAL SEN | 7.02 | 6.86 | 97.71 | 100
12 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme | SM/09562 | Augmentation | Construction of Boundary Wall with gate, drain, land development, pathway including interconnection work and laying pipe line at Augmentation of Shikarpur PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000156/2024-2025 | 1530/JD | 01/10/2024 | 16/12/2024 | GOUTAM DAS | 16.48 | 0 | 0 | 100
13 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme | SM/09562 | Augmentation | VEHICLE BILL |  |  | BILL/01179/2023-2024 |  | 25/01/2024 | 25/01/2024 | DHIRAJ BISWAS | 1.2 | 0 | 0 | 0
14 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme | SM/09562 | Augmentation | FUEL BILL |  |  | BILL/01181/2023-2024 | BP-2023-24-631 | 06/02/2024 | 06/02/2024 | FILL & SMILE | 0.82 | 0 | 0 | 0
15 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme | SM/09562 | Augmentation | VEHICLE DRIVER |  |  | BILL/01178/2023-2024 |  | 25/01/2024 | 25/01/2024 | RAKESH SARKAR | 0.37 | 0 | 0 | 0
16 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme | SM/09562 | Augmentation | Providing Functional Household Tap Connection (FHTC) for Augmentation of Shikarpur Piped Water Supply Scheme at Block- Rajganj under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000542/2023-2024 | 1933/JD | 02/01/2024 | 16/02/2024 | JAYA SARKAR | 17.09 | 0 | 0 | 0
17 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme | SM/09562 | Augmentation | Laying of Water Distribution System with Functional Household Tap Connection (FHTC) including construction valve chamber and other ancillary works in connection with Jal Jeevan Mission for Augumentation of Shikarpur Piped Water Supply Scheme at Block - Rajganj under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000816/2023-2024 | 2622/JD | 07/03/2024 | 28/10/2025 | SCEC BOENTER AND KDAS JOINT VENTURE | 559.19 | 158.28 | 28.3 | 59
18 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme | SM/09562 | Augmentation | Supplying and Installation of 70 Nos. Display Board at Different Piped Water Supply Schemes in connection with JJM under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000602/2024-2025 | 271/JD | 07/02/2025 | 22/02/2025 | SAPTASWA SARKAR | 13.75 | 0 | 0 | 100
19 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme | SM/09562 | Augmentation | Continuation Order for the Work of "Providing Contractual Monthly Salary basis Agency personnel for day to day work in Estimate Section, under Jalpaiguri Division, P.H.E. Dte. (w.e.f. 01.07.2025 to 29.11.2025) | Assistant Engineer,HQ |  | ORD/000142/2025-2026 | 1495/JD | 30/06/2025 | 29/11/2025 | SOMNATH ROY | 0.94 | 0 | 0 | 0
20 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme | SM/09562 | Augmentation | CONSTRUCTION OF RCC OVERHEAD RESERVOIUR CAPACITY 350 CUM AND 20 M STAGGING HEIGHT INCLUDING CONSTRUCTION OF PUMP HOUSE (5.40 M X 3.60M) AS PER DEPERMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SHIKARPUR PIPED WATER SUPPLY SCHEME BLOCK:RAJGANJ ,DISTRICT:JALPAIGURI, UNDER JALPAIGURI DIVISION, P.H.E. DTE. | Assistant Engineer,HQ | Junior Engineer | ORD/000584/2021-2022 | 733/JD | 17/03/2022 | 26/01/2025 | GOUTAM DAS | 83.34 | 75.13 | 90.14 | 100
Total | [13 empty] | 750.29 | 284.21 | 37.88