## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | Restoration of damaged DI Pipeline at Kathapara Piped W/S at Dhupguri Development Block Under Jalpaiguri Division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000128/2022-2023 | 1320/JD | 16/06/2022 | 01/07/2022 | SADHAN KARMAKAR | 0.96 | 0.96 | 99.3 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | Sinking of 250mm x 150mm dia tubewell by Reverse Rotary method of drilling for Rejuvenation of Kathapara at Dhupguri Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000324/2022-2023 | 2411/JD | 19/12/2022 | 18/01/2023 | SAUMENDU DUTTA | 8.61 | 8.02 | 93.09 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | Construction of Boundary wall with ancillary works for the Pump House No. 1 Premises of the Bhatia para Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000128/2020-2021 | 1196/JD | 06/11/2020 | 06/12/2020 | RABINDRANATH DUTTA | 4.99 | 5.09 | 102.02 | 100
4 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | Soil Investigation for the work of Construction of R.C.C. Over Head Reservoir for the Head Works Site of Augmentation of Kathapara P.W.S.S. under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000190/2022-2023 | 1693/JD | 06/09/2022 | 27/09/2022 | MOYTEC | 0.97 | 0.71 | 73.49 | 100
5 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | Shifting and Laying of Parallel pipeline in place of partially damaged pipeline for widening and strengthening BRO Road from Chamurchi to Banerhat more including minor retrofitting works to the Division line under Haritalguri T.G. P.W.S.S. command area under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000148/2022-2023 | 1553/JD | 05/08/2022 | 26/08/2022 | NARAYAN CHANDRA SAHA | 25.32 | 25.28 | 99.81 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | Land Developmrent at Head Works site under Jabramali Piped Water Supply Scheme whithin Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000280/2022-2023 | 645/RWS | 21/10/2022 | 05/11/2022 | M/S RATAN KUMAR DAS GUPTA AND CO | 2.59 | 2.56 | 98.54 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | Construction of Pump House (3.60m x 2.40m) size with sanitary & plumbing arrangement at 3rd Tube Well site for Kathapara PWSS i.c.w. Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000374/2022-2023 | 299/JD | 10/02/2023 | 27/03/2023 | ABHIK BHOWMIK | 4.64 | 4.73 | 101.82 | 100
8 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | TEMPORARY HIRING OF ONE MAXI CAB WITH DRIVER |  |  | BILL/00265/2023-2024 | BP-2023-24-251 | 21/07/2023 | 21/07/2023 | RUPA PRASAD | 0.34 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation |  |  |  | BILL/00266/2023-2024 | BP-2023-24-252 | 21/07/2023 | 21/07/2023 | APIKUL ALI | 0.35 | 0 | 0 | 0
10 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | New Service Connection Charge for KATHAPARA, TW No. III, DHUPGURI CCC, [APPLICATION NO. 4003147726, Reference ID : 403014087] |  |  | BILL/00057/2023-2024 | BP/23-24/17 | 24/05/2023 | 24/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | supply for fuel |  |  | BILL/00264/2023-2024 | BP-2023-24-250 | 21/07/2023 | 21/07/2023 | FILL & SMILE | 0.58 | 0 | 0 | 0
12 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | Infrastructure Cost for KATHAPARA, TW No. III, DHUPGURI CCC, [APPLICATION NO. 100000077916, Reference ID : 860269056] |  |  | BILL/00058/2023-2024 | BP/23-24/17 | 24/05/2023 | 24/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.38 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | Construction of 400 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing at Head Works site for Augmentation of Kathapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000585/2021-2022 | 734/JD | 17/03/2022 | 13/09/2022 | SCEC BOENTER KDAS JOINT VENTURE | 82.2 | 34.61 | 42.11 | 75
14 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | Rejuvenation of 2nd Tube Well Site and Head Work Site Pump House at Kathapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000378/2024-2025 | 2027/JD | 19/11/2024 | 09/12/2024 | ABHIK BHOWMIK | 2.41 | 0 | 0 | 0
15 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2024-2025 | 58/JD | 09/04/2024 | 09/04/2024 | Resource Division | 18.24 | 0 | 0 | 0
16 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | Fuel charges for Government Inspection vehicle under NMD ,PHE,DTE Invoice No :0003/2024-2025 ,Dt - 30/06/24 |  |  | BILL/01056/2024-2025 | BP/24-25/199 | 12/09/2024 | 12/09/2024 | M/S MILLENNIUM FUEL CENTRE | 0.35 | 0 | 0 | 0
17 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | Fuel ,lubrication charges for Government Inspection vehicle under NMD ,PHE,DTE Invoice No :0002/2024-2025 ,Dt - 31/05/24 |  |  | BILL/01055/2024-2025 |  | 16/08/2024 | 16/08/2024 | M/S MILLENNIUM FUEL CENTRE | 0.51 | 0 | 0 | 0
18 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | Providing Functional Household Tap Connection in connection with Jal Swapna/JJM with minor retrofitting works under Kathapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Phase-I) | Assistant Engineer,HQ | Junior Engineer | ORD/000229/2022-2023 | 1746/JD | 08/09/2022 | 01/08/2025 | SCEC BOENTER KDAS JOINT VENTURE | 76.15 | 0 | 0 | 15
19 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | Laying Rising Main of 3rd Tube Well site of Kathapara PWSS, in connection with Rejuvenation of Kathapara Piped Water Supply Scheme under Jal Jeevan Mission at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000529/2023-2024 | 1850/JD | 15/12/2023 | 01/01/2025 | ABHIK BHOWMIK | 4.73 | 0 | 0 | 100
20 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | Construction of Boundary Wall, Sluice Valve, Pathway, Drain etc. at 3rd TW Site for Kathapara PWSS i.c.w. JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000488/2024-2025 | 2427/JD | 24/12/2024 | 11/09/2025 | ABHIK BHOWMIK | 11.54 | 0 | 0 | 80
21 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Driller-in-Charge |  | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 25/03/2025 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
22 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | Laying Distribution System for Augmentation of Kathapara Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000016/2022-2023 | 972/JD | 20/04/2022 | 01/08/2025 | SCEC BOENTER KDAS JOINT VENTURE | 430.18 | 104.72 | 24.34 | 60
23 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KATHAPARA PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000877/2022-2023 | 341/NMD | 29/03/2023 | 01/08/2024 | TAPAN BISWAS | 10.9 | 10.88 | 99.88 | 100
Total | [13 empty] | 692.8 | 197.55 | 28.52