## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. | SM/09564 | Augmentation | Construction of permanent service Road and repairing of Internal pathway for the Head Works Site of the Purba Magurmari P.W.S.S. |  |  | ORD/000189/2018-2019 | 264/JD | 19/02/2019 | 12/03/2019 | ARATI CONSTRUCTION | 4.84 | 2.37 | 49.01 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. | SM/09564 | Augmentation | Sinking of 2 No. 250mm x 150mm x 133 m deep Rig Bored tube well by Reverse Rotary method of drilling for Rejuvenation of Purba Magurmari Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000562/2021-2022 | 442/JD | 17/02/2022 | 19/03/2022 | MALAY BHOWMIK | 15.63 | 15.19 | 97.23 | 1
3 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. | SM/09564 | Augmentation | Infrastructure Cost for PURBA MAGURMARI W/S Scheme, T/W No. V, under DHUPGURI CCC, [APPLICATION NO. 100000066800, Reference ID : 860257020] |  |  | BILL/00039/2022-2023 | BP/22-23/131 | 20/01/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.04 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. | SM/09564 | Augmentation | New Service Connection Charge for PURBA MAGURMARI W/S Scheme, T/W No. V, under DHUPGURI CCC, [APPLICATION NO. 4003018653, Reference ID : 402927251] |  |  | BILL/00038/2022-2023 | BP/22-23/131 | 20/01/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. | SM/09564 | Augmentation | New Service Connection Charge for PURBA MAGURMARI W/S Scheme, T/W No. IV, under DHUPGURI CCC, [APPLICATION NO. 4003018663, Reference ID : 402928488] |  |  | BILL/00040/2022-2023 | BP/22-23/131 | 20/01/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. | SM/09564 | Augmentation | Infrastructure Cost for PURBA MAGURMARI W/S Scheme, T/W No. IV, under DHUPGURI CCC, [APPLICATION NO. 100000066800, Reference ID : 860257020] |  |  | BILL/00041/2022-2023 | BP/22-23/131 | 20/01/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.93 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. | SM/09564 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 4th Tube well site for Purba Magurmari P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000503/2021-2022 | 104/JD | 11/01/2022 | 12/03/2022 | LOKNATH CONSTRUCTION | 4.65 | 4.78 | 102.73 | 1
8 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. | SM/09564 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 5th Tube well site for Purba Magurmari P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000506/2021-2022 | 105/JD | 11/01/2022 | 12/03/2022 | PRITAM DUTTA | 4.65 | 4.76 | 102.42 | 1
9 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. | SM/09564 | Augmentation | Shifting and repairing of damaged/chokage pipe line due to development, widening of roads and agricultural land related to L.D.S. within the command area of rejuvenation of Purba Magurmari P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000209/2022-2023 | 1799/JD | 14/09/2022 | 05/10/2022 | ARATI CONSTRUCTION | 4.85 | 4.87 | 100.38 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. | SM/09564 | Augmentation | Permanent restoration of G.I. lines across the small stream in two places along with others ancillary works related to distribution system, strengthening of valve chambers due to strengthening of village/PWD roads and culvert works in various places within the command area of rejuvenation of Purba Magurmari P.W.S.S. under Jalpaiguri Division,P.H.E. Dte.Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000210/2022-2023 | 1800/JD | 14/09/2022 | 05/10/2022 | ARATI CONSTRUCTION | 4.5 | 4.44 | 98.64 | 0
11 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. | SM/09564 | Augmentation | Infrastructure Cost for PURBO MAGURMARI, T/W IV, under DHUPGURI CCC, [APPLICATION NO. 100000086997, Reference ID : 860278198] |  |  | BILL/01067/2023-2024 | BP/23-24/108 | 30/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.63 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. | SM/09564 | Augmentation | Laying of Rising Main/Direct Boosting Line for The Rejuvenation of Purba Magurmari P.W.S.S and Rejuvenation of Chouhaddi P.W.S.S. along with FHTC(PhaseVII) within the command area of Rejuventaion of Purba Magurmari P.W.S.S. in connection with Jal Jeevan Mission under Jalpaiguri Division,P.H.E.Dte. |  |  | ORD/000397/2023-2024 | 1587/JD | 06/11/2023 | 06/12/2023 | SAHA CONSTRUCTION | 37.11 | 0 | 0 | 0
13 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. | SM/09564 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for PURBA MAGURMARI (REJU) PWSS, at TW no. IV, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000773/2022-2023 | 82/NMD | 27/01/2023 | 26/02/2023 | MIHIR SARKAR | 8 | 3.15 | 39.42 | 65
14 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. | SM/09564 | Augmentation | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under PURBA MAGURMARI (Reju) WS Scheme at TW No. IV in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000782/2022-2023 | 103/NMD | 03/02/2023 | 24/02/2023 | MIHIR SARKAR | 2.27 | 0.98 | 43.25 | 80
15 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. | SM/09564 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for PURBA MAGURMARI (REJU) PWSS, at TW no. V, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Driller-in-Charge | Junior Engineer | ORD/000578/2022-2023 | 1125/NMD | 12/09/2022 | 12/10/2022 | UTTAM PAUL | 8.01 | 2.65 | 33.09 | 60
16 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. | SM/09564 | Augmentation | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under PURBA MAGURMARI (Reju) WS Scheme at TW No. V in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD,Driller-in-Charge | Junior Engineer | ORD/000783/2022-2023 | 104/NMD | 03/02/2023 | 24/02/2023 | UTTAM PAUL | 2.27 | 0.84 | 36.81 | 50
Total | [13 empty] | 110.15 | 44.04 | 39.98