## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mainatali Piped Water Supply Scheme | SM/09565 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Mainatali P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000500/2021-2022 | 95/JD | 10/01/2022 | 11/03/2022 | ABHIJIT SARKAR | 4.65 | 4.68 | 100.61 | 100
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mainatali Piped Water Supply Scheme | SM/09565 | Augmentation | Sinking of 183 mm x 125mm dia tube well by ODEX-165 method of drilling for Rejuvenation of Mainatali PWSS at Dhupguri Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000450/2021-2022 | 198/JD | 21/01/2022 | 20/02/2022 | M/S BABUN BISWAS | 7.89 | 5.33 | 67.56 | 100
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mainatali Piped Water Supply Scheme | SM/09565 | Augmentation | Laying Rising Main at 3rd Tubewell site of Mainatali PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000059/2023-2024 | 324/JD | 18/05/2023 | 01/06/2023 | GANAPATI CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 4.64 | 2.39 | 51.6 | 50
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mainatali Piped Water Supply Scheme | SM/09565 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF MAINATALI PWSS, at TW NO III AND IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Driller-in-Charge | Junior Engineer | ORD/000893/2022-2023 | 392/NMD | 29/03/2023 | 01/04/2025 | BLUE PINE | 24.99 | 11.94 | 47.77 | 100
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mainatali Piped Water Supply Scheme | SM/09565 | Augmentation | Construction of Blower Room & IEP (40m3/hr.) of Mainatali PWSS, in connection with Rejuvenation of Mainatali PWSS under Jal Jeevan Mission at Dhupguri Block under Jalpaiguri Division, P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000510/2023-2024 | 1778/JD | 08/12/2023 | 06/02/2024 | D. S. ENTERPRISE | 16.9 | 15.26 | 90.29 | 75
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mainatali Piped Water Supply Scheme | SM/09565 | Augmentation | Infrastructure Cost for MAYNATALI, TW No. III, DHUPGURI CCC, [APPLICATION NO. 100000077915, Reference ID : 860269055] |  |  | BILL/00064/2023-2024 | BP/23-24/18 | 24/05/2023 | 24/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.27 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mainatali Piped Water Supply Scheme | SM/09565 | Augmentation | New Service Connection Charge for MAYNATALI, TW No. III, DHUPGURI CCC, [APPLICATION NO. 4003147727, Reference ID : 403014098] |  |  | BILL/00063/2023-2024 | BP/23-24/18 | 24/05/2023 | 24/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mainatali Piped Water Supply Scheme | SM/09565 | Augmentation | Construction of Boundary Wall, IEP Washout, Pathway, Drain etc. at 3rd TW Site for Mainatali PWSS icw JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000437/2024-2025 | 2314./JD | 11/12/2024 | 21/03/2025 | ABHIJIT SARKAR | 9.55 | 0 | 0 | 100
9 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mainatali Piped Water Supply Scheme | SM/09565 | Augmentation | New Service Connection Charge for MAINATALI, T/W-IV, under DHUPGURI CCC, [APPLICATION NO. 4003336981, Reference ID : 403161218] |  |  | BILL/02135/2023-2024 |  | 29/02/2024 | 29/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.18 | 0 | 0 | 0
10 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mainatali Piped Water Supply Scheme | SM/09565 | Augmentation | New Service Connection Charge for Rejuvenation of Mainatali, T/W-IV under DHUPGURI CCC APPLICATION NO. 4003336981 Reference ID :- 403161218 |  |  | BILL/00209/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.18 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mainatali Piped Water Supply Scheme | SM/09565 | Augmentation | Additional New Service Connection Charge for REJUVENATION OF MAINATALI PWSS, at TW NO IV, under DHUPGURI CCC APPLICATION NO. 100000113878 Reference ID : 860306078 |  |  | BILL/00642/2024-2025 | BP/24-25/156 | 06/08/2024 | 06/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.74 | 0 | 0 | 0
12 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mainatali Piped Water Supply Scheme | SM/09565 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
13 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mainatali Piped Water Supply Scheme | SM/09565 | Augmentation | Additional New Service Connection Charge for REJUVENATION OF MAINATALI PWSS, at TW NO IV, under DHUPGURI CCC APPLICATION NO. 100000133512 Reference ID : 860331002 |  |  | BILL/00317/2025-2026 |  | 19/05/2025 | 19/05/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.4 | 0 | 0 | 0
Total | [13 empty] | 173.08 | 39.59 | 22.88