## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/09858 | Augmentation | Sinking of Two Nos. 183 mm x 125 mm dia 120 m deep Tube well by ODEX-165 drilling Method of Rejuvenation of water supply scheme for Nagaisuree Tea Garden under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000008/2022-2023 | 869/JD | 04/04/2022 | 04/05/2022 | UNIBRO INFRASERV PRIVATE LIMITED | 13.85 | 12.19 | 88.03 | 0
2 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/09858 | Augmentation | Installation of Infrastructure COST at NAGAISUREE TEA GARDEN NEAR TANKI LINE W/S SCHEME, T/W No. I, under MATELLI CCC, [APPLICATION NO. 100000059931, Reference ID : 860249351] |  |  | VCH/000976/2022-2023 | BP/22-23/90 | 01/11/2022 | 01/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.16 | 0 | 0 | 0
3 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/09858 | Augmentation | New Service Connection Charge for NAGAISUREE TEA GARDEN NEAR TANKI LINE W/S SCHEME, T/W No. I, under MATELLI CCC, [APPLICATION NO. 4002964334, Reference ID :402851949] |  |  | VCH/000975/2022-2023 | BP/22-23/90 | 01/11/2022 | 01/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/09858 | Augmentation | Installation of Infrastructure COST at NAGAISUREE TEA GARDEN NEAR MANDAKINI FIELD W/S SCHEME, T/W No. II, under MATELLI CCC, [APPLICATION NO. 100000059480, Reference ID : 860249200] |  |  | VCH/000978/2022-2023 | BP/22-23/90 | 01/11/2022 | 01/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.17 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/09858 | Augmentation | New Service Connection Charge for NAGAISUREE TEA GARDEN NEAR MANDAKINI FIELD W/S SCHEME, T/W No. II, under MATELLI CCC, [APPLICATION NO. 4002964306, Reference ID :402851943] |  |  | VCH/000977/2022-2023 | BP/22-23/90 | 01/11/2022 | 01/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/09858 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF NAGAISUREE TG AREA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000765/2022-2023 | 71/NMD | 27/01/2023 | 26/02/2023 | TALUKDER ENTERPRISE | 11.31 | 11.31 | 100 | 100
7 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/09858 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 4th tube well site for Nagaisuree TG P.W.S.S. under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000269/2022-2023 | 217/JSSD | 16/09/2022 | 15/11/2022 | ARUP SARKAR | 4.65 | 4.65 | 100 | 100
8 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/09858 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 3rd tube well site for Nagaisuree TG P.W.S.S. under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000270/2022-2023 | 216/JSSD | 16/09/2022 | 15/11/2022 | BAJRANG ENTERPRISE | 4.65 | 4.65 | 100 | 0
9 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/09858 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF NAGAISUREE TG AREA PWSS, TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000766/2022-2023 | 72/NMD | 27/01/2023 | 26/02/2023 | M/S PALIDEB ENGINEERING WORKS | 10.76 | 10.76 | 100 | 80
10 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/09858 | Augmentation | Construction of different for Rejuvenation of Nagaisuree Tea Garden Piped Water Supply Scheme i.e. 2 (Two) Nos Pump House, Boundary Wall, Rising Main including Functional Household Tap Connection (FHTC) etc. in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000182/2025-2026 | 2165/JD | 30/10/2025 | 14/12/2025 | PRASENJIT BASAK | 30.87 | 0 | 0 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/09858 | Augmentation | Retrofitting works for laying Distribution System of Rejuvenation of Nagaisuree T.G. Area piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000700/2021-2022 | 767/JD | 23/03/2022 | 11/05/2025 | SADHAN KARMAKAR | 64.75 | 50.42 | 77.87 | 60
Total | [13 empty] | 146.53 | 93.98 | 64.14