## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | SM/09859 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Carron T.G piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-II) |  | Junior Engineer | ORD/000197/2021-2022 | 470/JSSD | 05/10/2021 | 20/10/2021 | SANDIP BANIK | 4.63 | 9.07 | 195.91 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | SM/09859 | Augmentation | Construction of Boundary wall with gate, drain and pathway for 4th tube well site at Caron T.G. P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000727/2021-2022 | 1042/JSSD | 24/01/2022 | 13/02/2022 | SK. MOBIN HUSSAIN | 3.75 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | SM/09859 | Augmentation | Sinking of Two Nos. 183 mm x 125 mm dia 120 m deep Tube well by ODEX-165 drilling Method of Rejuvenation of water supply scheme of Caron Tea Garden under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000009/2022-2023 | 870/JD | 04/04/2022 | 04/05/2022 | UNIBRO INFRASERV PRIVATE LIMITED | 13.85 | 13.46 | 97.22 | 100
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | SM/09859 | Augmentation | Continuation Order for the work "Supply of (one) Maxi Cab with engine capacity more than 2000 C.C on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Sub-Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi Permit)" from 01.01.2023 to 31.03.2023 | Assistant Engineer | Junior Engineer | ORD/000368/2022-2023 | 348/JSSD | 27/12/2022 | 27/03/2023 | TANMOY CHOUDHURY | 0.44 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | SM/09859 | Augmentation | Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Caron T.G. P.W.S.S under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001127/2021-2022 | 1011/W/JSSD | 27/01/2022 | 02/01/2025 | GOURAB GUHA ROY | 3.76 | 0 | 0 | 100
6 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | SM/09859 | Augmentation | Continuation Order for the work "Supply of 1 (one) Maxi Cab with engine capacity more than 2000 C.C. on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi permit) from 01.01.2023 to 31.03.2023 |  |  | ORD/000597/2022-2023 | 348/JSSD | 27/12/2022 | 27/03/2023 | TANMOY CHOUDHURY | 0.45 | 0.06 | 13.62 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | SM/09859 | Augmentation | Construction of Pump House (3.60 M X 2.40 M)size with sanitary & plumbing arrangement at 3rd Tube-Well site for Caron T.G.PWSS under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000893/2021-2022 | 1027/W/JSSD | 31/01/2022 | 17/11/2024 | SARKAR ASSOCIATES | 4.64 | 4.64 | 100 | 100
8 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | SM/09859 | Augmentation | Repairing of Pump House ( 1st site ), boundary wall ( 1st site ) and other Allied works at CARRON Piped Water Supply Scheme under Jalpaiguri Division ,P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000114/2022-2023 | 112/JSSD | 27/07/2022 | 11/08/2022 | SANDIP BANIK | 4.75 | 3.32 | 69.94 | 100
9 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | SM/09859 | Augmentation | Continuation Order for the work "Supply of (one) Maxi Cab with engine capacity more than 2000 C.C on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Sub-Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi Permit)" from 01.04.2023 to 30.04.2023. |  |  | ORD/000510/2022-2023 | 503/JSSD | 30/03/2023 | 29/04/2023 | TANMOY CHOUDHURY | 0.15 | 0.24 | 162.76 | 0
10 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | SM/09859 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CARON TG PWSS, TW No III AND IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000856/2023-2024 | 1811/NMD | 31/10/2023 | 01/10/2026 | M/S B.ENTERPRISE | 30.99 | 9.39 | 30.3 | 85
11 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | SM/09859 | Augmentation | Laying Rising Main for Rejuvenation of Carron Tea Garden piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000481/2022-2023 | 800/JD.. | 29/03/2023 | 02/12/2024 | TECHNO CRACY | 2.84 | 1.89 | 66.5 | 100
12 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | SM/09859 | Augmentation | Supply of fuel |  |  | BILL/00209/2023-2024 | BP-2023-24-117 | 01/06/2023 | 01/06/2023 | FILL & SMILE | 0.66 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | SM/09859 | Augmentation | Construction of different components of rejuvenation of Carron Tea Garden PWSS at 4th TW site i.e. Steel staging OHR, Water Distribution Network, FHTC, interconnection, etc. in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000036/2024-2025 | 939/JD | 07/08/2024 | 02/04/2026 | SANKAR DAS | 15.03 | 0 | 0 | 90
14 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | SM/09859 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2024-2025 | 2096/JD | 25/11/2024 | 25/11/2024 | Resource Division | 5.22 | 0 | 0 | 0
15 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | SM/09859 | Augmentation | New Service Connection Charge for CARON TEA GARDEN, T/W No. IV, under NAGRAKATA CCC, [APPLICATION NO. 4003320133, Reference ID : 403147059] |  |  | BILL/01935/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
16 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | SM/09859 | Augmentation | New Service Connection Charge for CARON, T/W-III, under NAGRAKATA CCC, [APPLICATION NO. 4003352267, Reference ID : 403172839] |  |  | BILL/02136/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
17 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | SM/09859 | Augmentation | Infrastructure Cost for CARON TEA GARDEN, T/W No. IV, under NAGRAKATA CCC, [APPLICATION NO. 100000098886, Reference ID : 860291136] |  |  | BILL/01936/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.52 | 0 | 0 | 0
18 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | SM/09859 | Augmentation | Infrastructure Cost for CARON, T/W-III, under NAGRAKATA CCC, [APPLICATION NO. 100000101246, Reference ID : 860293456] |  |  | BILL/02137/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.21 | 0 | 0 | 0
19 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | SM/09859 | Augmentation | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  | Junior Engineer | ORD/001135/2024-2025 | 51/DSD | 10/03/2025 | 25/03/2025 | D.K. & SONS | 1.23 | 0 | 0 | 0
20 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | SM/09859 | Augmentation | Laying of dedicated DI pipeline from Carron 3rd TW site pump to Matu line at Carron TG Piped W/S Scheme in connection with JJM at Nagrakata Block, under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000047/2025-2026 | 77/JSSD | 30/05/2025 | 29/06/2025 | PRIYABRATA KARMAKAR | 3.73 | 0 | 0 | 100
Total | [13 empty] | 106.32 | 42.06 | 39.57