## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | Replacement of existing defunct sluice valve for Gairkata Water Supply Scheme at Banarhat Development block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000027/2023-2024 | 127/JD | 28/04/2023 | 05/05/2023 | SHANTI CONSTRUCTION | 1.66 | 0 | 0 | 100
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2021-2022 | 554/JD | 01/03/2022 | 01/03/2022 | Resource Division | 14.26 | 0 | 0 | 0
3 | JALPAIGURI |  | Northern Mechanical | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | New Service Connection Charge for GAIRKATA, T/W I, under DHUPGURI CCC [APPLICATION NO. 4003208335 ; Reference ID : 403057217] |  |  | BILL/00990/2023-2024 | BP/23-24/93 | 29/08/2023 | 29/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.44 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | New Service Connection Charge for GAIRKATA, T/W II, under DHUPGURI CCC [APPLICATION NO. 4003208338 ; Reference ID : 403057218] |  |  | BILL/00991/2023-2024 | BP/23-24/93 | 29/08/2023 | 29/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.94 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | New Service Connection Charge for GAIRKATA, T/W III, under DHUPGURI CCC, [APPLICATION NO. 4003196195, Reference ID : 403048167] |  |  | BILL/00569/2023-2024 | BP/23-24/70 | 09/08/2023 | 09/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.42 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | Laying Distribution System including providing CI/DI Rising Main connection and providing FHTC in connection with JJM for Augmentation of Gairkata Piped Water Supply Scheme at Banarhat Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000442/2022-2023 | 695/JD | 17/03/2023 | 16/03/2025 | M/S R.N. TRADERS | 333.21 | 0 | 0 | 8
7 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | Sinking of 250mm x 150mm dia tubewell by Reverse Rotary method of drilling for Augmentation of Gairkata PWSS at Dhupguri Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000563/2021-2022 | 455/JD | 18/02/2022 | 11/03/2022 | MAA ENTERPRISES | 7.93 | 0 | 0 | 100
8 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 3rd tube well site for Augmentation Gairkata P.W.S.S under Jalpaiguri Division P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000049/2022-2023 | 1191/JD | 20/05/2022 | 04/07/2022 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 4.65 | 0 | 0 | 100
9 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | Construction of Boundary Wall, Sluice Valve, Pathway, Drain etc. at 3rd Tube Well Site of Gairkata Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000495/2024-2025 | 2057/JD | 25/11/2024 | 31/12/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 8.51 | 0 | 0 | 60
10 | JALPAIGURI |  | Northern Mechanical | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001041/2024-2025 | 29/NMD | 06/01/2025 | 05/02/2025 | DIAMOND ELECTRICAL WORKS | 12.26 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | Installation of two tank chlorination system at different water supply scheme UNDER JJM under BANARHAT Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Driller-in-Charge |  | ORD/001136/2024-2025 | 52/DSD | 10/03/2025 | 25/03/2025 | D.K. & SONS | 1.39 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | Rejuvenation of different components of PWSS of Over Head Reservoir site at Gairkata Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000546/2023-2024 | 1974/JD | 03/01/2024 | 01/06/2025 | APEX ENGINEERING | 22.45 | 0 | 0 | 50
13 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | Rejuvenation of 2nd Tube Well Site, 3rd Tube Well Site and Head Work Site Pump House at Gairkata Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000498/2024-2025 | 2390/JD | 19/12/2024 | 01/04/2025 | BISHAL DAS | 2.48 | 0 | 0 | 100
Total | [13 empty] | 420.6 | 0 | 0