## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme | SM/09861 | Augmentation | Shifting of DI pipeline due to widening of road of Purba Salbari Area Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000154/2022-2023 | 1534/JD | 02/08/2022 | 17/08/2022 | ABHIJIT SARKAR | 1.52 | 0 | 0 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme | SM/09861 | Augmentation | Repairing of 2 nos. of Pump House (Head Work site & 2nd site) ( 3.60M X 2.40M ) Size with sanitary & plumbing arrangement and other allied works at Purba Salbari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000641/2020-2021 | 251/JD | 19/02/2021 | 21/03/2021 | ABHIJIT SARKAR | 4.85 | 0 | 0 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme | SM/09861 | Augmentation | CONST H/W BHANGARHAT WSS |  |  | VCH/001371/2021-2022 | BP-2021-22-516 | 30/03/2022 | 30/03/2022 | SAHA CONSTRUCTION | 4.83 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme | SM/09861 | Augmentation | Sinking of 250mm x 150mm dia tubewell by Reverse Rotary method of drilling for Rejuvenation of Purba Salbari PWSS at Dhupguri Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000475/2021-2022 | 349/JD | 22/02/2022 | 15/03/2022 | ABHIJIT SARKAR | 7.97 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme | SM/09861 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 3rd tube well site for Rejuvenation Purba Salbari P.W.S.S. under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000212/2022-2023 | 1802/JD | 14/09/2022 | 05/10/2022 | ABHIJIT SARKAR | 4.65 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme | SM/09861 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2021-2022 | 553/JD | 01/03/2022 | 01/03/2022 | Resource Division | 39.86 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme | SM/09861 | Augmentation | FUEL BILL |  |  | VCH/000665/2022-2023 | BP-2022-23-350 | 09/12/2022 | 09/12/2022 | FILL & SMILE | 0.62 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Purbba Salbari Piped Water Supply Scheme | SM/09861 | Augmentation | New Service Connection Charge for JURAPANI,SALBARI W/S Scheme, T/W No. III, under DHUPGURI CCC, [APPLICATION NO. 4003018659, Reference ID : 402928489] |  |  | BILL/00036/2022-2023 | BP/22-23/128 | 20/01/2023 | 20/01/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Purbba Salbari Piped Water Supply Scheme | SM/09861 | Augmentation | Infrastructure Cost for JURAPANI,SALBARI W/S Scheme, T/W No. III, under DHUPGURI CCC, [APPLICATION NO. 100000066802, Reference ID : 860257022] |  |  | BILL/00037/2022-2023 | BP/22-23/128 | 20/01/2023 | 20/01/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.01 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme | SM/09861 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna including retrofitting of Laying Distribution System for Rejuvenation of Purba Salbari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000003/2022-2023 | 879/JD | 05/04/2022 | 01/11/2022 | M/S GARGO TRADERS | 417.6 | 0 | 0 | 64
11 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Purbba Salbari Piped Water Supply Scheme | SM/09861 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for PURBA SALBARI (REJU) PWSS, at TW no. III, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000579/2022-2023 | 1124/NMD | 12/09/2022 | 12/10/2022 | DIAMOND ELECTRICAL WORKS | 8.02 | 0 | 0 | 100
12 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme | SM/09861 | Augmentation | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing for Rejuvenation of Purba Salbari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000201/2022-2023 | 1964/JD | 18/10/2022 | 16/04/2023 | SAHA CONSTRUCTION | 69.07 | 0 | 0 | 60
13 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Purbba Salbari Piped Water Supply Scheme | SM/09861 | Augmentation | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under PURBA SALBARI (Reju) WS Scheme at TW No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000784/2022-2023 | 105/NMD | 03/02/2023 | 24/02/2023 | DIAMOND ELECTRICAL WORKS | 2.27 | 0 | 0 | 100
14 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme | SM/09861 | Augmentation | Laying Rising Main at 3rd Tubewell site of Purba Salbari PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000057/2023-2024 | 323/JD | 18/05/2023 | 01/06/2023 | ABHIJIT SARKAR | 4.59 | 0 | 0 | 80
15 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme | SM/09861 | Augmentation | Construction of different components of Rejuvenation of Purba Salbari PWSS i.e. RISING MAIN, Boundary wall etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000039/2024-2025 | 986/JD | 14/08/2024 | 01/04/2026 | SAHA CONSTRUCTION | 29.57 | 0 | 0 | 50
16 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme | SM/09861 | Augmentation | Balance Laying Distribution System with Providing Functional House Hold Tap Connection in connection with JJM at Purbba Salbari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000008/2025-2026 | 677/JD | 04/04/2025 | 19/05/2025 | A P CONSTRUCTION | 36.26 | 0 | 0 | 0
Total | [13 empty] | 637.06 | 0 | 0